## 1 PACKAGE OWNERS
INPUT | OUTPUT
PRECON | [20 empty] | OPS
Package Description | Package Code | Stage | Date Transmitted | Owner | Ready For BJ | Drawing Loaded in CMiC | Detail Book Loaded in CMiC | RFI slipsheets to add to CMiC Subfolder? | In BB Studio? | Bookmarking & Hyperlinking Complete? | Have all prior versions been superceded? | Allow Public Access (Posted to Public Side) | Status Updated | Notes | Actively Down? ("Y" or Blank if No) | Actively Down By Whom? | Package Identifier | Manual Override (Currently in Pkg Compare) | Currently in Pkg Compare | Duplicate Package Code | Owner | Hand-Off Date | Notes
CPK01 | CPK01 | IFC | 2021-07-19 | Max | Y - MP | Y | NONE |  | Y |  |  |  | 2022-03-23 | Sheets beginning in RA4-SS-20A-D0000 revised |  |  | CPK01-IFC |  | N - ADD | FALSE | Drew | 2021-12-06
CPK01-R1 | CPK01-R1 | IFC | 2021-08-03 | Ernesto | Y | Y | NONE |  | Y |  |  |  | 2022-03-23 |  |  |  | CPK01-R1-IFC |  | N - ADD | FALSE | Drew | 2021-12-06
CPK01-R2 | CPK01-R2 | IFC | 2021-09-08 | Max | Y - MP | Y | Y |  | Y |  |  |  | 2022-03-23 |  |  |  | CPK01-R2-IFC |  | N - ADD | FALSE | Drew | 2021-12-06
CPK02 | CPK02 | IFC | 2021-09-24 | Ernesto | Y | Y | Y | 0164 | Y |  |  |  | 2022-03-23 |  |  |  | CPK02-IFC |  | N - ADD | TRUE | Jon S | 2022-02-04
CPK02-R1_(UST) | CPK02-R1 | IFC | 2021-11-02 | Taylor | Y | Y | Y |  | Y |  |  |  | 2022-03-23 |  |  |  | CPK02-R1-IFC |  | N - ADD | TRUE | Jon S | 2022-02-04
CPK02-R2 | CPK02-R2 | IFC | 2021-11-27 | Ernesto | Y | Y | Y | 0044, 0128R1, 0132, 0242, 0245, 0263 | Y |  |  |  | 2022-03-23 |  |  |  | CPK02-R2-IFC |  | N - ADD | TRUE
CPK02-R2_Add01 | CPK02-R2-ADD01 | IFC | 2021-11-29 | Ernesto | N/A |  |  |  | Y |  |  |  | 2022-03-23 | No need to incorporate into IFC drawing set |  |  | CPK02-R2-ADD01-IFC | N/A | N/A | TRUE
CPK02-R2_Add02 | CPK02-R2-ADD02 | IFC | 2021-11-30 | Ernesto | Y | Y | NONE |  | Y |  |  |  | 2022-03-23 | Incorporated into IFC drawing set |  |  | CPK02-R2-ADD02-IFC | N/A | N/A | TRUE
CPK02-R3 | CPK02-R3 | IFC | 2021-12-16 | Taylor | Y | Y | Y |  | Y |  | Y - BC - 2/23/2022 |  | 2022-03-23 |  |  |  | CPK02-R3-IFC |  | N - ADD | TRUE
CPK02-R4 | CPK02-R4 | IFC | 2022-01-17 | Ernesto | Y | Y | Y | 0246 | Y |  |  |  | 2022-03-23 |  |  |  | CPK02-R4-IFC |  | N - ADD | TRUE
CPK03-R12_90 | CPK03-R12 | IFC | 2022-03-21 | Max | [12 empty] | CPK03-R12-IFC |  |  | TRUE
CPK02-R5 | CPK02-R5 | IFC | 2022-01-21 | Taylor | Y | Y | Y |  | Y |  |  |  | 2022-03-23 |  |  |  | CPK02-R5-IFC |  | N - ADD | TRUE
CPK02-R6 | CPK02-R6 | IFC | 2022-02-02 | Ernesto | Y | Y | Y |  | Y |  | Y - BC - 2/28/2022 |  | 2022-03-23 |  |  |  | CPK02-R6-IFC |  | N - ADD | TRUE
CPK02-R7 | CPK02-R7 | IFC | 2022-02-21 | Taylor | Y | Y | Y |  | Y |  | Y - BC - 2/24/2022 |  | 2022-03-23 |  |  |  | CPK02-R7-IFC |  | N - ADD | TRUE
CPK02-R8 | CPK02-R8 | IFC | 2022-02-25 | Ernesto | Y - TP | Y | Y |  | Y |  |  |  | 2022-03-23 |  |  |  | CPK02-R8-IFC |  | N - ADD | TRUE
CPK03 | CPK03 | IFC | 2021-09-24 | Max | Y - MP | Y | Y - PM |  | Y |  |  |  | 2022-03-23 |  |  |  | CPK03-IFC |  | Y | TRUE | Drew | 2022-02-04
CPK03-R1_(UST) | CPK03-R1 | IFC | 2021-11-02 | Max | Y - MP | Y | Y - PM |  | Y |  |  |  | 2022-03-23 |  |  |  | CPK03-R1-IFC |  | Y | TRUE
CPK03-R10 | CPK03-R10 | IFC | 2022-02-23 | Max | Y - MP | Y |  |  | Y |  |  |  | 2022-03-23 |  |  |  | CPK03-R10-IFC |  | Y | TRUE
CPK03-R11_IFC | CPK03-R11 | IFC | 2022-03-04 | Max | Y - MP | Y |  |  | Y |  |  |  | 2022-03-23 |  |  |  | CPK03-R11-IFC |  | Y | TRUE
CPK03-R11_Add-01 | CPK03-R11-ADD01 | IFC | 2022-03-16 | Max | Y - MP | Y |  |  | Y |  |  |  | 2022-03-23 |  |  |  | CPK03-R11-ADD01-IFC |  | Y | FALSE
CPK03-R1_(UST)_Add01 | CPK03-R1-ADD01 | IFC | 2021-11-16 | Max | Y - MP |  |  |  | Y |  |  |  | 2022-03-23 | Detail book added |  |  | CPK03-R1-ADD01-IFC | N/A | N/A | FALSE
CPK03-R2 | CPK03-R2 | IFC | 2021-11-28 | Max | Y - MP | Y | Y - PM | Y | Y |  |  |  | 2022-03-23 |  |  |  | CPK03-R2-IFC |  | Y | TRUE
CPK03-R2_Add01 | CPK03-R2-ADD01 | IFC | 2021-11-29 | Max | Y - MP |  |  | Y | Archived |  |  |  | 2022-03-23 | Navis Model |  |  | CPK03-R2-ADD01-IFC | N/A | N/A | TRUE
CPK03-R2_Add02 | CPK03-R2-ADD02 | IFC | 2021-12-28 | Connor | N/A |  |  |  | Archived |  |  |  | 2022-03-23 | Only RVT |  |  | CPK03-R2-ADD02-IFC | N/A | N/A | FALSE
CPK07_AT | CPK07 | 60 | 2021-12-15 | Ernesto |  |  |  |  | Archived |  |  | Y | 2021-12-28 |  |  |  | CPK07-60 |  | N | TRUE
CPK03-R3 | CPK03-R3 | IFC | 2021-12-24 | Connor | Y - MP | Y | Y - PM |  | Y |  |  |  | 2022-03-23 | No Cover Page |  |  | CPK03-R3-IFC |  | Y | TRUE
CPK03-R4 | CPK03-R4 | IFC | 2021-10-13 | Max | Y - MP | Y | N/A - PM |  | Y |  |  |  | 2022-03-23 |  |  |  | CPK03-R4-IFC |  | Y | TRUE
CPK03-R5 | CPK03-R5 | IFC | 2021-11-24 | Connor | Y - MP | Y | Y - PM |  | Y |  |  |  | 2022-03-23 |  |  |  | CPK03-R5-IFC |  | Y | TRUE
CPK03-R6 | CPK03-R6 | IFC | 2021-12-28 | Max | Y - MP | Y | Y - PM |  | Y |  | Y - BC - 2/23/2022 |  | 2022-03-23 |  |  |  | CPK03-R6-IFC |  | Y | TRUE
CPK03-R7 | CPK03-R7 | IFC | 2022-01-17 | Max | Y - MP | Y |  |  | Y |  |  |  | 2022-03-23 |  |  |  | CPK03-R7-IFC |  | Y | TRUE
CPK03-R8 | CPK03-R8 | IFC | 2022-01-22 | Connor | Y - MP | Y |  |  | Y |  |  |  | 2022-03-23 |  |  |  | CPK03-R8-IFC |  | Y | TRUE
CPK02-R5_AT | CPK02-R5 | 90 | 2022-01-06 | Taylor | Y |  |  |  | Archived |  |  | Y | 2022-01-07 |  |  |  | CPK02-R5-90 |  | N | TRUE
CPK03-R9 | CPK03-R9 | IFC | 2022-02-03 | Connor | Y - MP | Y |  |  | Y |  |  |  | 2022-03-23 |  |  |  | CPK03-R9-IFC |  | Y | TRUE
CPK02-R6_AT | CPK02-R6 | 90 | 2022-01-13 | Ernesto |  |  |  |  | Archived |  |  | Y | 2022-01-14 |  |  |  | CPK02-R6-90 |  | N | TRUE
CPK03-R9_AT | CPK03-R9 | 90 | 2022-01-13 | Connor |  |  |  |  | Archived |  |  | Y | 2022-01-11 |  |  |  | CPK03-R9-90 |  | N | TRUE
LLE01-R2_AT | LLE01-R2 | 90 | 2022-01-14 | Max |  |  |  |  | Archived |  |  |  | 2022-02-14 |  |  |  | LLE01-R2-90 |  | N | TRUE
CPK04 | CPK04 | IFC | 2021-12-09 | Max | Y - MP | Y |  |  | Y |  |  |  | 2022-03-23 |  |  |  | CPK04-IFC |  | N - ADD | TRUE | David Philips/Patrick McCarthy | 2021-12-14 | Per conversation
CPK04-R1 | CPK04-R1 | IFC | 2022-02-04 | Ernesto | Y - CH | Y |  |  | Y |  |  |  | 2022-03-23 |  |  |  | CPK04-R1-IFC |  | N - ADD | TRUE | David Philips/Patrick McCarthy | 2022-02-14 | Per conversation
CPK04-R2 | CPK04-R2 | IFC | 2022-02-25 | Max | Y - MP | Y |  |  | Y | Y | N |  | 2022-03-23 |  |  |  | CPK04-R2-IFC |  | N - ADD | TRUE | David Philips/Patrick McCarthy | 2022-02-14 | Per conversation
CPK04-R1_AT | CPK04-R1 | 90 | 2022-01-21 | Max |  |  |  |  | Archived |  |  | Y | 2022-02-14 |  |  |  | CPK04-R1-90 |  | N | TRUE | David Philips/Patrick McCarthy | 2022-02-14 | Per conversation
CPK05_AT | CPK05 | 60 | 2022-01-21 | Ernesto |  |  |  |  | Y |  |  |  | 2022-01-24 |  |  |  | CPK05-60 |  | N | TRUE
CPK04-R3_AT | CPK04-R3 | IFC | 2022-03-02 | Max | Y - MP | Y |  |  | Y | Y |  |  | 2022-03-23 |  |  |  | CPK04-R3-IFC |  | N - ADD | TRUE | David Philips/Patrick McCarthy | 2022-02-14 | Per conversation
CPK06-R1_AT | CPK06-R1 | 90 | 2022-01-24 | Connor |  |  |  |  | Archived |  |  | Y | 2022-02-14 | only electrical |  |  | CPK06-R1-90 |  | N | TRUE
CPK04-R5_AT | CPK04-R5 | IFC | 2022-03-17 | Connor | Y - MP | Y |  |  | Y |  |  |  | 2022-03-23 | Just Navis files and ISAT Pipe suppport |  |  | CPK04-R5-IFC |  | N - ADD | TRUE
CPK02-R7_AT | CPK02-R7 | 90 | 2022-01-28 | Taylor | Y |  |  |  | Archived |  |  | Y | 2022-01-31 |  |  |  | CPK02-R7-90 |  | N | TRUE
CPK03-R10_AT | CPK03-R10 | 90 | 2022-01-28 | Connor |  |  |  |  | N |  |  | Y | 2022-01-31 |  |  |  | CPK03-R10-90 |  | N | TRUE
CPK07_AT | CPK07 | 90 | 2022-01-28 | Ernesto |  |  |  |  | Archived |  |  |  | 2022-01-31 | Uploaded |  |  | CPK07-90 |  | N | TRUE
CPK05 | CPK05 | IFC | 2022-03-24 | Ernesto | [8 empty] | 2022-03-25 | Working on uploading to BB Studio
CPK06 | CPK06 | IFC | 2022-01-12 | Connor | Y - MP | Y |  |  | Y |  |  |  | 2022-03-23 |  |  |  | CPK06-IFC |  | N - ADD | TRUE
CPK06-R1_AT | CPK06-R1 | IFC | 2022-02-01 | Connor | Y - MP | Y |  |  | Y |  |  |  | 2022-03-23 |  |  |  | CPK06-R1-IFC |  | N - ADD | TRUE
CPK03-R10_AT ISAT | CPK03-R10-ISAT | 90 | 2022-02-04 | Max |  |  |  |  | Y |  |  | Y | 2022-02-23 |  |  |  | CPK03-R10-ISAT-90 |  | N | FALSE
CPK07 | CPK07 | IFC | 2022-02-23 | Ernesto | Y - MP | Y |  |  | Y |  |  |  | 2022-03-23 |  |  |  | CPK07-IFC |  | N - ADD | TRUE
CPK04-R2 | CPK04-R2 | 90 | 2022-02-07 | Max |  |  |  |  | Y |  |  | Y | 2022-02-14 |  |  |  | CPK04-R2-90 |  | N | TRUE | David Philips/Patrick McCarthy | 2022-02-14 | Per conversation
CPK02-R8_AT | CPK02-R8 | 90 | 2022-02-08 | Ernesto |  |  |  |  | Archived |  |  | Y | 2022-02-14 |  |  |  | CPK02-R8-90 |  | N | TRUE
CPK03-R11_AT90 | CPK03-R11 | 90 | 2022-02-11 | Max |  |  |  |  | Y |  |  | Y | 2022-02-14 |  |  |  | CPK03-R11-90 |  | N | TRUE
CPK04-R3_AT | CPK04-R3 | 90 | 2022-02-11 | Connor |  |  |  |  | N |  |  | Y | 2022-02-14 |  |  |  | CPK04-R3-90 |  | N | TRUE | David Philips/Patrick McCarthy | 2022-02-14 | Per conversation
CPK07_AT_Add01 | CPK07-ADD01 | IFC | 2022-02-25 | Ernesto | Y - MP | Y |  |  | Y |  |  |  | 2022-03-23 | Uploaded (Cover Sheet replaced) |  |  | CPK07-ADD01-IFC | N/A | N/A | FALSE
CPK07-R1 | CPK07-R1 | IFC | 2022-03-18 | Taylor | Y | Y |  |  | Y |  |  |  | 2022-03-23 |  |  |  | CPK07-R1-IFC |  | N - ADD | TRUE
LLE01 | LLE01 | IFC | 2021-07-20 | Connor | Y - MP | Y |  |  | Y |  |  |  | 2022-03-23 |  |  |  | LLE01-IFC |  | Y | TRUE | Drew | 2021-11-05
LLE01-R1 | LLE01-R1 | IFC | 2021-10-08 | Connor | Y - MP | Y |  |  | Y |  |  |  | 2022-03-23 |  |  |  | LLE01-R1-IFC |  | Y | TRUE | Jeremy Friedrichs | 2022-02-04
LLE01-R2_AT | LLE01-R2 | IFC | 2022-01-25 | Connor | Y - MP | NONE |  |  | Y |  |  |  | 2022-03-23 |  |  |  | LLE01-R2-IFC | N/A | N/A | TRUE | Jeremy Friedrichs | 2022-02-04
LLP02 | LLP02 | IFC | 2021-08-20 | Connor | Y - MP | Y |  |  | Y |  |  |  | 2022-03-23 |  |  |  | LLP02-IFC |  | Y | TRUE | Jeremy Friedrichs | 2022-02-04
LLP02-R1 | LLP02-R1 | IFC | 2021-10-08 | Connor | Y - MP | Y |  |  | Y |  |  |  | 2022-03-23 |  |  |  | LLP02-R1-IFC |  | Y | TRUE | Jeremy Friedrichs | 2021-12-06
CPK07-R1_AT | CPK07-R1 | 90 | 2022-03-03 | Taylor | Y |  |  |  | Y | [7 empty] | CPK07-R1-90 |  | N | TRUE
LLP03 | LLP03 | IFC | 2021-10-26 | Max | Y - MP | Y |  |  | Y |  |  |  | 2022-03-23 |  |  |  | LLP03-IFC |  | Y | FALSE | Phil | 2021-12-06
CPK04-R5_AT | CPK04-R5 | 90 | 2022-03-04 | Connor |  |  |  |  | Archived | [7 empty] | CPK04-R5-90 |  | N | TRUE
CPK05_AT | CPK05 | 90 | 2022-03-11 | Ernesto |  |  |  |  | Y |  |  |  | 2022-03-14 |  |  |  | CPK05-90 |  | N | TRUE
CPK03-R12_90 | CPK03-R12 | 90 | 2022-03-15 | Connor | N/A |  |  |  | Y |  |  |  | 2022-03-15 |  |  |  | CPK03-R12-90 |  | N | TRUE
LLP04 | LLP04 | IFC | 2021-12-21 | Taylor | Y | Y |  |  | Y |  |  |  | 2022-03-23 |  |  |  | LLP04-IFC |  | Y | TRUE | Phil | 2022-01-03
MS01 | MS01 | IFC | 2021-07-02 | Taylor | Y |  |  |  | Y |  |  |  | 2022-03-23 | Revised by MS01-R1 |  |  | MS01-IFC |  | Y | FALSE | Phil | 2021-12-06
CPK04-R6_AT | CPK04-R6 | 90 | 2022-03-18 | Connor | Y | Y |  |  | Y |  |  |  | 2022-03-18 | Just Navis files and ISAT Pipe suppport |  |  | CPK04-R6-90 |  | N | FALSE
MS01-R1 | MS01-R1 | IFC | 2021-07-23 | Connor | Y - MP |  |  |  | Y |  |  |  | 2022-03-23 |  |  |  | MS01-R1-IFC |  | Y | FALSE | Collin Ratliff | 2021-12-20
CPK07-R2_AT | CPK07-R2 | 90 | 2022-03-18 | Ernesto |  |  |  |  | Y |  |  |  | 2022-03-18 |  |  |  | CPK07-R2-90 |  | N | FALSE
MS02 | MS02 | IFC | 2021-08-13 | Taylor | Y |  |  |  | Y |  |  |  | 2022-03-23 |  |  |  | MS02-IFC |  | Y | FALSE | Collin Ratliff | 2022-02-04
CPK02_AT | CPK02 | 90 | NA | Ernesto |  |  |  |  | Archived |  |  |  | 2021-10-20 |  |  |  | CPK02-90 |  | N | TRUE | Phil | 2021-12-06
CPK02_AT | CPK02 | 60 | NA | Ernesto |  |  |  |  | Archived |  |  |  | 2021-09-29 |  |  |  | CPK02-60 |  | N | TRUE
CPK02-R1_AT | CPK02-R1 | 90 | NA | Taylor | Y |  |  |  | Archived |  |  |  | 2021-11-18 |  |  |  | CPK02-R1-90 |  | N | TRUE
CPK02-R2_AT | CPK02-R2 | 90 | NA | Ernesto |  |  |  |  | Archived |  |  | Y | 2021-11-21 |  |  |  | CPK02-R2-90 |  | N | TRUE
CPK02-R2_AT | CPK02-R2 | 60 | NA | Ernesto |  |  |  |  | Archived |  |  | Y | 2021-11-18 |  |  |  | CPK02-R2-60 |  | N | TRUE
CPK02-R2_AT | CPK02-R2 | 30 | NA | Ernesto |  |  |  |  | Archived |  |  |  | 2021-10-27 |  |  |  | CPK02-R2-30 |  | N | TRUE
CPK02-R2_AT_Add01 | CPK02-R2-ADD01 | 30 | NA | Ernesto |  |  |  |  | Archived |  |  |  | 2021-12-06 |  |  |  | CPK02-R2-ADD01-30 |  | N | TRUE
CPK02-R2_AT_Add01 | CPK02-R2-ADD01 | 60 | NA | Ernesto |  |  |  |  | Archived |  |  |  | 2021-12-06 |  |  |  | CPK02-R2-ADD01-60 |  | N | TRUE
CPK02-R2_AT_Add02 | CPK02-R2-ADD02 | 60 | NA | Ernesto |  |  |  |  | Archived |  |  |  | 2021-12-06 |  |  |  | CPK02-R2-ADD02-60 |  | N | TRUE
CPK02-R2_CPK03-R2_KICKOFF | CPK02-R2-CPK03-R2 | NA | NA | Ernesto |  |  |  |  | Archived |  |  |  | 2021-12-06 | Presentation |  |  | CPK02-R2-CPK03-R2-NA |  | N | FALSE
CPK02-R3_AT | CPK02-R3 | 90 | NA | Taylor | Y |  |  |  | N |  |  |  | 2021-12-06 |  |  |  | CPK02-R3-90 |  | N | TRUE
CPK02-R4_AT | CPK02-R4 | 90 | NA | Ernesto |  |  |  |  | Archived |  |  | Y | 2022-01-11 |  |  |  | CPK02-R4-90 |  | N | TRUE
CPK03_AT | CPK03 | 90 | NA | Max |  |  |  |  | Archived |  |  |  | 2021-10-18 |  |  |  | CPK03-90 |  | N | TRUE | Drew | 2021-12-06
CPK03_AT | CPK03 | 60 | NA | Max |  |  |  |  | Archived |  |  |  | 2021-09-30 |  |  |  | CPK03-60 |  | N | TRUE
CPK03-R1_AT | CPK03-R1 | 90 | NA | Max |  |  |  |  | Archived |  |  |  | 2021-10-20 |  |  |  | CPK03-R1-90 |  | N | TRUE
CPK03-R2_AT | CPK03-R2 | 60 | NA | Max |  |  |  |  | Archived |  |  | Y | 2021-12-06 |  |  |  | CPK03-R2-60 |  | N | TRUE
CPK03-R2_AT | CPK03-R2 | 90 | NA | Max |  |  |  |  | Archived |  |  | Y | 2021-11-15 |  |  |  | CPK03-R2-90 |  | N | TRUE
CPK03-R2_AT | CPK03-R2 | 30 | NA | Max |  |  |  |  | Archived |  |  |  | 2021-10-26 |  |  |  | CPK03-R2-30 |  | N | TRUE
CPK03-R2_AT_Add01 | CPK03-R2-ADD01 | 30 | NA | Max |  |  |  |  | Archived |  |  |  | 2021-12-06 | Specs |  |  | CPK03-R2-ADD01-30 |  | N | TRUE
CPK03-R2_AT_Add01 | CPK03-R2-ADD01 | 90 | NA | Max |  |  |  |  | Archived |  |  |  | 2021-12-06 | Specs |  |  | CPK03-R2-ADD01-90 |  | N | TRUE
CPK03-R3_AT | CPK03-R3 | 90 | NA | Max |  |  |  |  | Archived |  |  |  | 2021-12-06 |  |  |  | CPK03-R3-90 |  | N | TRUE
CPK03-R3_AT | CPK03-R3 | 60 | NA | Max |  |  |  |  | Archived |  |  |  | 2021-11-02 |  |  |  | CPK03-R3-60 |  | N | TRUE
CPK03-R4_AT | CPK03-R4 | 90 | NA | Max |  |  |  |  | Archived |  |  |  | 2021-11-18 |  |  |  | CPK03-R4-90 |  | N | TRUE
CPK03-R5_AT | CPK03-R5 | 90 | NA | Max |  |  |  |  | Archived |  |  |  | 2021-12-06 |  |  |  | CPK03-R5-90 |  | N | TRUE
CPK03-R5_AT | CPK03-R5 | 60 | NA | Max |  |  |  |  | Archived |  |  |  | 2021-11-18 |  |  |  | CPK03-R5-60 |  | N | TRUE
CPK03-R5_AT | CPK03-R5 | 30 | NA | Max |  |  |  |  | Archived |  |  |  | 2021-11-03 |  |  |  | CPK03-R5-30 |  | N | TRUE
CPK03-R6_AT | CPK03-R6 | 90 | NA | Connor |  |  |  |  | Archive |  |  |  | 2021-12-06 |  |  |  | CPK03-R6-90 |  | N | TRUE
CPK03-R7 | CPK03-R7 | 90 | NA | Max |  |  |  |  | Archived |  |  | Y | 2022-01-03 |  |  |  | CPK03-R7-90 |  | N | TRUE
CPK03-R8_AT | CPK03-R8 | 90 | NA | Max |  |  |  |  | Archived |  |  | Y | 2022-01-07 | missing files found, redownloading now. |  |  | CPK03-R8-90 |  | N | TRUE
CPK03-STRUCT_AT | CPK03 | 90 | NA | Max |  |  |  |  | Archived |  |  |  | 2021-12-06 |  |  |  | CPK03-90 |  | N | TRUE
CPK04_AT | CPK04 | 60 | NA | Ernesto |  |  |  |  | Archived |  |  |  | 2021-11-01 |  |  |  | CPK04-60 |  | N | TRUE
CPK04_AT | CPK04 | 90 | NA | Max |  |  |  |  | Archived |  |  |  | 2021-11-24 |  |  |  | CPK04-90 |  | N | TRUE
CPK04_AT | CPK04 | 30 | NA | Max |  |  |  |  | Archived |  |  |  | 2021-10-11 |  |  |  | CPK04-30 |  | N | TRUE
CPK04-Kick-off | CPK04 | NA | NA | Ernesto |  |  |  |  | Archived |  |  |  | 2021-12-06 | Presentation |  |  | CPK04-NA |  | N | TRUE
CPK06_AT | CPK06 | 60 | NA | Connor |  |  |  |  | Archived |  |  |  | 2021-12-06 |  |  |  | CPK06-60 |  | N | TRUE | Jeremy Friedrichs | 2021-12-06
CPK06_AT | CPK06 | 90 | NA | Connor |  |  |  |  | N |  |  |  | 2021-12-30 | only electrical |  |  | CPK06-90 |  | N | TRUE
LLE01_AT | LLE01 | 90 | NA | Max |  |  |  |  | Archived |  |  |  | 2021-12-06 |  |  |  | LLE01-90 |  | N | TRUE | Jeremy Friedrichs | 2021-12-06
LLE01-R1_AT | LLE01-R1 | 90 | NA | Max |  |  |  |  | Archived |  |  |  | 2021-09-27 |  |  |  | LLE01-R1-90 |  | N | TRUE | Jeremy Friedrichs | 2021-12-06
LLP02_AT | LLP02 | 90 | NA | Max |  |  |  |  | Archived |  |  |  | 2021-12-06 |  |  |  | LLP02-90 |  | N | TRUE | Jeremy Friedrichs | 2021-12-06
LLP02-R1_AT | LLP02-R1 | 90 | NA | Max |  |  |  |  | Archived |  |  |  | 2021-12-06 |  |  |  | LLP02-R1-90 |  | N | TRUE | Phil | 2021-12-06
LLP04 | LLP04 | 90 | NA | Taylor | Y |  |  |  | Y |  |  |  | 2021-12-10 |  |  |  | LLP04-90 |  | N | TRUE | Phil
PRD01 | PRD01 | IFD | NA | Ernesto |  |  |  |  | Y |  |  |  | 2021-08-11 |  |  |  | PRD01-IFD |  | N | TRUE
PRD01_AT | PRD01 | 90 | NA | Ernesto |  |  |  |  | Archived |  |  |  | 2021-12-06 |  |  |  | PRD01-90 |  | N | TRUE
PRD01_Midpoint | PRD01 | NA | NA | Ernesto |  |  |  |  | Archived |  |  |  | 2021-12-06 |  |  |  | PRD01-NA |  | N | TRUE
PRD02 | PRD02 | IFD | NA | Taylor | Y |  |  |  | Y |  |  |  | 2021-11-17 |  |  |  | PRD02-IFD |  | N | TRUE
PRD02_AT | PRD02 | 90 | NA | Ernesto |  |  |  |  | Archived |  |  |  | 2021-11-18 |  |  |  | PRD02-90 |  | N | TRUE
Programming_Kick-Off | PRD | NA | NA | Ernesto |  |  |  |  | Archived |  |  |  | 2021-12-06 |  |  |  | PRD-NA |  | N | FALSE

## 2 IFC DRAWING PAGE COMPARE
Drawing Number in Set | PKG-CODE | Date Issued | Instances | Reviewed | Notes
RAC-GN-0001 | CPK03-IFC | 2021-09-24 | 5
RAC-GN-0002 | CPK03-IFC | 2021-09-24 | 5
RAC-GN-0003 | CPK03-IFC | 2021-09-24 | 5
RAC-GN-0004 | CPK03-IFC | 2021-09-24 | 5
RAC-GN-0005 | CPK03-IFC | 2021-09-24 | 5
RAC-GN-0006 | CPK03-IFC | 2021-09-24 | 5
RAC-GN-0007 | CPK03-IFC | 2021-09-24 | 5
RAC-GN-0008 | CPK03-IFC | 2021-09-24 | 5
RAC-GN-0009 | CPK03-IFC | 2021-09-24 | 5
RAC-GN-0010 | CPK03-IFC | 2021-09-24 | 5
MS1-S0-0010 | CPK03-IFC | 2021-09-24 | 8 | Y
MS1-S0-6210 | CPK03-IFC | 2021-09-24 | 6 | Y
MS1-SS-5RF-4000 | CPK03-IFC | 2021-09-24 | 3 | Y
MS1-SS-5RF-C0000 | CPK03-IFC | 2021-09-24 | 5 | Y
RA-SG-1-0001A | CPK03-IFC | 2021-09-24 | 1
RA-SG-1-0001B | CPK03-IFC | 2021-09-24 | 1
RA-SG-1-0010A | CPK03-IFC | 2021-09-24 | 1
RA-SG-1-0010B | CPK03-IFC | 2021-09-24 | 1
RA-SG-1-0030 | CPK03-IFC | 2021-09-24 | 1
RA-SG-1-0040 | CPK03-IFC | 2021-09-24 | 1
RA-SG-1-0050 | CPK03-IFC | 2021-09-24 | 1
RA-SG-1-0100 | CPK03-IFC | 2021-09-24 | 1
RA-SG-1-3001A | CPK03-IFC | 2021-09-24 | 1
RA-SG-1-3001B | CPK03-IFC | 2021-09-24 | 1
RA-SG-1-3005A | CPK03-IFC | 2021-09-24 | 1
RA-SG-1-3005B | CPK03-IFC | 2021-09-24 | 1
RA-SG-1-3060 | CPK03-IFC | 2021-09-24 | 1
RA-SG-1-5001A | CPK03-IFC | 2021-09-24 | 1
RA-SG-1-5001B | CPK03-IFC | 2021-09-24 | 1
RA-SG-1-5001C | CPK03-IFC | 2021-09-24 | 1
RA-SG-1-5001D | CPK03-IFC | 2021-09-24 | 1
RA-SG-1-5030A | CPK03-IFC | 2021-09-24 | 1
RA-SG-1-5030b | CPK03-IFC | 2021-09-24 | 1
RA-SG-1-5040 | CPK03-IFC | 2021-09-24 | 1
RA-SG-1-5501A | CPK03-IFC | 2021-09-24 | 1
RA-SG-1-5501B | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-0001A | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-0001B | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-0001C | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-0210 | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-0212A | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-0212B | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-0212C | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-0212D | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-0212E | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-0214A | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-0214B | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-0214C | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-0216B | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-0300A | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-0300B | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-0300C | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-0300D | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-0300E | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-0600A | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-0600B | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-1100 | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-1200A | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-1310A | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-1310B | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-1310C | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-1340 | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-1350A | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-1350B | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-1360A | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-1360B | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-1360C | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-1360D | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-1360E | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-1500A | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-1500B | CPK03-IFC | 2021-09-24 | 1
RA-SG-2-1700 | CPK03-IFC | 2021-09-24 | 1
RA-SG-3-8010A | CPK03-IFC | 2021-09-24 | 1
RA-SG-3-8010B | CPK03-IFC | 2021-09-24 | 1
RA-SG-3-8015 | CPK03-IFC | 2021-09-24 | 1
MS1-101-MH-A01 | CPK03-IFC | 2021-09-24 | 1
MS1-111-MW-A03 | CPK03-IFC | 2021-09-24 | 2 | Y
MS1-117-MW-A02 | CPK03-IFC | 2021-09-24 | 2 | Y
MS1-ME-5RA-A0D00 | CPK03-IFC | 2021-09-24 | 2
RA-MH-D010 | CPK03-IFC | 2021-09-24 | 3
RA-MH-D011 | CPK03-IFC | 2021-09-24 | 3
RA-MH-D012 | CPK03-IFC | 2021-09-24 | 1
RA-MH-D013 | CPK03-IFC | 2021-09-24 | 3
RA-MH-D015 | CPK03-IFC | 2021-09-24 | 3
RA-MH-D016 | CPK03-IFC | 2021-09-24 | 3
RA-MH-D017 | CPK03-IFC | 2021-09-24 | 3
RA-MH-D018 | CPK03-IFC | 2021-09-24 | 3
RA-MH-D020 | CPK03-IFC | 2021-09-24 | 3
RA-MH-D028 | CPK03-IFC | 2021-09-24 | 3
RA-MH-D035 | CPK03-IFC | 2021-09-24 | 3
RA-MH-D036 | CPK03-IFC | 2021-09-24 | 3
RA-MH-D037 | CPK03-IFC | 2021-09-24 | 3
RA-MH-D038 | CPK03-IFC | 2021-09-24 | 3
RA-MH-D051 | CPK03-IFC | 2021-09-24 | 3
RA-MH-D052 | CPK03-IFC | 2021-09-24 | 3
RA-MH-D053 | CPK03-IFC | 2021-09-24 | 3
RA-MH-D054 | CPK03-IFC | 2021-09-24 | 3
RA-MH-D057 | CPK03-IFC | 2021-09-24 | 3
RA-MH-D062 | CPK03-IFC | 2021-09-24 | 3
RA-MH-D086 | CPK03-IFC | 2021-09-24 | 3
RA-MH-D097 | CPK03-IFC | 2021-09-24 | 3
RA-MP-D001 | CPK03-IFC | 2021-09-24 | 3
RA-MP-D002 | CPK03-IFC | 2021-09-24 | 3
RA-MP-D003 | CPK03-IFC | 2021-09-24 | 3
RA-MP-D004 | CPK03-IFC | 2021-09-24 | 3
RA-MP-D005 | CPK03-IFC | 2021-09-24 | 3
RA-MP-D006 | CPK03-IFC | 2021-09-24 | 1
RA-MP-D007 | CPK03-IFC | 2021-09-24 | 1
RA-MP-D008 | CPK03-IFC | 2021-09-24 | 1
RA-MP-D009 | CPK03-IFC | 2021-09-24 | 1
RA-MP-D010 | CPK03-IFC | 2021-09-24 | 3
RA-MP-D011 | CPK03-IFC | 2021-09-24 | 3
RA-MP-D012 | CPK03-IFC | 2021-09-24 | 1
RA-MP-D013 | CPK03-IFC | 2021-09-24 | 3
RA-MP-D014 | CPK03-IFC | 2021-09-24 | 1
RA-MP-D015 | CPK03-IFC | 2021-09-24 | 1
RA-MP-D040 | CPK03-IFC | 2021-09-24 | 1
RA-MP-D041 | CPK03-IFC | 2021-09-24 | 1
RA-MP-D042 | CPK03-IFC | 2021-09-24 | 1
RA-MP-D043 | CPK03-IFC | 2021-09-24 | 1
RA-MP-D044 | CPK03-IFC | 2021-09-24 | 1
RA-MP-D045 | CPK03-IFC | 2021-09-24 | 1
RA-MP-D046 | CPK03-IFC | 2021-09-24 | 3
RA-MP-D047 | CPK03-IFC | 2021-09-24 | 1
RA-MP-D055 | CPK03-IFC | 2021-09-24 | 1
RA-MP-D056 | CPK03-IFC | 2021-09-24 | 1
RA-MP-D062 | CPK03-IFC | 2021-09-24 | 1
RA-MP-D063 | CPK03-IFC | 2021-09-24 | 1
RA-PL-D001 | CPK03-IFC | 2021-09-24 | 3
RA-PL-D002 | CPK03-IFC | 2021-09-24 | 3
RA-PL-D003 | CPK03-IFC | 2021-09-24 | 3
RA-PL-D004 | CPK03-IFC | 2021-09-24 | 3
RA-PL-D005 | CPK03-IFC | 2021-09-24 | 3
RA-PL-D006 | CPK03-IFC | 2021-09-24 | 3
RA-PL-D007 | CPK03-IFC | 2021-09-24 | 3
RA-PL-D116 | CPK03-IFC | 2021-09-24 | 3
RA-PL-D117 | CPK03-IFC | 2021-09-24 | 3
RA-PL-D118 | CPK03-IFC | 2021-09-24 | 3
RA-PL-D119 | CPK03-IFC | 2021-09-24 | 3
RA-PL-D120 | CPK03-IFC | 2021-09-24 | 3
RA-PL-D121 | CPK03-IFC | 2021-09-24 | 3
RA-PL-D122 | CPK03-IFC | 2021-09-24 | 3
RA-PL-D123 | CPK03-IFC | 2021-09-24 | 3
RA-PL-D127 | CPK03-IFC | 2021-09-24 | 3
RA-PL-D128 | CPK03-IFC | 2021-09-24 | 3
RA-PL-D132 | CPK03-IFC | 2021-09-24 | 3
RA-PL-D136 | CPK03-IFC | 2021-09-24 | 3
RA-PL-D137 | CPK03-IFC | 2021-09-24 | 3
RA-PL-D138 | CPK03-IFC | 2021-09-24 | 3
RA-PL-D139 | CPK03-IFC | 2021-09-24 | 3
MS1-ES-1250A | CPK03-IFC | 2021-09-24 | 3
MS1-ES-1251C | CPK03-IFC | 2021-09-24 | 3
RAC-EN-0000 | CPK03-IFC | 2021-09-24 | 1
RAC-EN-0001 | CPK03-IFC | 2021-09-24 | 1
MS1-HF-5RA-C0000 | CPK03-IFC | 2021-09-24 | 2
MS1-HF-0100 | CPK03-IFC | 2021-09-24 | 3
MS1-HF-0102 | CPK03-IFC | 2021-09-24 | 3
MS1-HF-3000C | CPK03-IFC | 2021-09-24 | 2
MS1-HF-3000D | CPK03-IFC | 2021-09-24 | 2
RA3-HF-3000C | CPK03-IFC | 2021-09-24 | 3
RAC-HF-0001 | CPK03-IFC | 2021-09-24 | 3
MS1-I0-4DA-C0000 | CPK03-IFC | 2021-09-24 | 1
MS1-I0-4DA-D0000 | CPK03-IFC | 2021-09-24 | 2
MS1-IE-1SA-D0000 | CPK03-IFC | 2021-09-24 | 5
MS1-IE-2FA-B0000 | CPK03-IFC | 2021-09-24 | 3
MS1-IE-2FA-B0000-D | CPK03-IFC | 2021-09-24 | 1
MS1-IE-2FA-C0000 | CPK03-IFC | 2021-09-24 | 4
MS1-IE-2FA-C0000-D | CPK03-IFC | 2021-09-24 | 1
MS1-IE-2FA-D0000 | CPK03-IFC | 2021-09-24 | 3
MS1-IE-2FA-D0000-D | CPK03-IFC | 2021-09-24 | 1
MS1-IE-5RA-C0000 | CPK03-IFC | 2021-09-24 | 2
MS1-IE-1001 | CPK03-IFC | 2021-09-24 | 3
MS1-IE-1023 | CPK03-IFC | 2021-09-24 | 1
MS1-T0-4DA-C0000 | CPK03-IFC | 2021-09-24 | 1
MS1-T0-5RA-C0000 | CPK03-IFC | 2021-09-24 | 1
RAC-T0-0001 | CPK03-IFC | 2021-09-24 | 4
RAC-T0-9001 | CPK03-IFC | 2021-09-24 | 4
D1X-117-D0-Z03 | CPK03-IFC | 2021-09-24 | 1
MS1-101-D0-A01 | CPK03-IFC | 2021-09-24 | 2
MS1-101-D0-A02 | CPK03-IFC | 2021-09-24 | 3
MS1-101-D0-A05 | CPK03-IFC | 2021-09-24 | 2
MS1-101-D0-A06 | CPK03-IFC | 2021-09-24 | 3
MS1-101-D0-A07 | CPK03-IFC | 2021-09-24 | 2
MS1-101-D0-A09 | CPK03-IFC | 2021-09-24 | 2
MS1-213-D0-Z03 | CPK03-IFC | 2021-09-24 | 1
MS1-234-D0-A01 | CPK03-IFC | 2021-09-24 | 1
1810_VFD_08 | CPK03-IFC | 2021-09-24 | 4
D-I-1910_01 | CPK03-IFC | 2021-09-24 | 2
D-I-1910_02 | CPK03-IFC | 2021-09-24 | 2
D-I-1910_03 | CPK03-IFC | 2021-09-24 | 2
D-I-1910_04 | CPK03-IFC | 2021-09-24 | 2
D-I-1910_05 | CPK03-IFC | 2021-09-24 | 2
D-I-1910_06 | CPK03-IFC | 2021-09-24 | 2
D-I-1910_07 | CPK03-IFC | 2021-09-24 | 2
D-I-1910_08 | CPK03-IFC | 2021-09-24 | 3
D-I-1910_09 | CPK03-IFC | 2021-09-24 | 2
D-I-1910_10 | CPK03-IFC | 2021-09-24 | 2
D-I-1910_11 | CPK03-IFC | 2021-09-24 | 2
D-I-1910_12 | CPK03-IFC | 2021-09-24 | 2
D-I-1910_13 | CPK03-IFC | 2021-09-24 | 2
D-I-1910_14 | CPK03-IFC | 2021-09-24 | 2
D-I-1910_15 | CPK03-IFC | 2021-09-24 | 2
D-I-1910_16 | CPK03-IFC | 2021-09-24 | 2
D-I-1910_17 | CPK03-IFC | 2021-09-24 | 2
D-I-1910_18 | CPK03-IFC | 2021-09-24 | 2
D-I-1910_19 | CPK03-IFC | 2021-09-24 | 2
D-I-1910_20 | CPK03-IFC | 2021-09-24 | 2
D-I-1910_23 | CPK03-IFC | 2021-09-24 | 4
MSB1_RIO650_2A_03 | CPK03-IFC | 2021-09-24 | 1
MSB1_RIO650_2B_03 | CPK03-IFC | 2021-09-24 | 1
RAC-E0-D001 | CPK03-IFC | 2021-09-24 | 2
RAC-E0-D002 | CPK03-IFC | 2021-09-24 | 2
RAC-E0-D003 | CPK03-IFC | 2021-09-24 | 2
RAC-E0-D004 | CPK03-IFC | 2021-09-24 | 2
RAC-E0-D005 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D001 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D002 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D003 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D004 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D005 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D006 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D007 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D008 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D009 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D010 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D011 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D012 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D013 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D014 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D015 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D016 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D017 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D018 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D019 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D020 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D021 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D022 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D023 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D024 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D025 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D026 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D027 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D028 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D029 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D030 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D031 | CPK03-IFC | 2021-09-24 | 2
RAC-EG-D032 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D001 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D002 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D003 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D004 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D005 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D006 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D007 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D008 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D009 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D010 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D011 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D012 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D013 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D014 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D015 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D016 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D017 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D018 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D019 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D020 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D021 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D022 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D023 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D024 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D025 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D026 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D027 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D028 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D029 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D030 | CPK03-IFC | 2021-09-24 | 2
RAC-EH-D031 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D001 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D002 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D003 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D004 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D005 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D006 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D007 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D008 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D009 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D010 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D011 | CPK03-IFC | 2021-09-24 | 1
RAC-EL-D012 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D013 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D014 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D015 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D016 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D017 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D018 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D019 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D020 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D021 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D022 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D023 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D024 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D025 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D026 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D027 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D028 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D029 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D030 | CPK03-IFC | 2021-09-24 | 2
RAC-EL-D031 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D001 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D002 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D003 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D004 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D005 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D006 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D007 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D008 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D009 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D010 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D011 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D012 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D013 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D014 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D015 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D016 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D017 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D018 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D019 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D020 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D021 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D022 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D023 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D024 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D025 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D026 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D027 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D028 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D029 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D030 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D031 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D032 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D033 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D034 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D035 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D036 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D037 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D038 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D039 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D040 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D041 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D042 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D043 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D044 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D045 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D046 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D047 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D048 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D049 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D050 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D051 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D052 | CPK03-IFC | 2021-09-24 | 2
RAC-EP-D053 | CPK03-IFC | 2021-09-24 | 2
RAC-ET-D001 | CPK03-IFC | 2021-09-24 | 2
RAC-ET-D002 | CPK03-IFC | 2021-09-24 | 2
RAC-ET-D003 | CPK03-IFC | 2021-09-24 | 2
RAC-ET-D004 | CPK03-IFC | 2021-09-24 | 2
RAC-ET-D005 | CPK03-IFC | 2021-09-24 | 2
RAC-ET-D006 | CPK03-IFC | 2021-09-24 | 2
RAC-ET-D007 | CPK03-IFC | 2021-09-24 | 2
RAC-ET-D008 | CPK03-IFC | 2021-09-24 | 2
RAC-ET-D009 | CPK03-IFC | 2021-09-24 | 2
RAC-ET-D010 | CPK03-IFC | 2021-09-24 | 2
RAC-ET-D011 | CPK03-IFC | 2021-09-24 | 2
RAC-ET-D012 | CPK03-IFC | 2021-09-24 | 2
RAC-ET-D013 | CPK03-IFC | 2021-09-24 | 2
RAC-ET-D014 | CPK03-IFC | 2021-09-24 | 2
RAC-ET-D015 | CPK03-IFC | 2021-09-24 | 2
RAC-ET-D016 | CPK03-IFC | 2021-09-24 | 2
RAC-ET-D017 | CPK03-IFC | 2021-09-24 | 2
RAC-ET-D018 | CPK03-IFC | 2021-09-24 | 2
RAC-ET-D019 | CPK03-IFC | 2021-09-24 | 2
RAC-ET-D020 | CPK03-IFC | 2021-09-24 | 2
RAC-ET-D021 | CPK03-IFC | 2021-09-24 | 2
RAC-ET-D022 | CPK03-IFC | 2021-09-24 | 2
RAC-ET-D023 | CPK03-IFC | 2021-09-24 | 2
RAC-ET-D024 | CPK03-IFC | 2021-09-24 | 2
RAC-ET-D025 | CPK03-IFC | 2021-09-24 | 2
RAC-ET-D026 | CPK03-IFC | 2021-09-24 | 2
D-H-1840-LSS-MDP-H33 | CPK03-IFC | 2021-09-24 | 3
D-H-1840-LSS-MDP-H34 | CPK03-IFC | 2021-09-24 | 3
D-H-1840-LSS-MDP-H35 | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-001-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-100-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-101-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-105-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-110-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-115-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-200-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-201-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-202-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-204-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-206-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-207-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-210-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-211-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-215-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-250-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-255-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-256-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-260-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-261-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-270-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-271-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-275-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-276-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-300-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-301-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-302-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-303-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-304-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-305-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-306-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-310-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-311-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-312-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-350-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-360-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-365-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-366-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-FIRE-375-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1841-LSS-MDP-F01 | CPK03-IFC | 2021-09-24 | 3
D-H-1841-LSS-MDP-F02 | CPK03-IFC | 2021-09-24 | 3
D-H-1841-LSS-MDP-F03 | CPK03-IFC | 2021-09-24 | 3
D-H-1841-LSS-MDP-F04 | CPK03-IFC | 2021-09-24 | 3
D-H-1841-LSS-MDP-F05 | CPK03-IFC | 2021-09-24 | 3
D-H-1841-LSS-MDP-F06 | CPK03-IFC | 2021-09-24 | 3
D-H-1842-TAS-203-MDP | CPK03-IFC | 2021-09-24 | 2
D-H-1842-LSS-MDP-H09 | CPK03-IFC | 2021-09-24 | 2
D-H-1842-LSS-MDP-H52 | CPK03-IFC | 2021-09-24 | 2
D-H-1842-LSS-MDP-H52A | CPK03-IFC | 2021-09-24 | 2
D-H-1842-LSS-MDP-H70 | CPK03-IFC | 2021-09-24 | 2
D-H-1842-LSS-MDP-H70A | CPK03-IFC | 2021-09-24 | 2
D-H-1842-LSS-MDP-H71 | CPK03-IFC | 2021-09-24 | 2
D-H-1842-LSS-MDP-H72 | CPK03-IFC | 2021-09-24 | 2
D-H-1842-LSS-MDP-H72A | CPK03-IFC | 2021-09-24 | 2
D-H-1842-TAS-100-MDP | CPK03-IFC | 2021-09-24 | 2
D-H-1842-TAS-200-MDP | CPK03-IFC | 2021-09-24 | 2
D-H-1842-TAS-201-MDP | CPK03-IFC | 2021-09-24 | 2
D-H-1842-TAS-202-MDP | CPK03-IFC | 2021-09-24 | 2
D-H-1844-HPM-001-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-HPM-320-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-HPM-322-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-HPM-323-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-HPM-325-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-HPM-326-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-HPM-327-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-HPM-328-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-HPM-329-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-HPM-330-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-HPM-538-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-HPM-539-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-HPM-540-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-HPM-585-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-HPM-703-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-HPM-704-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-HPM-705-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-HPM-707-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-HPM-708-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-HPM-711-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-HPM-713-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-HPM-714-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-HPM-715-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-HPM-716-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-HPM-717-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-HPM-718-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-HPM-719-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H01 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H02 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H03 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H05 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H06 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H07 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H08 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H15 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H16 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H20 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H21 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H22 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H23 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H24 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H25 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H26 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H27 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H30 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H31 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H32 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H33 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H34 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H35 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H50 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H50A | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H55 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H55A | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H55B | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H56 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H56A | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H56B | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H57 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H58 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H58A | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H58B | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H59 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H59A | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H60 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H60A | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H61 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H61A | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H61B | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H61C | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H62 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H62A | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H62B | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H63 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H63A | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H63B | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H64 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H64A | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H64B | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H80 | CPK03-IFC | 2021-09-24 | 3
D-H-1844-LSS-MDP-H80A | CPK03-IFC | 2021-09-24 | 3
D-H-1845-HPM-402-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1845-HPM-403-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1845-HPM-404-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1845-HPM-405-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1845-HPM-406-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1845-HPM-410-MDP | CPK03-IFC | 2021-09-24 | 4
D-H-1845-HPM-411-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1846-EWS-100-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1846-EWS-201-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1846-EWS-202-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1846-EWS-204-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1846-EWS-205-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1846-EWS-301-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1846-FIRE-150-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1846-FIRE-151-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1846-FIRE-152-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1846-FIRE-155-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1846-FIRE-156-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1846-FIRE-157-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1846-FIRE-158-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1846-FIRE-160-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1846-FIRE-161-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1846-FIRE-162-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1846-FIRE-163-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1846-FIRE-164-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1846-FIRE-165-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1846-FIRE-166-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1846-FIRE-167-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1846-FIRE-168-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1846-FIRE-170-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1846-FIRE-171-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1846-FIRE-172-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1846-FIRE-173-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1846-FIRE-174-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-HPM-725-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1844-HPM-726-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-126-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-128-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-130-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-146-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-160-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-161-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-162-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-163-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-164E-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-164-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-164M-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-165E-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-165-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-165M-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-166-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-167-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-168-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-169-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-170-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-171-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-172-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-173-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-174-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-203-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-252E-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-252-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-252M-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-253-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-254-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-255-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-261-MDP | CPK03-IFC | 2021-09-24 | 3
D-H-1848-HPM-270-MDP | CPK03-IFC | 2021-09-24 | 3
MSB1-PZ101-7-00C | CPK03-IFC | 2021-09-24 | 1
MSB1-PZ101-7-00D | CPK03-IFC | 2021-09-24 | 1
MSB1-NET101-0-15L | CPK03-IFC | 2021-09-24 | 1
MSB1-NET101-0-15M | CPK03-IFC | 2021-09-24 | 1
MSB1-NET101-0-15N | CPK03-IFC | 2021-09-24 | 1
MSB1-NET101-0-15P | CPK03-IFC | 2021-09-24 | 1
MSB1-NET101-0-15Q | CPK03-IFC | 2021-09-24 | 1
MSB1-NET101-7-11A | CPK03-IFC | 2021-09-24 | 1
MSB1-NET101-8-11A | CPK03-IFC | 2021-09-24 | 1
MSB1-PDIT101-0-04G | CPK03-IFC | 2021-09-24 | 1
MSB1-PDIT101-0-04H | CPK03-IFC | 2021-09-24 | 1
MSB1-PDIT101-0-04J | CPK03-IFC | 2021-09-24 | 1
MSB1-PSH101-7-00A | CPK03-IFC | 2021-09-24 | 1
MSB1-PSH101-8-00A | CPK03-IFC | 2021-09-24 | 1
MSB1-TET101-7-06A | CPK03-IFC | 2021-09-24 | 1
MSB1-TET101-7-08A | CPK03-IFC | 2021-09-24 | 1
MSB1-TET101-7-09A | CPK03-IFC | 2021-09-24 | 1
MSB1-TET101-7-10A | CPK03-IFC | 2021-09-24 | 1
MSB1-TET101-7-13A | CPK03-IFC | 2021-09-24 | 1
MSB1-TET101-8-06A | CPK03-IFC | 2021-09-24 | 1
MSB1-TET101-8-08A | CPK03-IFC | 2021-09-24 | 1
MSB1-TET101-8-09A | CPK03-IFC | 2021-09-24 | 1
MSB1-TET101-8-10A | CPK03-IFC | 2021-09-24 | 1
MSB1-TET101-8-13A | CPK03-IFC | 2021-09-24 | 1
MSB1-TSL101-7-00A | CPK03-IFC | 2021-09-24 | 1
MSB1-TSL101-8-00A | CPK03-IFC | 2021-09-24 | 1
RA-ST-0001 | CPK03-IFC | 2021-09-24 | 9
RA-ST-0002 | CPK03-IFC | 2021-09-24 | 9
RA-ST-0003 | CPK03-IFC | 2021-09-24 | 9
RA-ST-0004 | CPK03-IFC | 2021-09-24 | 9
RA-ST-0005 | CPK03-IFC | 2021-09-24 | 9
RA-ST-0006 | CPK03-IFC | 2021-09-24 | 9
RA-ST-0007 | CPK03-IFC | 2021-09-24 | 9
RA-ST-0009 | CPK03-IFC | 2021-09-24 | 9
RA-ST-0010 | CPK03-IFC | 2021-09-24 | 9
RA-ST-0011 | CPK03-IFC | 2021-09-24 | 9
RA-ST-0012 | CPK03-IFC | 2021-09-24 | 9
RA-ST-0013 | CPK03-IFC | 2021-09-24 | 9
RA-ST-0014 | CPK03-IFC | 2021-09-24 | 9
RA-ST-0015 | CPK03-IFC | 2021-09-24 | 9
RA-ST-0016 | CPK03-IFC | 2021-09-24 | 9
RA-ST-0018 | CPK03-IFC | 2021-09-24 | 9
RA-ST-0500 | CPK03-IFC | 2021-09-24 | 9
RA-ST-0501 | CPK03-IFC | 2021-09-24 | 9
RA-ST-0502 | CPK03-IFC | 2021-09-24 | 9
RA-ST-0503 | CPK03-IFC | 2021-09-24 | 9
RA-ST-0504 | CPK03-IFC | 2021-09-24 | 9
RA-ST-0505 | CPK03-IFC | 2021-09-24 | 9
RA-ST-0506 | CPK03-IFC | 2021-09-24 | 9
RA-ST-2000 | CPK03-IFC | 2021-09-24 | 9
RA-ST-2006 | CPK03-IFC | 2021-09-24 | 9
RA-ST-2007 | CPK03-IFC | 2021-09-24 | 9
RA-ST-2008 | CPK03-IFC | 2021-09-24 | 9
RA-ST-2012 | CPK03-IFC | 2021-09-24 | 9
RA-ST-2013 | CPK03-IFC | 2021-09-24 | 9
RA-ST-2014 | CPK03-IFC | 2021-09-24 | 9
RA-ST-2015 | CPK03-IFC | 2021-09-24 | 9
RA-ST-2016 | CPK03-IFC | 2021-09-24 | 9
RA-ST-2024 | CPK03-IFC | 2021-09-24 | 9
RA-ST-2028 | CPK03-IFC | 2021-09-24 | 9
RA-ST-2032 | CPK03-IFC | 2021-09-24 | 9
RA-ST-2042 | CPK03-IFC | 2021-09-24 | 9
RA-ST-2044 | CPK03-IFC | 2021-09-24 | 9
RA-ST-3000 | CPK03-IFC | 2021-09-24 | 9
RA-ST-3001 | CPK03-IFC | 2021-09-24 | 9
RA-ST-3002 | CPK03-IFC | 2021-09-24 | 9
RA-ST-4000 | CPK03-IFC | 2021-09-24 | 9
RA-ST-4001 | CPK03-IFC | 2021-09-24 | 9
RA-ST-4002 | CPK03-IFC | 2021-09-24 | 9
RA-ST-4003 | CPK03-IFC | 2021-09-24 | 9
D1X-S0-6211 | CPK03-R10-IFC | 2022-02-23 | 1
D1X-SS-5RA-C0300 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-S0-6259 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-S0-6261 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-S0-6262 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-S0-6263 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-S0-6264 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-S0-6265 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-S0-6266 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-S0-6267 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-S0-6268 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-SS-1SA-4006 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-SS-1SA-4007 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-SS-1SA-4008 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-SS-1SA-4009 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-SS-1SA-4010 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-SS-1SA-C0300 | CPK03-R10-IFC | 2022-02-23 | 2
MS1-SS-2FA-4002 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-SS-2FA-4003 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-SS-2FA-4004 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-SS-2FA-4005 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-SS-2FA-4009 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-SS-2FA-4010 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-SS-2FA-4011 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-SS-3FA-4000 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-SS-3FA-4001 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-SS-3FA-4002 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-SS-4DA-4001 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-SS-4DA-4002 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-SS-4DA-4003 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-SS-5RA-4001 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-SS-5RA-4002 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-SS-5RA-4003 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-SS-5RA-4004 | CPK03-R10-IFC | 2022-02-23 | 1
MS1-AC-2FH-4001 | CPK03-R10-IFC | 2022-02-23 | 4
MS1-AC-2FH-B0000 | CPK03-R10-IFC | 2022-02-23 | 5
MS1-AC-2FH-C0000 | CPK03-R10-IFC | 2022-02-23 | 4
MS1-AC-2FH-D0000 | CPK03-R10-IFC | 2022-02-23 | 4
MS1-AC-2FI-4002 | CPK03-R10-IFC | 2022-02-23 | 3
RA-ST-2500 | CPK03-R10-IFC | 2022-02-23 | 4
RA-ST-2501 | CPK03-R10-IFC | 2022-02-23 | 5
RA-ST-2502 | CPK03-R10-IFC | 2022-02-23 | 5
RA-ST-2503 | CPK03-R10-IFC | 2022-02-23 | 5
RA-ST-2504 | CPK03-R10-IFC | 2022-02-23 | 5
RA-ST-2505 | CPK03-R10-IFC | 2022-02-23 | 5
RA-ST-2506 | CPK03-R10-IFC | 2022-02-23 | 5
RA-ST-2507 | CPK03-R10-IFC | 2022-02-23 | 5
RA-ST-2508 | CPK03-R10-IFC | 2022-02-23 | 5
RA-ST-2509 | CPK03-R10-IFC | 2022-02-23 | 5
RA-ST-2510 | CPK03-R10-IFC | 2022-02-23 | 5
RA-ST-2511 | CPK03-R10-IFC | 2022-02-23 | 5
RA-ST-2512 | CPK03-R10-IFC | 2022-02-23 | 5
RA-ST-2513 | CPK03-R10-IFC | 2022-02-23 | 5
RA-ST-2514 | CPK03-R10-IFC | 2022-02-23 | 5
RA-ST-2515 | CPK03-R10-IFC | 2022-02-23 | 5
RA-ST-2516 | CPK03-R10-IFC | 2022-02-23 | 5
RA-ST-2517 | CPK03-R10-IFC | 2022-02-23 | 5
RA-ST-2518 | CPK03-R10-IFC | 2022-02-23 | 5
RA-ST-2519 | CPK03-R10-IFC | 2022-02-23 | 5
RA-ST-2520 | CPK03-R10-IFC | 2022-02-23 | 5
RA-ST-2521 | CPK03-R10-IFC | 2022-02-23 | 4
RA-ST-2522 | CPK03-R10-IFC | 2022-02-23 | 4
RA-ST-2523 | CPK03-R10-IFC | 2022-02-23 | 4
RA-ST-2524 | CPK03-R10-IFC | 2022-02-23 | 4
RA-ST-2525 | CPK03-R10-IFC | 2022-02-23 | 4
RA-ST-2526 | CPK03-R10-IFC | 2022-02-23 | 4
RA-ST-2527 | CPK03-R10-IFC | 2022-02-23 | 4
RA-ST-2528 | CPK03-R10-IFC | 2022-02-23 | 4
RA-ST-2529 | CPK03-R10-IFC | 2022-02-23 | 4
RA-ST-2530 | CPK03-R10-IFC | 2022-02-23 | 4
RA-ST-2531 | CPK03-R10-IFC | 2022-02-23 | 4
RA-ST-2532 | CPK03-R10-IFC | 2022-02-23 | 4
RA-ST-2533 | CPK03-R10-IFC | 2022-02-23 | 4
RA-ST-2534 | CPK03-R10-IFC | 2022-02-23 | 4
RA-ST-2535 | CPK03-R10-IFC | 2022-02-23 | 4
RA-ST-2536 | CPK03-R10-IFC | 2022-02-23 | 4
RA-ST-2537 | CPK03-R10-IFC | 2022-02-23 | 4
RA-ST-2538 | CPK03-R10-IFC | 2022-02-23 | 4
RA-ST-2539 | CPK03-R10-IFC | 2022-02-23 | 4
RA-ST-2540 | CPK03-R10-IFC | 2022-02-23 | 4
RA-ST-2541 | CPK03-R10-IFC | 2022-02-23 | 4
RA-ST-2542 | CPK03-R10-IFC | 2022-02-23 | 4
RA-ST-2543 | CPK03-R10-IFC | 2022-02-23 | 4
RA-ST-2544 | CPK03-R10-IFC | 2022-02-23 | 4
RA-ST-2545 | CPK03-R10-IFC | 2022-02-23 | 4
RA-ST-2546 | CPK03-R10-IFC | 2022-02-23 | 4
RA-ST-2547 | CPK03-R10-IFC | 2022-02-23 | 4
RA-ST-2548 | CPK03-R10-IFC | 2022-02-23 | 3
RA-ST-2549 | CPK03-R10-IFC | 2022-02-23 | 3
RA-ST-2550 | CPK03-R10-IFC | 2022-02-23 | 3
RA-ST-2551 | CPK03-R10-IFC | 2022-02-23 | 3
RA-ST-2552 | CPK03-R10-IFC | 2022-02-23 | 3
RA-ST-2553 | CPK03-R10-IFC | 2022-02-23 | 3
RA-ST-2554 | CPK03-R10-IFC | 2022-02-23 | 3
RA-ST-2555 | CPK03-R10-IFC | 2022-02-23 | 3
RA-ST-2556 | CPK03-R10-IFC | 2022-02-23 | 3
RA-ST-2557 | CPK03-R10-IFC | 2022-02-23 | 3
RA-ST-2558 | CPK03-R10-IFC | 2022-02-23 | 3
RA-ST-2559 | CPK03-R10-IFC | 2022-02-23 | 3
RA-ST-2560 | CPK03-R10-IFC | 2022-02-23 | 3
RA-ST-2561 | CPK03-R10-IFC | 2022-02-23 | 3
RA-ST-2562 | CPK03-R10-IFC | 2022-02-23 | 3
RA-ST-2563 | CPK03-R10-IFC | 2022-02-23 | 3
RA-ST-2564 | CPK03-R10-IFC | 2022-02-23 | 3
RA-ST-2565 | CPK03-R10-IFC | 2022-02-23 | 3
RA-ST-2566 | CPK03-R10-IFC | 2022-02-23 | 3
RA-ST-2567 | CPK03-R10-IFC | 2022-02-23 | 3
RA-ST-2568 | CPK03-R10-IFC | 2022-02-23 | 3
RA-ST-2569 | CPK03-R10-IFC | 2022-02-23 | 3
RA-ST-2570 | CPK03-R10-IFC | 2022-02-23 | 3
RA-ST-2571 | CPK03-R10-IFC | 2022-02-23 | 3
RA-ST-2572 | CPK03-R10-IFC | 2022-02-23 | 2
RA-ST-2573 | CPK03-R10-IFC | 2022-02-23 | 2
RA-ST-2574 | CPK03-R10-IFC | 2022-02-23 | 2
RA-ST-2575 | CPK03-R10-IFC | 2022-02-23 | 2
RA-ST-2576 | CPK03-R10-IFC | 2022-02-23 | 2
RA-ST-2577 | CPK03-R10-IFC | 2022-02-23 | 2
RA-ST-2578 | CPK03-R10-IFC | 2022-02-23 | 2
RA-ST-2579 | CPK03-R10-IFC | 2022-02-23 | 2
RA-ST-2580 | CPK03-R10-IFC | 2022-02-23 | 2
RA-ST-2581 | CPK03-R10-IFC | 2022-02-23 | 2
RA-ST-2582 | CPK03-R10-IFC | 2022-02-23 | 2
RA-ST-2583 | CPK03-R10-IFC | 2022-02-23 | 2
RA-ST-2584 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2585 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2586 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2587 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2588 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2589 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2590 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2591 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2592 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2593 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2594 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2595 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2596 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2597 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2598 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2599 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2600 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2601 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2602 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2603 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2604 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2605 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2606 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2607 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2608 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2609 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2610 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2611 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2612 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2613 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2614 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2615 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2616 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2617 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2618 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2619 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2620 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2621 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2622 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2623 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2624 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2625 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2626 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2627 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2628 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2629 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2630 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2631 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2632 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2633 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2634 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2635 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2636 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2637 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2638 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2639 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2640 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2641 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2642 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2643 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2644 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2645 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2646 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2647 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2648 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2649 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2650 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2651 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2652 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2653 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2654 | CPK03-R10-IFC | 2022-02-23 | 1
RA-ST-2655 | CPK03-R10-IFC | 2022-02-23 | 1
ISAT-MP-AT-NA-L1-B-VB | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-AT-NA-L3-B-VB | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-AT-CS-G1-B | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-AT-CS-G2-B | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-AT-CS-G3-B | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-AT-CS-G4-B | CPK03-R10-IFC | 2022-02-23 | 3
ISAT-MP-AT-CS-A1-B | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-AT-NA-A1-B | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-AT-PS-A1-U | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-AT-CS-A2-B | CPK03-R10-IFC | 2022-02-23 | 1
ISAT-MP-AT-NA-A2-B | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-AT-CS-A3-B | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-AT-NA-A3-B | CPK03-R10-IFC | 2022-02-23 | 1
ISAT-MP-AT-CS-A4-B | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-AT-NA-L1-B | CPK03-R10-IFC | 2022-02-23 | 2
ISAT-MP-AT-NA-L2-B | CPK03-R10-IFC | 2022-02-23 | 1
ISAT-MP-AT-NA-L3-B | CPK03-R10-IFC | 2022-02-23 | 1
ISAT-MP-AT-NA-L4-B | CPK03-R10-IFC | 2022-02-23 | 1
ISAT-MP-AT-NA-L5-B | CPK03-R10-IFC | 2022-02-23 | 1
ISAT-MP-AT-NA-L6-B | CPK03-R10-IFC | 2022-02-23 | 1
ISAT-MP-AT-NA-L7-B | CPK03-R10-IFC | 2022-02-23 | 1
ISAT-MP-AT-CS-U1-B | CPK03-R10-IFC | 2022-02-23 | 6
ISAT-MP-AT-NA-U1-B | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-AT-CS-U2-B | CPK03-R10-IFC | 2022-02-23 | 6
ISAT-MP-AT-NA-U2-B | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-AT-NA-U3-B | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-AT-NA-U4-B | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-AT-NA-U5-B | CPK03-R10-IFC | 2022-02-23 | 3
ISAT-MP-AT-NA-U6-B | CPK03-R10-IFC | 2022-02-23 | 2
ISAT-MP-AT-NA-U7-B | CPK03-R10-IFC | 2022-02-23 | 1
ISAT-MP-AT-NA-U8-B | CPK03-R10-IFC | 2022-02-23 | 1
ISAT-MP-AT-NA-U9-B | CPK03-R10-IFC | 2022-02-23 | 1
ISAT-MP-AT-NA-U10-B | CPK03-R10-IFC | 2022-02-23 | 1
ISAT-MP-AT-NA-U11-B | CPK03-R10-IFC | 2022-02-23 | 1
ISAT-MP-AT-NA-U12-B | CPK03-R10-IFC | 2022-02-23 | 1
ISAT-MP-AT-NA-W3-B | CPK03-R10-IFC | 2022-02-23 | 1
ISAT-MP-AT-NA-W4-B | CPK03-R10-IFC | 2022-02-23 | 1
ISAT-MP-BM-PF-S1-B-FL | CPK03-R10-IFC | 2022-02-23 | 2
ISAT-MP-BM-PF-G1-B-FL | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-BM-PF-A1-B-FL | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-BM-CS-S1-I-PI | CPK03-R10-IFC | 2022-02-23 | 6
ISAT-MP-BM-CS-S3-I-PI | CPK03-R10-IFC | 2022-02-23 | 6
ISAT-MP-BM-CS-G1-I-PI | CPK03-R10-IFC | 2022-02-23 | 6
ISAT-MP-BM-CS-G2-I-PI | CPK03-R10-IFC | 2022-02-23 | 6
ISAT-MP-BM-CS-G3-I-PI | CPK03-R10-IFC | 2022-02-23 | 2
ISAT-MP-BM-CS-G4-I-PI | CPK03-R10-IFC | 2022-02-23 | 2
ISAT-MP-BM-CS-A1-I-PI | CPK03-R10-IFC | 2022-02-23 | 6
ISAT-MP-BM-SS-A1-I-PI | CPK03-R10-IFC | 2022-02-23 | 3
ISAT-MP-BM-CS-A3-I-PI | CPK03-R10-IFC | 2022-02-23 | 2
ISAT-MP-BM-CS-A4-I-PI | CPK03-R10-IFC | 2022-02-23 | 2
ISAT-MP-BM-CS-A5-I-PI | CPK03-R10-IFC | 2022-02-23 | 2
ISAT-MP-BM-CS-S1-I-VB | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-CS-S1-U-VB | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-SS-S1-I-VB | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-SS-S1-U-VB | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-CS-G1-I-VB | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-SS-G1-U-VB | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-SS-G1-I-VB | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-CS-G2-I-VB | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-BM-SS-G2-U-VB | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-SS-G2-I-VB | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-SS-G3-I-VB | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-SS-G3-U-VB | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-CS-A1-I-VB | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-SS-A1-U-VB | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-CS-A2-I-VB | CPK03-R10-IFC | 2022-02-23 | 3
ISAT-MP-BM-SS-A2-U-VB | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-SS-A3-U-VB | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-SS-A3-I-VB | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-CS-A4-I-VB | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-SS-A4-U-VB | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-SS-A5-U-VB | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-SS-A5-I-VB | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-SS-A7-I-VB | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-CS-S1-I | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-BM-CS-S1-U | CPK03-R10-IFC | 2022-02-23 | 6
ISAT-MP-BM-CU-S1-U | CPK03-R10-IFC | 2022-02-23 | 1
ISAT-MP-BM-PF-S1-I | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-BM-PF-S1-U | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-BM-PS-S1-I | CPK03-R10-IFC | 2022-02-23 | 3
ISAT-MP-BM-PS-S1-U | CPK03-R10-IFC | 2022-02-23 | 6
ISAT-MP-BM-SS-S1-I | CPK03-R10-IFC | 2022-02-23 | 1
ISAT-MP-BM-CU-S2-U | CPK03-R10-IFC | 2022-02-23 | 1
ISAT-MP-BM-PF-S2-U | CPK03-R10-IFC | 2022-02-23 | 1
ISAT-MP-BM-PS-S2-U | CPK03-R10-IFC | 2022-02-23 | 1
ISAT-MP-BM-SS-S2-U | CPK03-R10-IFC | 2022-02-23 | 1
ISAT-MP-BM-CS-S7-U | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-BM-SS-S9-U | CPK03-R10-IFC | 2022-02-23 | 2
ISAT-MP-BM-CS-G1-I | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-BM-CS-G1-U | CPK03-R10-IFC | 2022-02-23 | 6
ISAT-MP-BM-CU-G1-U | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-BM-PF-G1-I | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-BM-PF-G1-U | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-BM-PS-G1-U | CPK03-R10-IFC | 2022-02-23 | 6
ISAT-MP-BM-PS-G1-I | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-BM-SS-G1-U | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-SS-G1-I | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-CS-G2-U | CPK03-R10-IFC | 2022-02-23 | 3
ISAT-MP-BM-PS-G2-I | CPK03-R10-IFC | 2022-02-23 | 1
ISAT-MP-BM-SS-G2-U | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-CS-G3-U | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-SS-G3-U | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-CS-G7-U | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-BM-SS-G9-U | CPK03-R10-IFC | 2022-02-23 | 2
ISAT-MP-BM-CS-A1-I | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-BM-CS-A1-U | CPK03-R10-IFC | 2022-02-23 | 6
ISAT-MP-BM-CU-A1-U | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-BM-PF-A1-I | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-BM-PF-A1-U | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-BM-PS-A1-I | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-BM-PS-A1-U | CPK03-R10-IFC | 2022-02-23 | 6
ISAT-MP-BM-SS-A1-U | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-SS-A1-I | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-PF-A2-I | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-BM-PF-A2-U | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-BM-PS-A2-U | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-BM-PS-A2-I | CPK03-R10-IFC | 2022-02-23 | 1
ISAT-MP-BM-SS-A2-U | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-PF-A3-U | CPK03-R10-IFC | 2022-02-23 | 2
ISAT-MP-BM-PF-A3-I | CPK03-R10-IFC | 2022-02-23 | 2
ISAT-MP-BM-CS-A4-U | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-SS-A4-I | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-BM-SS-A4-U | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-CS-A6-U | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-BM-SS-A6-U | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-BM-CS-A7-U | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-BM-SS-A7-U | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-BM-CS-A8-U | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-BM-SS-A9-U | CPK03-R10-IFC | 2022-02-23 | 2
ISAT-MP-FM-CS-S1-I-VB | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-FM-SS-S1-U | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-FM-NA-L1-B | CPK03-R10-IFC | 2022-02-23 | 1
ISAT-MP-OH-PF-S1-B-FL | CPK03-R10-IFC | 2022-02-23 | 3
ISAT-MP-OH-CS-S1-I | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-OH-CS-S2-I-PI | CPK03-R10-IFC | 2022-02-23 | 6
ISAT-MP-OH-CS-S2-I-VB | CPK03-R10-IFC | 2022-02-23 | 6
ISAT-MP-OH-SS-S2-U-VB | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-OH-SS-S2-I-VB | CPK03-R10-IFC | 2022-02-23 | 3
ISAT-MP-OH-CS-S3-I-VB | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-OH-CS-S1-U | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-OH-CU-S1-U | CPK03-R10-IFC | 2022-02-23 | 1
ISAT-MP-OH-PF-S1-I | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-OH-PF-S1-U | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-OH-PS-S1-U | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-OH-PS-S1-I | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-OH-SS-S1-U | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-OH-SS-S1-I | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-OH-PS-G1-U | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-OH-PF-G2-I | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-OH-PF-G2-U | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-OH-PS-G2-U | CPK03-R10-IFC | 2022-02-23 | 3
ISAT-MP-OH-SS-G2-U | CPK03-R10-IFC | 2022-02-23 | 3
ISAT-MP-OH-PF-A2-I | CPK03-R10-IFC | 2022-02-23 | 3
ISAT-MP-OH-PF-A2-U | CPK03-R10-IFC | 2022-02-23 | 3
ISAT-MP-OH-SS-A2-U | CPK03-R10-IFC | 2022-02-23 | 3
ISAT-MP-OH-PF-A3-U | CPK03-R10-IFC | 2022-02-23 | 3
ISAT-MP-OH-SS-A3-U | CPK03-R10-IFC | 2022-02-23 | 3
ISAT-MP-OH-NA-U1-B | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-RS-CS-A1-U-VB | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-RS-CS-A1-I-VB | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-RS-CS-A2-I-VB | CPK03-R10-IFC | 2022-02-23 | 3
ISAT-MP-RS-CS-S1-U | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-RS-PF-S1-U | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-RS-SS-S1-U | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-RS-CS-G2-I | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-RS-SS-G2-U | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-RS-CS-A1-U | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-RS-CS-A1-I | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-RS-PF-A1-U | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-RS-SS-A1-U | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-RS-SS-A1-I | CPK03-R10-IFC | 2022-02-23 | 1
ISAT-MP-SS-CS-L1-B-VB | CPK03-R10-IFC | 2022-02-23 | 6
ISAT-MP-SS-SS-L2-B-VB | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-SS-CS-L1-B | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-SS-CS-L2-B | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-SS-CS-L3-B | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-SS-NA-U1-B | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-SS-NA-U2-B | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-SS-NA-U3-B | CPK03-R10-IFC | 2022-02-23 | 3
ISAT-MP-SS-NA-U4-B | CPK03-R10-IFC | 2022-02-23 | 3
ISAT-MP-WM-NA-W1-B | CPK03-R10-IFC | 2022-02-23 | 4
ISAT-MP-WM-NA-W2-B | CPK03-R10-IFC | 2022-02-23 | 4
AT-VB-A-1 | CPK03-R10-IFC | 2022-02-23 | 5
MP-AT-A-2 | CPK03-R10-IFC | 2022-02-23 | 4
MP-AT-G-1 | CPK03-R10-IFC | 2022-02-23 | 5
MP-AT-G-2 | CPK03-R10-IFC | 2022-02-23 | 1
MP-AT-G-3 | CPK03-R10-IFC | 2022-02-23 | 1
MP-BM-A-1 | CPK03-R10-IFC | 2022-02-23 | 6
MP-BM-A-6 | CPK03-R10-IFC | 2022-02-23 | 5
MP-BM-A-7 | CPK03-R10-IFC | 2022-02-23 | 4
MP-BM-A-8 | CPK03-R10-IFC | 2022-02-23 | 4
MP-BM-A-9 | CPK03-R10-IFC | 2022-02-23 | 3
MP-BM-G-1 | CPK03-R10-IFC | 2022-02-23 | 6
MP-BM-G-3 | CPK03-R10-IFC | 2022-02-23 | 3
MP-FL-A-1 | CPK03-R10-IFC | 2022-02-23 | 4
MP-OH-S-1 | CPK03-R10-IFC | 2022-02-23 | 4
MP-OH-S-3 | CPK03-R10-IFC | 2022-02-23 | 3
MP-OH-S-5 | CPK03-R10-IFC | 2022-02-23 | 5
MP-RS-G-1 | CPK03-R10-IFC | 2022-02-23 | 5
MP-RS-S-2 | CPK03-R10-IFC | 2022-02-23 | 1
MP-RS-S-3 | CPK03-R10-IFC | 2022-02-23 | 4
MP-SS-S-2 | CPK03-R10-IFC | 2022-02-23 | 5
MP-VB-A-2 | CPK03-R10-IFC | 2022-02-23 | 5
MP-VB-S-1 | CPK03-R10-IFC | 2022-02-23 | 6
MP-VB-S-2 | CPK03-R10-IFC | 2022-02-23 | 6
MP-VB-S-3 | CPK03-R10-IFC | 2022-02-23 | 5
ISAT-MP-AT-CS-U1-B | CPK03-R1-IFC | 2021-11-02 | 6
ISAT-MP-AT-CS-U2-B | CPK03-R1-IFC | 2021-11-02 | 6
D1X-S0-6252 | CPK03-R1-IFC | 2021-11-02 | 1
D1X-SS-5RA-4000 | CPK03-R1-IFC | 2021-11-02 | 1
MS1-SS-5RA-4000 | CPK03-R1-IFC | 2021-11-02 | 1
MS1-S0-6251 | CPK03-R1-IFC | 2021-11-02 | 1
D1X-MS-1000 | CPK03-R1-IFC | 2021-11-02 | 1
MS1-MS-1000 | CPK03-R1-IFC | 2021-11-02 | 1
MS1-MS-1001 | CPK03-R1-IFC | 2021-11-02 | 1
RAC-EO-OOOO | CPK03-R1-IFC | 2021-11-02 | 1
RAC-E0-0001 | CPK03-R1-IFC | 2021-11-02 | 2
D1X-EH-5RA-C0000 | CPK03-R1-IFC | 2021-11-02 | 1
MS1-EH-5RE-B0000 | CPK03-R1-IFC | 2021-11-02 | 1
MS1-EH-5RE-C0000 | CPK03-R1-IFC | 2021-11-02 | 1
ISAT-MP-BM-CS-A1-I-PI | CPK03-R1-IFC | 2021-11-02 | 6
RA-ST-2500 | CPK03-R1-IFC | 2021-11-02 | 4
RA-ST-2501 | CPK03-R1-IFC | 2021-11-02 | 5
RA-ST-2502 | CPK03-R1-IFC | 2021-11-02 | 5
RA-ST-2504 | CPK03-R1-IFC | 2021-11-02 | 5
RA-ST-2505 | CPK03-R1-IFC | 2021-11-02 | 5
RA-ST-2506 | CPK03-R1-IFC | 2021-11-02 | 5
RA-ST-2507 | CPK03-R1-IFC | 2021-11-02 | 5
RA-ST-2508 | CPK03-R1-IFC | 2021-11-02 | 5
RA-ST-2509 | CPK03-R1-IFC | 2021-11-02 | 5
RA-ST-2510 | CPK03-R1-IFC | 2021-11-02 | 5
RA-ST-2511 | CPK03-R1-IFC | 2021-11-02 | 5
RA-ST-2512 | CPK03-R1-IFC | 2021-11-02 | 5
RA-ST-2513 | CPK03-R1-IFC | 2021-11-02 | 5
RA-ST-2514 | CPK03-R1-IFC | 2021-11-02 | 5
RA-ST-2515 | CPK03-R1-IFC | 2021-11-02 | 5
RA-ST-2516 | CPK03-R1-IFC | 2021-11-02 | 5
RA-ST-2517 | CPK03-R1-IFC | 2021-11-02 | 5
RA-ST-2518 | CPK03-R1-IFC | 2021-11-02 | 5
RA-ST-2519 | CPK03-R1-IFC | 2021-11-02 | 5
RA-ST-2520 | CPK03-R1-IFC | 2021-11-02 | 5
ISAT-MP-BM-CS-A1-U | CPK03-R1-IFC | 2021-11-02 | 6
ISAT-MP-BM-CS-G1-I-PI | CPK03-R1-IFC | 2021-11-02 | 6
ISAT-MP-BM-CS-G1-U | CPK03-R1-IFC | 2021-11-02 | 6
ISAT-MP-BM-CS-G2-I-PI | CPK03-R1-IFC | 2021-11-02 | 6
ISAT-MP-BM-CS-S1-I-PI | CPK03-R1-IFC | 2021-11-02 | 6
ISAT-MP-BM-CS-S1-U | CPK03-R1-IFC | 2021-11-02 | 6
ISAT-MP-BM-CS-S3-I-PI | CPK03-R1-IFC | 2021-11-02 | 6
ISAT-MP-BM-PS-A1-U | CPK03-R1-IFC | 2021-11-02 | 6
ISAT-MP-BM-PS-G1-U | CPK03-R1-IFC | 2021-11-02 | 6
ISAT-MP-BM-PS-S1-U | CPK03-R1-IFC | 2021-11-02 | 6
ISAT-MP-OH-CS-S2-I-PI | CPK03-R1-IFC | 2021-11-02 | 6
ISAT-MP-OH-CS-S2-I-VB | CPK03-R1-IFC | 2021-11-02 | 6
ISAT-MP-SS-CS-L1-B-VB | CPK03-R1-IFC | 2021-11-02 | 6
MP-BM-A-1 | CPK03-R1-IFC | 2021-11-02 | 6
MP-BM-G-1 | CPK03-R1-IFC | 2021-11-02 | 6
MP-VB-S-1 | CPK03-R1-IFC | 2021-11-02 | 6
MP-VB-S-2 | CPK03-R1-IFC | 2021-11-02 | 6
RA-ST-2503 | CPK03-R1-IFC | 2021-11-02 | 5
RAC-GN-0001 | CPK03-R2-IFC | 2021-11-28 | 5
RAC-GN-0002 | CPK03-R2-IFC | 2021-11-28 | 5
RAC-GN-0003 | CPK03-R2-IFC | 2021-11-28 | 5
RAC-GN-0004 | CPK03-R2-IFC | 2021-11-28 | 5
RAC-GN-0005 | CPK03-R2-IFC | 2021-11-28 | 5
RAC-GN-0006 | CPK03-R2-IFC | 2021-11-28 | 5
RAC-GN-0007 | CPK03-R2-IFC | 2021-11-28 | 5
RAC-GN-0008 | CPK03-R2-IFC | 2021-11-28 | 5
RAC-GN-0009 | CPK03-R2-IFC | 2021-11-28 | 5
RAC-GN-0010 | CPK03-R2-IFC | 2021-11-28 | 5
MS1-S0-0010 | CPK03-R2-IFC | 2021-11-28 | 8
MS1-S0-0BA-B0400 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-S0-0BA-B0400-D | CPK03-R2-IFC | 2021-11-28 | 2
MS1-S0-1SA-D04C0 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-S0-1SA-4000 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-SS-1SF-B0000 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-S0-1SF-B01B0 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-SS-1SF-C0000 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-SS-1SF-D0000-D | CPK03-R2-IFC | 2021-11-28 | 1
MS1-SS-1SF-D0000 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-S0-1SF-4000 | CPK03-R2-IFC | 2021-11-28 | 4
MS1-SS-1SH-B0000 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-SS-1SH-C0000 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-SS-1SH-D0000 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-SS-2FA-B0000-D | CPK03-R2-IFC | 2021-11-28 | 1
MS1-SS-2FA-C0000-D | CPK03-R2-IFC | 2021-11-28 | 1
MS1-SS-2FA-D0000-D | CPK03-R2-IFC | 2021-11-28 | 1
MS1-SS-2FK-B0000 | CPK03-R2-IFC | 2021-11-28 | 4
MS1-SS-2FK-C0000 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-SS-2FL-B0000 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-SS-2FL-C0000 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-SS-2FM-B0000 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-SS-2FM-B0300 | CPK03-R2-IFC | 2021-11-28 | 4
MS1-SS-2FM-C0000 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-SS-4DA-C0100 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-SS-5RC-B0000 | CPK03-R2-IFC | 2021-11-28 | 6
MS1-SS-5RC-C0000 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-SS-5RE-B0000 | CPK03-R2-IFC | 2021-11-28 | 4
MS1-SS-5RE-4000 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-SS-5RF-C0000 | CPK03-R2-IFC | 2021-11-28 | 5
MS1-SS-5RF-4000 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-SS-5RJ-B0000 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-SS-5RO-B0000 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-SS-5RP-B0000 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-SS-5RS-B0000 | CPK03-R2-IFC | 2021-11-28 | 4
MS1-SS-5RX-B0000 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-S0-6201 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-S0-6203 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-S0-6204 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-S0-6210 | CPK03-R2-IFC | 2021-11-28 | 6
MS1-S0-6214-D | CPK03-R2-IFC | 2021-11-28 | 3
MS1-A0-0722 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-A0-6223 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-A0-6224 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-A0-6225 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AC-2FA-A0D00 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-AC-2FA-B0000 | CPK03-R2-IFC | 2021-11-28 | 4
MS1-AC-2FA-C0000 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-AC-2FH-4001 | CPK03-R2-IFC | 2021-11-28 | 4
MS1-AC-2FH-B0000 | CPK03-R2-IFC | 2021-11-28 | 5
MS1-AC-2FH-B0000-S | CPK03-R2-IFC | 2021-11-28 | 5
MS1-AC-2FH-B0D00-S | CPK03-R2-IFC | 2021-11-28 | 4
MS1-AC-2FH-C0000 | CPK03-R2-IFC | 2021-11-28 | 4
MS1-AC-2FH-C0000-S | CPK03-R2-IFC | 2021-11-28 | 4
MS1-AC-2FH-D0000 | CPK03-R2-IFC | 2021-11-28 | 4
MS1-AC-2FH-D0000-S | CPK03-R2-IFC | 2021-11-28 | 4
MS1-AC-2FI-4002 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-AC-2FI-B0C00-S | CPK03-R2-IFC | 2021-11-28 | 3
MS1-AC-2FN-A0D00 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AC-2FN-B0000 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AC-2FN-C0000 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AC-6200 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-AI-0106 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AI-0107 | CPK03-R2-IFC | 2021-11-28 | 4
MS1-AR-2FB-A0D00 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-AR-2FB-B0000 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-AR-2FB-C0000 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-AW-0BA-A0D00 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AW-0BA-B0000 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AW-1SA-A0D00 | CPK03-R2-IFC | 2021-11-28 | 3 | Y
MS1-AW-1SA-B0000 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-AW-1SA-B0000-D | CPK03-R2-IFC | 2021-11-28 | 1
MS1-AW-1SA-C0000 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-AW-1SA-C0000-D | CPK03-R2-IFC | 2021-11-28 | 3
MS1-AW-1SA-D0000 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AW-2FA-A0D00 | CPK03-R2-IFC | 2021-11-28 | 4
MS1-AW-2FA-B0000 | CPK03-R2-IFC | 2021-11-28 | 4
MS1-AW-2FA-B0000-D | CPK03-R2-IFC | 2021-11-28 | 1
MS1-AW-2FA-C0000 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-AW-2FA-C0000-D | CPK03-R2-IFC | 2021-11-28 | 1
MS1-AW-2FA-D0000-D | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AW-2FM-A0D00 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AW-2FM-B0000 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-AW-2FM-C0000 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-AW-2UA-A0D00 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AW-2UA-B0000 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AW-2UA-C0000 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AW-3FA-A0D00 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-AW-4DA-A0D00 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-AW-5RA-A0D00 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-AW-5RA-B0000 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-AW-6115 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AW-6116 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AW-6117 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AW-6118 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AW-6119 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AW-6120 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AW-6121 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AW-6122 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AW-6123 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AW-6124 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AZ-0100 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-AZ-0101 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-AZ-0200 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AZ-0201 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AZ-0202 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AZ-0203 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AZ-0204 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AZ-0205 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-AZ-2FA-A0D00 | CPK03-R2-IFC | 2021-11-28 | 3
RAC-A0-0001 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-A0-0002 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-A0-0003 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-A0-9000 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-A0-9001 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-A0-9002 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-AZ-0001 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-AZ-0200 | CPK03-R2-IFC | 2021-11-28 | 1
D1X-237-PH-Z41 | CPK03-R2-IFC | 2021-11-28 | 1
D1X-249-PU-Z01 | CPK03-R2-IFC | 2021-11-28 | 2
D1X-409-PG-Z33 | CPK03-R2-IFC | 2021-11-28 | 1
D1X-530-PK-Z02 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-202-PH-Z10 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-212-PA-Z10 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-217-PG-Z10 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-218-PA-Z10 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-221-PV-Z10 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-221-PV-Z11 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-237-PH-Z10 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-245-PU-Z10 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-248-PH-Z10 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-249-PH-Z10 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-261-PW-Z10 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-261-PW-Z13 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-266-PW-Z10 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-269-PW-Z10 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-270-PW-Z10 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-280-PW-Z10 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-299-PW-Z10 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-401-PG-Z10 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-403-PG-Z10 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-404-PG-Z10 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-408-PG-Z10 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-409-PG-Z10 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-412-PG-Z10 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-523-PK-Z22 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-524-PK-Z22 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-528-PK-Z22 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-PE-0211 | CPK03-R2-IFC | 2021-11-28 | 4
MS1-PE-0BA-A0D00 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-PE-0BA-B0000 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-PE-1SA-A0D00 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-PE-1SA-B0000 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-PE-1SA-C0000 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-PE-1SA-D0000 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-PE-5RA-B0000 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-WP-0150 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-FZ-1SA-A0D00 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-FZ-2FA-A0D00 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-FZ-4DA-A0D00 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-FZ-5RA-A0D00 | CPK03-R2-IFC | 2021-11-28 | 1
CB4-ME-20A-B0000 | CPK03-R2-IFC | 2021-11-28 | 1
D1X-133-MX-A01 | CPK03-R2-IFC | 2021-11-28 | 1
D1X-133-MX-A01-D | CPK03-R2-IFC | 2021-11-28 | 1
D1X-138-MX-A01 | CPK03-R2-IFC | 2021-11-28 | 1
D1X-138-MX-A01-D | CPK03-R2-IFC | 2021-11-28 | 1
MS1-104-MH-A01 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-104-MH-A03 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-111-MW-A03 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-117-MW-A02 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-ME-1SA-A0D00 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-ME-2FA-A0D00 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-ME-5RA-A0D00 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-MH-0150 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-E0-0000 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-E0-0001 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-1650 | CPK03-R2-IFC | 2021-11-28 | 1
CB4-ES-1252C | CPK03-R2-IFC | 2021-11-28 | 2
CB4-ES-1400 | CPK03-R2-IFC | 2021-11-28 | 2
CB4-EE-20A-A0000 | CPK03-R2-IFC | 2021-11-28 | 1
CB4-EE-20A-B0000 | CPK03-R2-IFC | 2021-11-28 | 1
D1X-ES-1257C | CPK03-R2-IFC | 2021-11-28 | 1
D1X-ES-1322C | CPK03-R2-IFC | 2021-11-28 | 1
MS1-ES-1001 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-ES-1005 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-ES-1050 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-ES-1052 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-ES-1152B | CPK03-R2-IFC | 2021-11-28 | 1
MS1-ES-1152C | CPK03-R2-IFC | 2021-11-28 | 1
MS1-ES-1152D | CPK03-R2-IFC | 2021-11-28 | 1
MS1-ES-1153D | CPK03-R2-IFC | 2021-11-28 | 2
MS1-ES-1154D | CPK03-R2-IFC | 2021-11-28 | 2
MS1-ES-1250A | CPK03-R2-IFC | 2021-11-28 | 3
MS1-ES-1250B | CPK03-R2-IFC | 2021-11-28 | 2
MS1-ES-1251C | CPK03-R2-IFC | 2021-11-28 | 3
MS1-ES-1300 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-ES-1301 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-ES-1304 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-ES-1305 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-ES-1306 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-ES-1308 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-ES-1311C | CPK03-R2-IFC | 2021-11-28 | 2
MS1-ES-1314B | CPK03-R2-IFC | 2021-11-28 | 3
MS1-ES-1326B | CPK03-R2-IFC | 2021-11-28 | 3
MS1-ES-1342 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-ES-1343A | CPK03-R2-IFC | 2021-11-28 | 2
MS1-ES-1344B | CPK03-R2-IFC | 2021-11-28 | 3
MS1-ES-1503 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-EE-0BA-B0000 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-EE-1SA-A0D00 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-EE-1SA-B0000 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-EE-1SA-C0000 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-EE-1SA-D0000 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-EE-2FA-C0000 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-EE-2FA-D0000 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-EE-4DA-B0000 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-EE-4DA-C0000 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-EE-5RA-B0000 | CPK03-R2-IFC | 2021-11-28 | 1
CB4-IE-10A-B0000 | CPK03-R2-IFC | 2021-11-28 | 1
CB4-IE-20A-B0000 | CPK03-R2-IFC | 2021-11-28 | 1
D1X-IE-1YA-F0000 | CPK03-R2-IFC | 2021-11-28 | 2
D1X-IE-1YA-J0000 | CPK03-R2-IFC | 2021-11-28 | 2
D1X-IE-2SA-E0000 | CPK03-R2-IFC | 2021-11-28 | 1
D1X-IE-2SA-J0000 | CPK03-R2-IFC | 2021-11-28 | 1
DX3-IE-4JA-D0000 | CPK03-R2-IFC | 2021-11-28 | 1
DX3-IE-5JA-D0000 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-I0-4DA-D0000 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-I0-9001 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-IE-0BA-B0000 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-IE-0BA-C0000 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-IE-1001 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-IE-1004 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-IE-1005 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-IE-1022 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-IE-1024 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-IE-1025 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-IE-1026 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-IE-1220 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-IE-1220-D | CPK03-R2-IFC | 2021-11-28 | 1
MS1-IE-1SA-B0000 | CPK03-R2-IFC | 2021-11-28 | 4
MS1-IE-1SA-C0000 | CPK03-R2-IFC | 2021-11-28 | 5
MS1-IE-1SA-D0000 | CPK03-R2-IFC | 2021-11-28 | 5
MS1-IE-2FA-B0000 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-IE-2FA-C0000 | CPK03-R2-IFC | 2021-11-28 | 4
MS1-IE-2FA-D0000 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-IE-3FA-B0000 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-IE-3FA-C0000 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-IE-3FA-D0000 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-IE-4DA-B0000 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-IE-4DA-C0000 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-IE-5RA-B0000 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-IE-5RA-C0000 | CPK03-R2-IFC | 2021-11-28 | 2
PB1-I0-10A-A0000 | CPK03-R2-IFC | 2021-11-28 | 1
PB1-I0-10A-B0000 | CPK03-R2-IFC | 2021-11-28 | 1
D1X-TD-1603 | CPK03-R2-IFC | 2021-11-28 | 1
D1X-TD-1692 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-TC-1SA-B0000 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-TC-1SA-C0000 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-TC-1SA-D0000 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-TC-2FA-B0000 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-TC-2FA-C0000 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-TC-5RA-B0000 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-TD-1455 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-TD-1610 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-TT-1605 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-TT-1606 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-TT-1607 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-TT-1608 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-TT-1609 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-TT-1SA-A0D00-D | CPK03-R2-IFC | 2021-11-28 | 1
MS1-TT-1SA-B0000 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-TT-1SA-C0000 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-TT-1SA-D0000 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-T0-0001 | CPK03-R2-IFC | 2021-11-28 | 4
RAC-T0-9001 | CPK03-R2-IFC | 2021-11-28 | 4
RAC-T0-9002 | CPK03-R2-IFC | 2021-11-28 | 3
RAC-T0-9004 | CPK03-R2-IFC | 2021-11-28 | 3
RAC-T0-9005 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-TC-1453 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-TC-1454 | CPK03-R2-IFC | 2021-11-28 | 2
CB4-111-D0-A04 | CPK03-R2-IFC | 2021-11-28 | 1
CB4-111-D0-Z02 | CPK03-R2-IFC | 2021-11-28 | 1
D1X-111-D0-Z03 | CPK03-R2-IFC | 2021-11-28 | 1
D1X-133-D0-A24 | CPK03-R2-IFC | 2021-11-28 | 1
D1X-133-D0-A24-D | CPK03-R2-IFC | 2021-11-28 | 1
D1X-133-D0-Z01-D | CPK03-R2-IFC | 2021-11-28 | 1
D1X-138-D0-A29 | CPK03-R2-IFC | 2021-11-28 | 3
D1X-201-D0-B03 | CPK03-R2-IFC | 2021-11-28 | 1
D1X-201-D0-B05 | CPK03-R2-IFC | 2021-11-28 | 1
D1X-202-D0-B01 | CPK03-R2-IFC | 2021-11-28 | 1
D1X-202-D0-B02 | CPK03-R2-IFC | 2021-11-28 | 1
D1X-218-D0-A01 | CPK03-R2-IFC | 2021-11-28 | 1
D1X-237-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 1
D1X-243-D0-Z04 | CPK03-R2-IFC | 2021-11-28 | 1
D1X-243-D0-Z04-D | CPK03-R2-IFC | 2021-11-28 | 1
D1X-245-D0-B01 | CPK03-R2-IFC | 2021-11-28 | 2
D1X-245-D0-B02 | CPK03-R2-IFC | 2021-11-28 | 2
D1X-262-D0-Z06 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-101-D0-A02 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-102-D0-A07 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-102-D0-A08 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-103-D0-A02 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-104-D0-A03 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-104-D0-A05 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-104-D0-A05-D | CPK03-R2-IFC | 2021-11-28 | 1
MS1-104-D0-A06 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-104-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-104-D0-Z02 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-106-D0-A01 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-111-D0-Z04 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-113-D0-A02 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-113-D0-Z05 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-131-D0-A01 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-132-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-132-D0-Z02 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-132-D0-Z03 | CPK03-R2-IFC | 2021-11-28 | 3 | Y
MS1-133-D0-A03 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-133-D0-A04 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-133-D0-A05 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-133-D0-A06 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-133-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-133-D0-Z01-D | CPK03-R2-IFC | 2021-11-28 | 1
MS1-133-D0-Z02 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-133-D0-Z03 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-138-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-138-D0-Z02 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-138-D0-Z03 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-147-D0-A01 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-147-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-147-D0-Z02 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-202-D0-A01 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-202-D0-A02 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-202-D0-A03 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-202-D0-Y01 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-210-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-211-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-212-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-213-D0-Z02 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-213-D0-Z02-D | CPK03-R2-IFC | 2021-11-28 | 1
MS1-217-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-217-D0-Z02 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-218-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-221-D0-A01 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-221-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-221-D0-Z03 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-222-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-222-D0-Z02 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-237-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-237-D0-Z03 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-245-D0-A01 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-245-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-245-D0-Z01-D | CPK03-R2-IFC | 2021-11-28 | 1
MS1-245-D0-Z07 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-248-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-249-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-261-D0-B01 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-261-D0-B01-D | CPK03-R2-IFC | 2021-11-28 | 2
MS1-261-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-261-D0-Z01-D | CPK03-R2-IFC | 2021-11-28 | 3
MS1-266-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-266-D0-Z01-D | CPK03-R2-IFC | 2021-11-28 | 2
MS1-269-D0-A01 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-269-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-270-D0-A01 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-270-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-272-D0-A02 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-280-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-280-D0-Z01-D | CPK03-R2-IFC | 2021-11-28 | 1
MS1-299-D0-A01 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-299-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-400-D0-A02 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-401-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-402-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-403-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-404-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-408-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-409-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-412-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-520-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-523-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-524-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-527-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-528-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-529-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-530-D0-Z01 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-603-D0-A01 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-605-D0-A01 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-608-D0-A01 | CPK03-R2-IFC | 2021-11-28 | 2
PB1-241-D0-A06 | CPK03-R2-IFC | 2021-11-28 | 1
400-KSI-INTEL-AP-001 | CPK03-R2-IFC | 2021-11-28 | 2
DM-UHP-FM5-G-V-BKT-9IN | CPK03-R2-IFC | 2021-11-28 | 1
1810_CMS_04_01 | CPK03-R2-IFC | 2021-11-28 | 2
1810_CMS_04_02 | CPK03-R2-IFC | 2021-11-28 | 2
1810_VFD_08 | CPK03-R2-IFC | 2021-11-28 | 4
1810_VFD_09 | CPK03-R2-IFC | 2021-11-28 | 3
25_14_01_00_QFS_01 | CPK03-R2-IFC | 2021-11-28 | 1
D-I-1271_03 | CPK03-R2-IFC | 2021-11-28 | 1
D-I-1271_05 | CPK03-R2-IFC | 2021-11-28 | 1
D-I-1350_01 | CPK03-R2-IFC | 2021-11-28 | 1
D-I-1910_01 | CPK03-R2-IFC | 2021-11-28 | 2
D-I-1910_02 | CPK03-R2-IFC | 2021-11-28 | 2
D-I-1910_03 | CPK03-R2-IFC | 2021-11-28 | 2
D-I-1910_04 | CPK03-R2-IFC | 2021-11-28 | 2
D-I-1910_05 | CPK03-R2-IFC | 2021-11-28 | 2
D-I-1910_06 | CPK03-R2-IFC | 2021-11-28 | 2
D-I-1910_07 | CPK03-R2-IFC | 2021-11-28 | 2
D-I-1910_08 | CPK03-R2-IFC | 2021-11-28 | 3
D-I-1910_09 | CPK03-R2-IFC | 2021-11-28 | 2
D-I-1910_10 | CPK03-R2-IFC | 2021-11-28 | 2
D-I-1910_11 | CPK03-R2-IFC | 2021-11-28 | 2
D-I-1910_12 | CPK03-R2-IFC | 2021-11-28 | 2
D-I-1910_13 | CPK03-R2-IFC | 2021-11-28 | 2
D-I-1910_14 | CPK03-R2-IFC | 2021-11-28 | 2
D-I-1910_15 | CPK03-R2-IFC | 2021-11-28 | 2
D-I-1910_16 | CPK03-R2-IFC | 2021-11-28 | 2
D-I-1910_17 | CPK03-R2-IFC | 2021-11-28 | 2
D-I-1910_18 | CPK03-R2-IFC | 2021-11-28 | 2
D-I-1910_19 | CPK03-R2-IFC | 2021-11-28 | 2
D-I-1910_20 | CPK03-R2-IFC | 2021-11-28 | 2
D-I-1910_21 | CPK03-R2-IFC | 2021-11-28 | 1
D-I-1910_22 | CPK03-R2-IFC | 2021-11-28 | 1
D-I-1910_23 | CPK03-R2-IFC | 2021-11-28 | 4
D-I-1910_24 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-A0-0700 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0701 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0702 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0703 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0704 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0705 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0706 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0708 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0709 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0710 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0711 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0712 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0713 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0714 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0715 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0716 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0717 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0718 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0719 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0720 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0721 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0723 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-A0-0724 | CPK03-R2-IFC | 2021-11-28 | 3
MS1-A0-0725 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0726 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0727 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0728 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0730 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0731 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0732 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0733 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0735 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0736 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0737 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0738 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0739 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0740 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0741 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0742 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0743 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0744 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0745 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0746 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0747 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0748 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0749 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0750 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0751 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0752 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0753 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0754 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0755 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0756 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0757 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0759 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0760 | CPK03-R2-IFC | 2021-11-28 | 2
MS1-A0-0761 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D0200 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D0300 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D0301 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D0305 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D0306 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D0307 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D0310 | CPK03-R2-IFC | 2021-11-28 | 1
RA-AR-D0312 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D0313 | CPK03-R2-IFC | 2021-11-28 | 1
RA-AR-D0314 | CPK03-R2-IFC | 2021-11-28 | 1
RA-AR-D0315 | CPK03-R2-IFC | 2021-11-28 | 1
RA-AR-D0316 | CPK03-R2-IFC | 2021-11-28 | 1
RA-AR-D0317 | CPK03-R2-IFC | 2021-11-28 | 1
RA-AR-D0500 | CPK03-R2-IFC | 2021-11-28 | 1
RA-AR-D0600 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D0601 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1600 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1601 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1603 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1604 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1606 | CPK03-R2-IFC | 2021-11-28 | 3
RA-AR-D1607 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1609 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1610 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1611 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1612 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1614 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1617 | CPK03-R2-IFC | 2021-11-28 | 3
RA-AR-D1618 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1700 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1703 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1704 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1705 | CPK03-R2-IFC | 2021-11-28 | 3
RA-AR-D1706 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1707 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1708 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1709 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1710 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1711 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1712 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1713 | CPK03-R2-IFC | 2021-11-28 | 3
RA-AR-D1714 | CPK03-R2-IFC | 2021-11-28 | 3
RA-AR-D1715 | CPK03-R2-IFC | 2021-11-28 | 3
RA-AR-D1716 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1800 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1801 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1802 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1803 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1804 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1806 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1807 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1808 | CPK03-R2-IFC | 2021-11-28 | 3
RA-AR-D1809 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1903 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1906 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1907 | CPK03-R2-IFC | 2021-11-28 | 1
RA-AR-D1908 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1909 | CPK03-R2-IFC | 2021-11-28 | 1
RA-AR-D1910 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1911 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1912 | CPK03-R2-IFC | 2021-11-28 | 3
RA-AR-D1913 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1914 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D1915 | CPK03-R2-IFC | 2021-11-28 | 3
RA-AR-D1916 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2300 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2301 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2302 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2303 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2304 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2305 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2306 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2307 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2308 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2309 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2400 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2402 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2403 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2404 | CPK03-R2-IFC | 2021-11-28 | 1
RA-AR-D2405 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2406 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2407 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2408 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2409 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2410 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2411 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2412 | CPK03-R2-IFC | 2021-11-28 | 1
RA-AR-D2413 | CPK03-R2-IFC | 2021-11-28 | 1
RA-AR-D2414 | CPK03-R2-IFC | 2021-11-28 | 1
RA-AR-D2415 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2416 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2500 | CPK03-R2-IFC | 2021-11-28 | 3
RA-AR-D2501 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2502 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2503 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2504 | CPK03-R2-IFC | 2021-11-28 | 3
RA-AR-D2900 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2901 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2902 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2903 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2904 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2905 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2906 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2907 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2908 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2909 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2910 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2911 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2912 | CPK03-R2-IFC | 2021-11-28 | 2
RA-AR-D2913 | CPK03-R2-IFC | 2021-11-28 | 2
RA-FP-D002 | CPK03-R2-IFC | 2021-11-28 | 1
RA-FP-D006 | CPK03-R2-IFC | 2021-11-28 | 1
RA-FP-D008 | CPK03-R2-IFC | 2021-11-28 | 1
RA-FP-D009 | CPK03-R2-IFC | 2021-11-28 | 1
RA-FP-D010 | CPK03-R2-IFC | 2021-11-28 | 1
RA-FP-D012 | CPK03-R2-IFC | 2021-11-28 | 1
RA-FP-D013 | CPK03-R2-IFC | 2021-11-28 | 1
RA-FP-D014 | CPK03-R2-IFC | 2021-11-28 | 1
RA-FP-D015 | CPK03-R2-IFC | 2021-11-28 | 1
RA-FP-D016 | CPK03-R2-IFC | 2021-11-28 | 1
RA-FP-D017 | CPK03-R2-IFC | 2021-11-28 | 1
RA-FP-D018 | CPK03-R2-IFC | 2021-11-28 | 1
RA-FP-D019 | CPK03-R2-IFC | 2021-11-28 | 1
RA-FP-D021 | CPK03-R2-IFC | 2021-11-28 | 1
RA-FP-D022 | CPK03-R2-IFC | 2021-11-28 | 1
RA-FP-D024 | CPK03-R2-IFC | 2021-11-28 | 1
RA-FP-D025 | CPK03-R2-IFC | 2021-11-28 | 1
RA-FP-D026 | CPK03-R2-IFC | 2021-11-28 | 1
RA-FP-D027 | CPK03-R2-IFC | 2021-11-28 | 1
RA-FP-D031 | CPK03-R2-IFC | 2021-11-28 | 1
RA-ME-D005 | CPK03-R2-IFC | 2021-11-28 | 2
RA-ME-D007 | CPK03-R2-IFC | 2021-11-28 | 2
RA-ME-D008 | CPK03-R2-IFC | 2021-11-28 | 2
RA-ME-D009 | CPK03-R2-IFC | 2021-11-28 | 2
RA-ME-D010 | CPK03-R2-IFC | 2021-11-28 | 2
RA-ME-D011 | CPK03-R2-IFC | 2021-11-28 | 2
RA-ME-D015 | CPK03-R2-IFC | 2021-11-28 | 2
RA-ME-D018 | CPK03-R2-IFC | 2021-11-28 | 2
RA-ME-D019 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D002 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D003 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D004 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D005 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D007 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D008 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D009 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D010 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MH-D011 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MH-D013 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MH-D015 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MH-D016 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MH-D017 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MH-D018 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MH-D019 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D020 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MH-D021 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D022 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D023 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D024 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D025 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D028 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MH-D033 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D034 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D035 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MH-D036 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MH-D037 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MH-D038 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MH-D039 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D040 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D041 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D045 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D046 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D047 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D048 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D049 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D050 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D051 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MH-D052 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MH-D053 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MH-D054 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MH-D057 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MH-D059 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D060 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D061 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D062 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MH-D063 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D064 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D065 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D067 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D070 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D073 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D074 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D075 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D076 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D077 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D078 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D080 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D082 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D083 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D084 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D085 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D086 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MH-D091 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D093 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D094 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D096 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D097 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MH-D107 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D108 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D110 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D112 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D113 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D114 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D115 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D116 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D117 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D118 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MH-D119 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MP-D001 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MP-D002 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MP-D003 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MP-D004 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MP-D005 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MP-D010 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MP-D011 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MP-D013 | CPK03-R2-IFC | 2021-11-28 | 3
RA-MP-D016 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MP-D017 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MP-D018 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MP-D021 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MP-D023 | CPK03-R2-IFC | 2021-11-28 | 2
RA-MP-D046 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9001 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9002 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9003 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9004 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9005 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9006 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9007 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9008 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9009 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9010 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9011 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9012 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9013 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9014 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9015 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9016 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9017 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9018 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9019 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9020 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9021 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9022 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9023 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9024 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9025 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9026 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9027 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9028 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9029 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9030 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9031 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9032 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9033 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9034 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9035 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9036 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9037 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9038 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9039 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9040 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9041 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9042 | CPK03-R2-IFC | 2021-11-28 | 2
RA-P0-9043 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9044 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9045 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9046 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9047 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9048 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9049 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9050 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9051 | CPK03-R2-IFC | 2021-11-28 | 3
RA-P0-9052 | CPK03-R2-IFC | 2021-11-28 | 3
RA-PL-D001 | CPK03-R2-IFC | 2021-11-28 | 3
RA-PL-D002 | CPK03-R2-IFC | 2021-11-28 | 3
RA-PL-D003 | CPK03-R2-IFC | 2021-11-28 | 3
RA-PL-D004 | CPK03-R2-IFC | 2021-11-28 | 3
RA-PL-D005 | CPK03-R2-IFC | 2021-11-28 | 3
RA-PL-D006 | CPK03-R2-IFC | 2021-11-28 | 3
RA-PL-D007 | CPK03-R2-IFC | 2021-11-28 | 3
RA-PL-D008 | CPK03-R2-IFC | 2021-11-28 | 2
RA-PL-D101 | CPK03-R2-IFC | 2021-11-28 | 2
RA-PL-D102 | CPK03-R2-IFC | 2021-11-28 | 2
RA-PL-D103 | CPK03-R2-IFC | 2021-11-28 | 2
RA-PL-D104 | CPK03-R2-IFC | 2021-11-28 | 2
RA-PL-D106 | CPK03-R2-IFC | 2021-11-28 | 2
RA-PL-D108 | CPK03-R2-IFC | 2021-11-28 | 2
RA-PL-D112 | CPK03-R2-IFC | 2021-11-28 | 2
RA-PL-D114 | CPK03-R2-IFC | 2021-11-28 | 2
RA-PL-D115 | CPK03-R2-IFC | 2021-11-28 | 2
RA-PL-D116 | CPK03-R2-IFC | 2021-11-28 | 3
RA-PL-D117 | CPK03-R2-IFC | 2021-11-28 | 3
RA-PL-D118 | CPK03-R2-IFC | 2021-11-28 | 3
RA-PL-D119 | CPK03-R2-IFC | 2021-11-28 | 3
RA-PL-D120 | CPK03-R2-IFC | 2021-11-28 | 3
RA-PL-D121 | CPK03-R2-IFC | 2021-11-28 | 3
RA-PL-D122 | CPK03-R2-IFC | 2021-11-28 | 3
RA-PL-D123 | CPK03-R2-IFC | 2021-11-28 | 3
RA-PL-D126 | CPK03-R2-IFC | 2021-11-28 | 2
RA-PL-D127 | CPK03-R2-IFC | 2021-11-28 | 3
RA-PL-D128 | CPK03-R2-IFC | 2021-11-28 | 3
RA-PL-D129 | CPK03-R2-IFC | 2021-11-28 | 2
RA-PL-D131 | CPK03-R2-IFC | 2021-11-28 | 2
RA-PL-D132 | CPK03-R2-IFC | 2021-11-28 | 3
RA-PL-D133 | CPK03-R2-IFC | 2021-11-28 | 2
RA-PL-D134 | CPK03-R2-IFC | 2021-11-28 | 2
RA-PL-D136 | CPK03-R2-IFC | 2021-11-28 | 3
RA-PL-D137 | CPK03-R2-IFC | 2021-11-28 | 3
RA-PL-D138 | CPK03-R2-IFC | 2021-11-28 | 3
RA-PL-D139 | CPK03-R2-IFC | 2021-11-28 | 3
RA-PL-D140 | CPK03-R2-IFC | 2021-11-28 | 2
RA-PL-D141 | CPK03-R2-IFC | 2021-11-28 | 2
RA-ST-0019 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2021 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2030 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2038 | CPK03-R2-IFC | 2021-11-28 | 3
RA-ST-2039 | CPK03-R2-IFC | 2021-11-28 | 5
RA-ST-2049 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2050 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2119 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2132 | CPK03-R2-IFC | 2021-11-28 | 3
RA-ST-2135 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2145 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2159 | CPK03-R2-IFC | 2021-11-28 | 3
RA-ST-2162 | CPK03-R2-IFC | 2021-11-28 | 3
RA-ST-2163 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2180 | CPK03-R2-IFC | 2021-11-28 | 8
CC102-44-20 | CPK03-R2-IFC | 2021-11-28 | 1
CC102-45-20 | CPK03-R2-IFC | 2021-11-28 | 1
CC102-46-20 | CPK03-R2-IFC | 2021-11-28 | 1
CC102-47-20 | CPK03-R2-IFC | 2021-11-28 | 1
CC102-48-20 | CPK03-R2-IFC | 2021-11-28 | 1
CC102-49-20 | CPK03-R2-IFC | 2021-11-28 | 1
CC102-50-20 | CPK03-R2-IFC | 2021-11-28 | 1
CC102-51-20 | CPK03-R2-IFC | 2021-11-28 | 1
CC102-52-20 | CPK03-R2-IFC | 2021-11-28 | 1
CC102-53-20 | CPK03-R2-IFC | 2021-11-28 | 1
CC102-54-20 | CPK03-R2-IFC | 2021-11-28 | 1
CC102-55-20 | CPK03-R2-IFC | 2021-11-28 | 1
CC102-56-20 | CPK03-R2-IFC | 2021-11-28 | 1
CC102-57-20 | CPK03-R2-IFC | 2021-11-28 | 1
CC102-58-20 | CPK03-R2-IFC | 2021-11-28 | 1
CC102-59-20 | CPK03-R2-IFC | 2021-11-28 | 1
CC102-60-20 | CPK03-R2-IFC | 2021-11-28 | 1
CC102-1-50 | CPK03-R2-IFC | 2021-11-28 | 1
CC102-2-50 | CPK03-R2-IFC | 2021-11-28 | 1
CC102-3-50 | CPK03-R2-IFC | 2021-11-28 | 1
CC102-4-50 | CPK03-R2-IFC | 2021-11-28 | 1
CC102-5-50 | CPK03-R2-IFC | 2021-11-28 | 1
CC102-6-50 | CPK03-R2-IFC | 2021-11-28 | 1
CC102-7-50 | CPK03-R2-IFC | 2021-11-28 | 1
CC102-8-50 | CPK03-R2-IFC | 2021-11-28 | 1
CC102-9-50 | CPK03-R2-IFC | 2021-11-28 | 1
CC102-10-50 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-FC104-1-20 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-FC104-2-20 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-FC104-3-20 | CPK03-R2-IFC | 2021-11-28 | 1
MS1-FC104-4-20 | CPK03-R2-IFC | 2021-11-28 | 1
MSB1_PLC650_101_00 | CPK03-R2-IFC | 2021-11-28 | 3
MSB1_PLC650_102_00 | CPK03-R2-IFC | 2021-11-28 | 3
MSB1_PLC650_103_00 | CPK03-R2-IFC | 2021-11-28 | 3
MSB1-PLC650-104-00 | CPK03-R2-IFC | 2021-11-28 | 3
MSB1-PLC133-1-00 | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-LCP650-11-90 | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-LCP650-12-90 | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-JB650-14-90 | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-JB650-15-90 | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-JB650-16-90 | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-JB650-17-90 | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-JB650-18-90 | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-JB650-19-90 | CPK03-R2-IFC | 2021-11-28 | 1
MSB1_RIO650_1A_02 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-E0-D001 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-E0-D002 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-E0-D003 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-E0-D004 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-E0-D005 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D001 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D002 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D003 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D004 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D005 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D006 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D007 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D008 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D009 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D010 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D011 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D012 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D013 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D014 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D015 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D016 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D017 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D018 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D019 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D020 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D021 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D022 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D023 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D024 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D025 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D026 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D027 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D028 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D029 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D030 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D031 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D032 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EG-D033 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EG-D034 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EG-D035 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EH-D001 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D002 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D003 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D004 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D005 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D006 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D007 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D008 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D009 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D010 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D011 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D012 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D013 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D014 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D015 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D016 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D017 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D018 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D019 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D020 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D021 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D022 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D023 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D024 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D025 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D026 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D027 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D028 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D029 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D030 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D031 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EH-D032 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EL-D001 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D002 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D003 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D004 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D005 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D006 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D007 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D008 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D009 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D010 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D012 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D013 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D014 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D015 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D016 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D017 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D018 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D019 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D020 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D021 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D022 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D022a | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EL-D023 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D024 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D025 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D026 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D027 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D028 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D029 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D030 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D031 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EL-D032 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EL-D033 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EL-D034 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EL-D035 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EL-D036 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EL-D037 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EL-D038 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EL-D039 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EL-D040 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EL-D041 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EL-D042 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EL-D043 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EP-D001 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D002 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D003 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D004 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D005 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D006 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D007 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D008 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D009 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D010 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D011 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D012 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D013 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D014 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D015 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D016 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D017 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D018 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D019 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D020 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D021 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D022 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D023 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D024 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D025 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D026 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D027 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D028 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D029 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D030 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D031 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D032 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D033 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D034 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D035 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D036 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D037 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D038 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D039 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D040 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D041 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D042 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D043 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D044 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D045 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D046 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D047 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D048 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D049 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D050 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D051 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D052 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D053 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-EP-D054 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EP-D055 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EP-D056 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EP-D057 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EP-D058 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EP-D059 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EP-D060 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EP-D061 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EP-D062 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EP-D063 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EP-D064 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EP-D065 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EP-D066 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-EP-D067 | CPK03-R2-IFC | 2021-11-28 | 1
RAC-ET-D001 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-ET-D002 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-ET-D003 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-ET-D004 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-ET-D005 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-ET-D006 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-ET-D007 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-ET-D008 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-ET-D009 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-ET-D010 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-ET-D011 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-ET-D012 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-ET-D013 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-ET-D014 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-ET-D015 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-ET-D016 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-ET-D017 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-ET-D018 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-ET-D019 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-ET-D020 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-ET-D021 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-ET-D022 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-ET-D023 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-ET-D024 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-ET-D025 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-ET-D026 | CPK03-R2-IFC | 2021-11-28 | 2
RAC-ET-D027 | CPK03-R2-IFC | 2021-11-28 | 1
CDXR1X28A | CPK03-R2-IFC | 2021-11-28 | 2
CMXD1AB53A | CPK03-R2-IFC | 2021-11-28 | 2
CMXD1K52A | CPK03-R2-IFC | 2021-11-28 | 2
CMXD1M53A | CPK03-R2-IFC | 2021-11-28 | 2
CMXD1M55A | CPK03-R2-IFC | 2021-11-28 | 2
CMXD1Q53A | CPK03-R2-IFC | 2021-11-28 | 2
CMXD1Q55A | CPK03-R2-IFC | 2021-11-28 | 2
CMXD1T53A | CPK03-R2-IFC | 2021-11-28 | 2
CMXD1U53A | CPK03-R2-IFC | 2021-11-28 | 2
CMXD2S57B | CPK03-R2-IFC | 2021-11-28 | 2
CMXD2S57C | CPK03-R2-IFC | 2021-11-28 | 2
MXR1N53B | CPK03-R2-IFC | 2021-11-28 | 2
CMXR1N56A | CPK03-R2-IFC | 2021-11-28 | 2
CMXR1Q53B | CPK03-R2-IFC | 2021-11-28 | 3
CMXR1U53B | CPK03-R2-IFC | 2021-11-28 | 3
CMXR2R50A | CPK03-R2-IFC | 2021-11-28 | 2
CMXR2T50A | CPK03-R2-IFC | 2021-11-28 | 2
CMXR2Z50A | CPK03-R2-IFC | 2021-11-28 | 2
CMXR3W57A | CPK03-R2-IFC | 2021-11-28 | 2
CMXR4M57A | CPK03-R2-IFC | 2021-11-28 | 3
CMXR4N54C | CPK03-R2-IFC | 2021-11-28 | 2
CMXR4N57A | CPK03-R2-IFC | 2021-11-28 | 2
CMXR4Z56A | CPK03-R2-IFC | 2021-11-28 | 2
CPS-MXA | CPK03-R2-IFC | 2021-11-28 | 2
CPS-MXB | CPK03-R2-IFC | 2021-11-28 | 2
CPS-MXC | CPK03-R2-IFC | 2021-11-28 | 2
CPS-MXD | CPK03-R2-IFC | 2021-11-28 | 2
DXR1T23G | CPK03-R2-IFC | 2021-11-28 | 2
DXR1Y23A | CPK03-R2-IFC | 2021-11-28 | 2
MXD1AA52A | CPK03-R2-IFC | 2021-11-28 | 2
MXD1AA53A | CPK03-R2-IFC | 2021-11-28 | 2
MXD1AB55A | CPK03-R2-IFC | 2021-11-28 | 2
MXD1AC53A | CPK03-R2-IFC | 2021-11-28 | 2
MXD1AD53A | CPK03-R2-IFC | 2021-11-28 | 2
MXD1L53A | CPK03-R2-IFC | 2021-11-28 | 2
MXD1N52A | CPK03-R2-IFC | 2021-11-28 | 2
MXD1N53A | CPK03-R2-IFC | 2021-11-28 | 2
MXD1P53A | CPK03-R2-IFC | 2021-11-28 | 2
MXD1R53A | CPK03-R2-IFC | 2021-11-28 | 2
MXD1S52A | CPK03-R2-IFC | 2021-11-28 | 2
MXD1S53A | CPK03-R2-IFC | 2021-11-28 | 2
MXD1V53A | CPK03-R2-IFC | 2021-11-28 | 2
MXD1W53A | CPK03-R2-IFC | 2021-11-28 | 2
MXD1X53A | CPK03-R2-IFC | 2021-11-28 | 2
MXD1X55A | CPK03-R2-IFC | 2021-11-28 | 2
MXD1Z53A | CPK03-R2-IFC | 2021-11-28 | 2
MXD2H57B | CPK03-R2-IFC | 2021-11-28 | 2
MXD2H57C | CPK03-R2-IFC | 2021-11-28 | 2
MXD2R50A | CPK03-R2-IFC | 2021-11-28 | 2
MXD2R50B | CPK03-R2-IFC | 2021-11-28 | 2
MXD2S50C | CPK03-R2-IFC | 2021-11-28 | 2
MXD2S50D | CPK03-R2-IFC | 2021-11-28 | 2
MXD2S57A | CPK03-R2-IFC | 2021-11-28 | 2
MXD2T57A | CPK03-R2-IFC | 2021-11-28 | 2
MXD2X50F | CPK03-R2-IFC | 2021-11-28 | 2
MXD4M50C | CPK03-R2-IFC | 2021-11-28 | 2
MXD4V56A | CPK03-R2-IFC | 2021-11-28 | 2
MXR1AA53B | CPK03-R2-IFC | 2021-11-28 | 2
MXR1AC53B | CPK03-R2-IFC | 2021-11-28 | 2
MXR1N57A | CPK03-R2-IFC | 2021-11-28 | 2
MXR1W53B | CPK03-R2-IFC | 2021-11-28 | 2
MXR1V53B | CPK03-R2-IFC | 2021-11-28 | 2
MXR1Z53B | CPK03-R2-IFC | 2021-11-28 | 2
MXR2R50A | CPK03-R2-IFC | 2021-11-28 | 2
MXR2R50F | CPK03-R2-IFC | 2021-11-28 | 1
MXR2T50A | CPK03-R2-IFC | 2021-11-28 | 2
MXR2T57A | CPK03-R2-IFC | 2021-11-28 | 2
MXR2X50A | CPK03-R2-IFC | 2021-11-28 | 2
MXR2X57A | CPK03-R2-IFC | 2021-11-28 | 3
MXR4M54B | CPK03-R2-IFC | 2021-11-28 | 2
MXR4Q54F | CPK03-R2-IFC | 2021-11-28 | 2
MXR4T52A | CPK03-R2-IFC | 2021-11-28 | 2
MXS4H56A | CPK03-R2-IFC | 2021-11-28 | 2
MXS4H56B | CPK03-R2-IFC | 2021-11-28 | 2
MXS4H56C | CPK03-R2-IFC | 2021-11-28 | 2
XD4D2A06A | CPK03-R2-IFC | 2021-11-28 | 2
XD4S2A03A | CPK03-R2-IFC | 2021-11-28 | 1
XMXD2G57A | CPK03-R2-IFC | 2021-11-28 | 2
XMXD2R50A | CPK03-R2-IFC | 2021-11-28 | 2
XMXD2R50B | CPK03-R2-IFC | 2021-11-28 | 2
XMXD2S57B | CPK03-R2-IFC | 2021-11-28 | 2
XMXD2S57C | CPK03-R2-IFC | 2021-11-28 | 2
XMXD2T50B | CPK03-R2-IFC | 2021-11-28 | 2
XMXD2Z50A | CPK03-R2-IFC | 2021-11-28 | 2
XMXD5G52A | CPK03-R2-IFC | 2021-11-28 | 2
XMXD5G52B | CPK03-R2-IFC | 2021-11-28 | 2
XMXD5H52A | CPK03-R2-IFC | 2021-11-28 | 2
XMXD5H52B | CPK03-R2-IFC | 2021-11-28 | 2
XMXD5H52C | CPK03-R2-IFC | 2021-11-28 | 2
XMXD5H52D | CPK03-R2-IFC | 2021-11-28 | 2
XMXS4J56B | CPK03-R2-IFC | 2021-11-28 | 2
XMXS4J56C | CPK03-R2-IFC | 2021-11-28 | 2
PSV202-1-03 | CPK03-R2-IFC | 2021-11-28 | 1
PSV202-2-03 | CPK03-R2-IFC | 2021-11-28 | 1
PSV202-2-30A | CPK03-R2-IFC | 2021-11-28 | 1
PSV202-3-30A | CPK03-R2-IFC | 2021-11-28 | 1
PSV221-1-61A | CPK03-R2-IFC | 2021-11-28 | 1
PSV245-1-41A | CPK03-R2-IFC | 2021-11-28 | 1
PSV245-2-41A | CPK03-R2-IFC | 2021-11-28 | 1
PSV245-1-41 | CPK03-R2-IFC | 2021-11-28 | 1
PSV245-2-41 | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-LV133-2-08A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-LV133-3-08A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PCV221-1-61A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PCV237-0-36C | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PCV237-0-36D | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PCZ138-0-04A | CPK03-R2-IFC | 2021-11-28 | 2
MSB1-PCZ138-0-04B | CPK03-R2-IFC | 2021-11-28 | 2
MSB1-PCZ138-0-04C | CPK03-R2-IFC | 2021-11-28 | 2
MSB1-PCZ138-0-04D | CPK03-R2-IFC | 2021-11-28 | 2
MSB1-PCZ138-0-04E | CPK03-R2-IFC | 2021-11-28 | 2
MSB1-PCZ138-0-04F | CPK03-R2-IFC | 2021-11-28 | 2
MSB1-PCZ147-1-04G | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PCZ147-2-04G | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PCZ147-3-04G | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PCZ147-4-04G | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV102-1-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV102-2-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV102-3-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV102-4-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV102-5-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV102-6-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV102-7-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV102-8-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV102-9-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV102-10-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV102-11-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV102-12-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV102-13-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV102-14-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV102-15-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV102-16-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV102-17-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV102-19-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV102-20-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV102-21-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV102-22-22A | CPK03-R2-IFC | 2021-11-28 | 2
MSB1-TCV102-27-22A | CPK03-R2-IFC | 2021-11-28 | 2
MSB1-TCV102-28-22A | CPK03-R2-IFC | 2021-11-28 | 2
MSB1-TCV102-29-22A | CPK03-R2-IFC | 2021-11-28 | 2
MSB1-TCV102-30-22A | CPK03-R2-IFC | 2021-11-28 | 2
MSB1-TCV104-1-20A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV104-2-20A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV104-3-20A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV104-4-20A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV113-10-05A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV113-10-05B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV147-1-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV147-2-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV147-3-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV147-4-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV245-1-41A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TCV245-2-41A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-XV202-0-25A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-XV269-0-05A | CPK03-R2-IFC | 2021-11-28 | 1
RAPB1-FCV241-0-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-ACV133-1-09A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-ACV133-2-09A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-ACV133-3-09A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AV133-1-09A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AV133-2-09A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AV133-3-09A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FCV245-0-40A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FV133-1-07A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FV133-2-07A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FV133-3-07A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FV269-0-05A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FV269-0-05B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FV269-0-05C | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FV269-0-05D | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-LV133-1-08A | CPK03-R2-IFC | 2021-11-28 | 1
13XX_SOO_01_MS1 | CPK03-R2-IFC | 2021-11-28 | 1
0214_SOO_01_MSB | CPK03-R2-IFC | 2021-11-28 | 1
1255_SOO_07_MSB | CPK03-R2-IFC | 2021-11-28 | 1
1255_SOO_08_MSB | CPK03-R2-IFC | 2021-11-28 | 1
1256_SOO_05_MSB | CPK03-R2-IFC | 2021-11-28 | 1
1257_SOO_04_MSB | CPK03-R2-IFC | 2021-11-28 | 1
1257_SOO_06_MSB | CPK03-R2-IFC | 2021-11-28 | 2
1257_SOO_07_MSB | CPK03-R2-IFC | 2021-11-28 | 1
1261_SOO_04_MSB | CPK03-R2-IFC | 2021-11-28 | 2
1271_SOO_01_D1X | CPK03-R2-IFC | 2021-11-28 | 1
1271_SOO_06_MSB | CPK03-R2-IFC | 2021-11-28 | 1
1312_SOO_01_MS1 | CPK03-R2-IFC | 2021-11-28 | 1
1312_SPT_01 | CPK03-R2-IFC | 2021-11-28 | 1
1322_SOO_01_MS1 | CPK03-R2-IFC | 2021-11-28 | 1
1327_SOO_01_MS1 | CPK03-R2-IFC | 2021-11-28 | 1
1328_SOO_01_MS1 | CPK03-R2-IFC | 2021-11-28 | 1
1335_SOO_01_MSB | CPK03-R2-IFC | 2021-11-28 | 1
1443_SOO_01_MS1 | CPK03-R2-IFC | 2021-11-28 | 1
1443_SPT_01 | CPK03-R2-IFC | 2021-11-28 | 1
1448_SOO_01_MS1 | CPK03-R2-IFC | 2021-11-28 | 1
1448_SPT_01 | CPK03-R2-IFC | 2021-11-28 | 1
1510_SOO_01_MS1 | CPK03-R2-IFC | 2021-11-28 | 1
1510_SOO_05_MS1 | CPK03-R2-IFC | 2021-11-28 | 1
1510_SOO_07_MS1 | CPK03-R2-IFC | 2021-11-28 | 1
1510_SOO_09_MS1 | CPK03-R2-IFC | 2021-11-28 | 1
1510_SOO_10_MS1 | CPK03-R2-IFC | 2021-11-28 | 1
1510_SPT_01_MS1 | CPK03-R2-IFC | 2021-11-28 | 1
1510_SPT_05_MS1 | CPK03-R2-IFC | 2021-11-28 | 1
1510_SPT_07_MS1 | CPK03-R2-IFC | 2021-11-28 | 1
1510_SPT_09_MS1 | CPK03-R2-IFC | 2021-11-28 | 1
1510_SPT_10_MS1 | CPK03-R2-IFC | 2021-11-28 | 1
1814_SOO_01_MS1 | CPK03-R2-IFC | 2021-11-28 | 1
1834_SOO_01_MS1 | CPK03-R2-IFC | 2021-11-28 | 1
1839_SOO_02_MS1 | CPK03-R2-IFC | 2021-11-28 | 1
40_90_20_00_DAT | CPK03-R2-IFC | 2021-11-28 | 2
MSB1-AE133-1-09B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AE133-2-07A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AE133-2-09A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AE133-2-09B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AE133-3-07A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AE133-3-09A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AE133-3-09B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AIT133-1-07A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AIT133-1-09A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AIT133-1-09B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AIT133-2-07A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AIT133-2-09A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AIT133-2-09B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AIT133-3-07A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AIT133-3-09A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AIT133-3-09B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AIT202-0-25A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AIT202-0-25B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AY133-1-07A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AY133-1-09A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AY133-1-09B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AY133-2-07A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AY133-2-09A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AY133-2-09B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AY133-3-07A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AY133-3-09A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AY133-3-09B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AY202-0-25A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AY202-0-25B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AY202-0-26A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AY202-0-26B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FE132-0-02A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FE132-0-02B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FE132-0-02C | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FE133-0-02A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FE133-0-02B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FE133-0-02C | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FE138-0-02A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FE138-0-02B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FE138-0-02C | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FE147-0-02A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FIT113-10-06A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FIT132-0-02A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FIT132-0-02B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FIT132-0-02C | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FIT133-0-02A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FIT133-0-02B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FIT133-0-02C | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FIT133-0-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FIT133-1-05A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FIT133-1-19A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FIT133-2-05A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FIT133-2-19A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FIT133-3-05A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FIT133-3-19A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FIT138-0-02A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FIT138-0-02B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FIT138-0-02C | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FIT147-0-02A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FIT202-1-01A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FIT202-1-21A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FIT245-0-40A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FIT245-0-40B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FIT245-0-48A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FIT245-3-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FIT245-4-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FIT299-0-08A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FY113-10-06A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FY133-0-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FY133-1-05A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FY133-2-05A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FY133-3-05A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FY202-1-21A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FY245-0-48A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FY245-3-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-FY245-4-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-LIT133-0-07A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-LIT133-0-07B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-LIT133-1-08A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-LIT133-2-08A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-LIT133-3-08A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-LIT299-1-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-LS133-1-09A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-LS133-2-09A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-LS133-3-09A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-LSH269-1-01A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-LSH269-2-01A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-LSH270-1-01A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-LSH270-2-01A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-LSHH299-1-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-LSHH299-2-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-NET147-1-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-NET147-2-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-NET147-3-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-NET147-4-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT113-10-04A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT113-10-04B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT131-9-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT131-9-00B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT131-9-00C | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT131-9-00D | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-00J | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-00K | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-00L | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-00M | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-00N | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-00P | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-00Q | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-00R | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-00S | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-00T | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-00U | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-00V | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-90FA | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-90FB | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-90FC | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-90FD | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-90FE | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-90FF | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-90FG | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-90FH | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-90FJ | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-90FK | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-90FL | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-90FM | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-90FN | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-90FP | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-90FQ | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-90FR | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-90FS | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-90FT | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT132-0-90FU | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-00B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-00C | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-00D | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-00J | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-00K | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-00L | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-00M | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-00P | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-00Q | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-00V | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-00W | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-90FA | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-90FB | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-90FC | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-90FD | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-90FE | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-90FF | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-90FG | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-90FH | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-90FJ | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-90FK | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-90FL | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-90FM | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-90FN | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-90FP | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-90FQ | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-90FR | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-90FS | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-90FT | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-0-90FU | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-1-06A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-2-06A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT133-3-06A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-00B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-00C | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-00D | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-00G | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-00J | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-00K | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-00L | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-00M | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-00N | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-00P | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-00Q | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-90FA | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-90FB | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-90FC | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-90FD | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-90FE | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-90FF | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-90FG | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-90FH | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-90FJ | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-90FK | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-90FL | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-90FM | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-90FN | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-90FP | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-90FQ | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-90FR | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-90FS | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-90FT | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT138-0-90FU | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT147-0-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT147-0-00B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT147-0-00C | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT147-0-00D | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT147-0-90FA | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT147-0-90FB | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT147-0-90FC | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT147-0-90FD | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT147-0-90FE | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT147-0-90FF | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT147-0-90FG | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT147-0-90FH | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT147-0-90FJ | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT202-1-15A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT202-1-15B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT202-1-16C | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT202-1-16D | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT202-1-16E | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT202-1-16F | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT248-0-19A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDIT248-0-19B | CPK03-R2-IFC | 2021-11-28 | 1
MSb1-PDS269-1-05A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PDS270-1-05A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PIT133-0-21A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PIT133-0-21B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PIT202-1-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PIT202-1-00B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PIT202-1-20A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PIT202-1-31A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PIT212-0-21A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PIT217-0-92A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PIT218-0-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PIT218-0-00B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PIT218-0-01A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PIT218-0-01B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PIT221-0-21A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PIT221-0-61A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PIT221-0-61B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PIT221-0-61C | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PIT221-0-61D | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PIT237-0-36C | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PIT237-0-36D | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PIT245-3-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PIT245-3-00B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PIT245-4-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PIT245-4-00B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PIT249-1-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PIT249-1-00B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PIT269-1-05A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PIT299-0-07A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PIT530-0-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PSL299-1-05A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-PSL299-2-05A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TE113-10-05A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TE113-10-05B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TE113-10-07A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TE133-0-07A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TE133-1-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TE133-2-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TE133-3-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TE202-1-20A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TE202-1-30A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TE202-1-30B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TE202-1-31A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TE218-0-08A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-0-01A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-0-01B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-0-01C | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-0-01D | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-0-01E | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-0-01F | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-0-01G | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-0-01H | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-1-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-1-52A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-2-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-2-52A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-3-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-3-52A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-4-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-4-52A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-5-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-5-52A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-6-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-6-52A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-7-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-7-52A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-8-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-8-52A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-9-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-9-52A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-10-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-10-52A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-11-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-12-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-14-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-15-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-16-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-17-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-18-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-19-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-20-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-21-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-22-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-23-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-24-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-25-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-26-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-27-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-28-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-29-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-30-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET102-31-22A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET103-1-02 | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET103-1-03A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET103-1-03B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET103-1-03C | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET103-1-03D | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET104-1-20A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET104-2-20A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET104-3-20A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET104-4-20A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET113-10-05A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET113-10-05B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET113-10-07A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET202-1-30A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET202-1-30B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TET218-0-08A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TIT133-0-07A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TIT133-1-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TIT133-2-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TIT133-3-00A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TIT202-1-20A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TIT202-1-31A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TIT245-0-41A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TIT245-0-41B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-TSL103-1-00A | CPK03-R2-IFC | 2021-11-28 | 1
RAPB1-FIT241-0-00A | CPK03-R2-IFC | 2021-11-28 | 1
RAPB1-FIT241-0-00B | CPK03-R2-IFC | 2021-11-28 | 1
RAPB1-FY241-0-00A | CPK03-R2-IFC | 2021-11-28 | 1
RAPB1-FY241-0-00B | CPK03-R2-IFC | 2021-11-28 | 1
D1X1A-FIT245-1-97A | CPK03-R2-IFC | 2021-11-28 | 1
D1X1A-FIT245-1-98A | CPK03-R2-IFC | 2021-11-28 | 1
D1X1A-FIT245-1-98B | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AE133-1-07A | CPK03-R2-IFC | 2021-11-28 | 1
MSB1-AE133-1-09A | CPK03-R2-IFC | 2021-11-28 | 1
PMP272-16-40 | CPK03-R2-IFC | 2021-11-28 | 1
PMP272-17-40 | CPK03-R2-IFC | 2021-11-28 | 1
PMP272-18-40 | CPK03-R2-IFC | 2021-11-28 | 1
FFU102-##XX-##XX-X | CPK03-R2-IFC | 2021-11-28 | 1
HXRA-M01 | CPK03-R2-IFC | 2021-11-28 | 1
HXRA-M02 | CPK03-R2-IFC | 2021-11-28 | 1
HXRA-M03 | CPK03-R2-IFC | 2021-11-28 | 1
HXRA147-1-00 | CPK03-R2-IFC | 2021-11-28 | 1
HXRA147-2-00 | CPK03-R2-IFC | 2021-11-28 | 1
HXRA147-3-00 | CPK03-R2-IFC | 2021-11-28 | 1
HXRA147-4-00 | CPK03-R2-IFC | 2021-11-28 | 1
1347_MVT_01_SWS_D1X_MSB | CPK03-R2-IFC | 2021-11-28 | 1
1350_MVT_01_CHCO2DI_MSB | CPK03-R2-IFC | 2021-11-28 | 1
1350_MVT_01_UPW_D1X_MSB | CPK03-R2-IFC | 2021-11-28 | 1
1443_MVT_01_GSW_MSB | CPK03-R2-IFC | 2021-11-28 | 1
1448_MVT_01_CSW_MSB | CPK03-R2-IFC | 2021-11-28 | 1
1494_MVT_01_SWWT_MSB | CPK03-R2-IFC | 2021-11-28 | 1
MXR2X57B | CPK03-R2-IFC | 2021-11-28 | 2
RA-ST-0001 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-0002 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-0003 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-0004 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-0005 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-0006 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-0007 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-0008 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-0009 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-0010 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-0011 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-0012 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-0013 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-0014 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-0015 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-0016 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-0017 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-0018 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-0020 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-0021 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-0022 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-0500 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-0501 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-0502 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-0503 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-0504 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-0505 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-0506 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-1000 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-1001 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-1002 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-1003 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-1004 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-1008 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-1009 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-1011 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2000 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-2004 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2005 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2006 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-2007 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-2008 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-2009 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2010 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2011 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2012 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-2013 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-2014 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-2015 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-2016 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-2017 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2018 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2019 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2020 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2022 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2023 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2024 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-2025 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2026 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2027 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2028 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-2029 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2031 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2032 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-2033 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2034 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2035 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2036 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2037 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2040 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2041 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2042 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-2043 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2044 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-2045 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2046 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2048 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2051 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2052 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2053 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2054 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2055 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2056 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2057 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2058 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2059 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2060 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2061 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2062 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2063 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2064 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2065 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2066 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2067 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2068 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2069 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2070 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2071 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2072 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2073 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2074 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2075 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2076 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2077 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2078 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2079 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2080 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2081 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2082 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2083 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2084 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2085 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2086 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2087 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2088 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2089 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2090 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2091 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2092 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2093 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2094 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2095 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2097 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2100 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2102 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2105 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2106 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2107 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2108 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2109 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2110 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2111 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2112 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2113 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2114 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2118 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2120 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2126 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2127 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2128 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2129 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2131 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2136 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2137 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2138 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2139 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2140 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2141 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2142 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2143 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2144 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2147 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2148 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2149 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2150 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2151 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2157 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2158 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2160 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2161 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2164 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2165 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2166 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2168 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2169 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2170 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2171 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2172 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2173 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2174 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2175 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2177 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2178 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2179 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2182 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2184 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-2185 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-3000 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-3001 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-3002 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-3008 | CPK03-R2-IFC | 2021-11-28 | 8
RA-ST-4000 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-4001 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-4002 | CPK03-R2-IFC | 2021-11-28 | 9
RA-ST-4003 | CPK03-R2-IFC | 2021-11-28 | 9
00_01_00_00 | CPK03-R3-IFC | 2021-12-24 | 7
RA-ST-0001 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-0002 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-0003 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-0004 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-0005 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-0006 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-0007 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-0008 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-0009 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-0010 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-0011 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-0012 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-0013 | CPK03-R3-IFC | 2021-12-24 | 9
CB4-S0-20A-B0000 | CPK03-R3-IFC | 2021-12-24 | 1
MS1-S0-1SA-C02C0 | CPK03-R3-IFC | 2021-12-24 | 1
MS1-S0-1SF-4000 | CPK03-R3-IFC | 2021-12-24 | 4
MS1-S0-1SF-B01B0 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-S0-4DA-B0000 | CPK03-R3-IFC | 2021-12-24 | 1
MS1-S0-5RC-B0400 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-S0-0010 | CPK03-R3-IFC | 2021-12-24 | 8
MS1-S0-6210 | CPK03-R3-IFC | 2021-12-24 | 6
MS1-SS-1SF-B0000 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-SS-1SF-C0000 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-SS-1SF-C0000-D | CPK03-R3-IFC | 2021-12-24 | 1
MS1-SS-1SF-D0000 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-SS-2FD-C0100 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-SS-2FD-D0200 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-SS-2FK-B0000 | CPK03-R3-IFC | 2021-12-24 | 4
MS1-SS-2FK-C0000 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-SS-2FK-D0000 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-SS-2FL-B0000 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-SS-2FL-C0000 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-SS-2FL-D0000 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-SS-2FM-B0000 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-SS-2FM-B0300 | CPK03-R3-IFC | 2021-12-24 | 4
MS1-SS-2FM-C0000 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-SS-2FM-D0000 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-SS-5RC-B0000 | CPK03-R3-IFC | 2021-12-24 | 6
MS1-A0-0722 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-A0-0723 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-A0-0724 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-A0-6225 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-AC-2FA-A0D00 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-AC-2FA-B0000 | CPK03-R3-IFC | 2021-12-24 | 4
MS1-AC-2FA-C0000 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-AC-2FA-D0000 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-AC-2FH-4001 | CPK03-R3-IFC | 2021-12-24 | 4
MS1-AC-2FH-B0000 | CPK03-R3-IFC | 2021-12-24 | 5
MS1-AC-2FH-B0D00-S | CPK03-R3-IFC | 2021-12-24 | 4
MS1-AC-2FH-B0000-S | CPK03-R3-IFC | 2021-12-24 | 5
MS1-AC-2FH-C0000 | CPK03-R3-IFC | 2021-12-24 | 4
MS1-AC-2FH-C0000-S | CPK03-R3-IFC | 2021-12-24 | 4
MS1-AC-2FH-D0000 | CPK03-R3-IFC | 2021-12-24 | 4
MS1-AC-2FH-D0000-S | CPK03-R3-IFC | 2021-12-24 | 4
MS1-AI-0106 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-AI-0107 | CPK03-R3-IFC | 2021-12-24 | 4
MS1-AR-2FB-A0D00 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-AR-2FB-B0000 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-AR-2FB-C0000 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-AR-2FB-D0000 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-AW-1SA-A0D00 | CPK03-R3-IFC | 2021-12-24 | 3 | Y
MS1-AW-1SA-B0000 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-AW-1SA-C0000 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-AW-1SA-C0000-D | CPK03-R3-IFC | 2021-12-24 | 3
MS1-AW-1SA-D0000 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-AW-1SA-D0000-D | CPK03-R3-IFC | 2021-12-24 | 1
MS1-AW-2FA-A0D00 | CPK03-R3-IFC | 2021-12-24 | 4
MS1-AW-2FA-B0000 | CPK03-R3-IFC | 2021-12-24 | 4
MS1-AW-2FA-C0000 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-AW-2FA-D0000 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-AW-2FM-A0D00 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-AW-2FM-B0000 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-AW-2FM-C0000 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-AW-2FM-D0000 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-AW-2UA-A0D00 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-AW-2UA-B0000 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-AW-2UA-C0000 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-AW-2UA-D0000 | CPK03-R3-IFC | 2021-12-24 | 1
MS1-AZ-2FA-A0D00 | CPK03-R3-IFC | 2021-12-24 | 3
RAC-A0-0002 | CPK03-R3-IFC | 2021-12-24 | 2
CB4-ES-1252C | CPK03-R3-IFC | 2021-12-24 | 2
CB4-ES-1400 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-EE-2FA-C0000 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-EE-2FA-D0000 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-ES-1250B | CPK03-R3-IFC | 2021-12-24 | 2
MS1-ES-1251C | CPK03-R3-IFC | 2021-12-24 | 3
MS1-ES-1300 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-ES-1306 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-ES-1308 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-ES-1311C | CPK03-R3-IFC | 2021-12-24 | 2
RAC-GN-0001 | CPK03-R3-IFC | 2021-12-24 | 5
RAC-GN-0002 | CPK03-R3-IFC | 2021-12-24 | 5
RAC-GN-0003 | CPK03-R3-IFC | 2021-12-24 | 5
RAC-GN-0004 | CPK03-R3-IFC | 2021-12-24 | 5
RAC-GN-0005 | CPK03-R3-IFC | 2021-12-24 | 5
RAC-GN-0006 | CPK03-R3-IFC | 2021-12-24 | 5
RAC-GN-0007 | CPK03-R3-IFC | 2021-12-24 | 5
RAC-GN-0008 | CPK03-R3-IFC | 2021-12-24 | 5
RAC-GN-0009 | CPK03-R3-IFC | 2021-12-24 | 5
RAC-GN-0010 | CPK03-R3-IFC | 2021-12-24 | 5
D1X-IE-1YA-F0000 | CPK03-R3-IFC | 2021-12-24 | 2
D1X-IE-1YA-J0000 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-IE-1SA-B0000 | CPK03-R3-IFC | 2021-12-24 | 4
MS1-IE-1SA-C0000 | CPK03-R3-IFC | 2021-12-24 | 5
MS1-IE-1SA-D0000 | CPK03-R3-IFC | 2021-12-24 | 5
MS1-IE-2FA-B0000 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-IE-2FA-C0000 | CPK03-R3-IFC | 2021-12-24 | 4
MS1-IE-2FA-D0000 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-104-MH-A04 | CPK03-R3-IFC | 2021-12-24 | 1
MS1-131-MX-A01 | CPK03-R3-IFC | 2021-12-24 | 1
MS1-ME-1SA-A0D00 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-ME-2FA-A0D00 | CPK03-R3-IFC | 2021-12-24 | 2
D1X-262-D0-Z06 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-102-D0-A05 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-104-D0-A04 | CPK03-R3-IFC | 2021-12-24 | 1
MS1-104-D0-A06 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-104-D0-Z01 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-106-D0-A01 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-111-D0-Z04 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-113-D0-Z04 | CPK03-R3-IFC | 2021-12-24 | 1
MS1-113-D0-Z05 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-113-D0-Z06 | CPK03-R3-IFC | 2021-12-24 | 1
MS1-133-D0-A03 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-133-D0-Z01 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-133-D0-Z02 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-147-D0-A01 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-147-D0-Z01 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-147-D0-Z02 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-210-D0-Z01 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-211-D0-Z01 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-212-D0-Z01 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-213-D0-Z02 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-221-D0-A01 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-221-D0-Z03 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-237-D0-Z01 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-261-D0-Z01 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-261-D0-Z01-D | CPK03-R3-IFC | 2021-12-24 | 3
MS1-266-D0-Z01 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-266-D0-Z01-D | CPK03-R3-IFC | 2021-12-24 | 2
MS1-400-D0-A02 | CPK03-R3-IFC | 2021-12-24 | 3
D1X-249-PU-Z01 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-245-PU-Z10 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-249-PH-Z10 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-TC-1SA-C0000 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-TC-1SA-D0000 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-TC-2FA-C0000 | CPK03-R3-IFC | 2021-12-24 | 3
MS1-TC-2FA-D0000 | CPK03-R3-IFC | 2021-12-24 | 2
MS1-TC-4DA-B0000 | CPK03-R3-IFC | 2021-12-24 | 1
MS1-TC-5RA-B0000 | CPK03-R3-IFC | 2021-12-24 | 2
RAC-T0-0001 | CPK03-R3-IFC | 2021-12-24 | 4
RAC-T0-9001 | CPK03-R3-IFC | 2021-12-24 | 4
RAC-T0-9002 | CPK03-R3-IFC | 2021-12-24 | 3
RAC-T0-9004 | CPK03-R3-IFC | 2021-12-24 | 3
RAC-T0-9005 | CPK03-R3-IFC | 2021-12-24 | 2
RA-ME-D005 | CPK03-R3-IFC | 2021-12-24 | 2
RA-ME-D007 | CPK03-R3-IFC | 2021-12-24 | 2
RA-ME-D008 | CPK03-R3-IFC | 2021-12-24 | 2
RA-ME-D009 | CPK03-R3-IFC | 2021-12-24 | 2
RA-ME-D010 | CPK03-R3-IFC | 2021-12-24 | 2
RA-ME-D011 | CPK03-R3-IFC | 2021-12-24 | 2
RA-ME-D015 | CPK03-R3-IFC | 2021-12-24 | 2
RA-ME-D018 | CPK03-R3-IFC | 2021-12-24 | 2
RA-ME-D019 | CPK03-R3-IFC | 2021-12-24 | 2
RA-ME-D020 | CPK03-R3-IFC | 2021-12-24 | 1
RA-MH-D002 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D003 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D004 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D005 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D007 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D008 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D009 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D010 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MH-D011 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MH-D013 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MH-D015 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MH-D016 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MH-D017 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MH-D018 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MH-D019 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D020 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MH-D021 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D022 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D023 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D024 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D025 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D028 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MH-D033 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D034 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D035 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MH-D036 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MH-D037 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MH-D038 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MH-D039 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D040 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D041 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D045 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D046 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D047 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D048 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D049 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D050 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D051 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MH-D052 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MH-D053 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MH-D054 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MH-D057 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MH-D059 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D060 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D061 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D062 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MH-D063 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D064 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D065 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D067 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D070 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D073 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D074 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D075 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D076 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D077 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D078 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D080 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D082 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D083 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D084 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D085 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D086 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MH-D091 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D093 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D094 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D096 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D097 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MH-D107 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D108 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D110 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D112 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D113 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D114 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D115 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D116 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D117 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D118 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D119 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MH-D120 | CPK03-R3-IFC | 2021-12-24 | 1
RA-MP-D001 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MP-D002 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MP-D003 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MP-D004 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MP-D005 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MP-D010 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MP-D011 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MP-D013 | CPK03-R3-IFC | 2021-12-24 | 3
RA-MP-D016 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MP-D017 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MP-D018 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MP-D021 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MP-D023 | CPK03-R3-IFC | 2021-12-24 | 2
RA-MP-D046 | CPK03-R3-IFC | 2021-12-24 | 3
RA-AR-D0200 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D0300 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D0301 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D0305 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D0306 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D0307 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D0309 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D0311 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D0312 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D0320 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D0321 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D0600 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D0601 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D0603 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1600 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1601 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1602 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1603 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1604 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1606 | CPK03-R3-IFC | 2021-12-24 | 3
RA-AR-D1607 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1609 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1610 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1611 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1612 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1614 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1617 | CPK03-R3-IFC | 2021-12-24 | 3
RA-AR-D1618 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1700 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1703 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1704 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1705 | CPK03-R3-IFC | 2021-12-24 | 3
RA-AR-D1706 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1707 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1708 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1709 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1710 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1711 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1712 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1713 | CPK03-R3-IFC | 2021-12-24 | 3
RA-AR-D1714 | CPK03-R3-IFC | 2021-12-24 | 3
RA-AR-D1715 | CPK03-R3-IFC | 2021-12-24 | 3
RA-AR-D1716 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1717 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1718 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1719 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1720 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1721 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1722 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1723 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1724 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1726 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1727 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1729 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1730 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1731 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1732 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1733 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1734 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1735 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1736 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1737 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1738 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1739 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1740 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1741 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1742 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1743 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1744 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1800 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1801 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1802 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1803 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1804 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1806 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1807 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1808 | CPK03-R3-IFC | 2021-12-24 | 3
RA-AR-D1809 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1810 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1903 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1906 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1908 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1910 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1911 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1912 | CPK03-R3-IFC | 2021-12-24 | 3
RA-AR-D1913 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1914 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1915 | CPK03-R3-IFC | 2021-12-24 | 3
RA-AR-D1916 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D1917 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1918 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1919 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1920 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D1921 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D2300 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2301 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2302 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2303 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2304 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2305 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2306 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2307 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2308 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2309 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2400 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2403 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2402 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2405 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2406 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2407 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2408 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2409 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2410 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2411 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2415 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2416 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2417 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D2418 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D2419 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D2500 | CPK03-R3-IFC | 2021-12-24 | 3
RA-AR-D2501 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2502 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2503 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2504 | CPK03-R3-IFC | 2021-12-24 | 3
RA-AR-D2505 | CPK03-R3-IFC | 2021-12-24 | 1
RA-AR-D2506 | CPK03-R3-IFC | 2021-12-24 | 3
RA-AR-D2900 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2901 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2902 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2903 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2904 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2905 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2906 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2907 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2908 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2909 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2910 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2911 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2912 | CPK03-R3-IFC | 2021-12-24 | 2
RA-AR-D2913 | CPK03-R3-IFC | 2021-12-24 | 2
RA-ST-0014 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-0019 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-0015 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-1005 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-1006 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-1010 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-1012 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-1013 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-1014 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-1015 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-2001 | CPK03-R3-IFC | 2021-12-24 | 7
RA-ST-2002 | CPK03-R3-IFC | 2021-12-24 | 7
RA-ST-2003 | CPK03-R3-IFC | 2021-12-24 | 7
RA-ST-0016 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-0017 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2021 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2030 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-0018 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-203 | CPK03-R3-IFC | 2021-12-24 | 2
RA-ST-2039 | CPK03-R3-IFC | 2021-12-24 | 5
RA-ST-0020 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2047 | CPK03-R3-IFC | 2021-12-24 | 7
RA-ST-2049 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2050 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-0021 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-0022 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-0500 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-0501 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-2096 | CPK03-R3-IFC | 2021-12-24 | 7
RA-ST-2098 | CPK03-R3-IFC | 2021-12-24 | 7
RA-ST-2099 | CPK03-R3-IFC | 2021-12-24 | 7
RA-ST-2101 | CPK03-R3-IFC | 2021-12-24 | 7
RA-ST-2103 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-2104 | CPK03-R3-IFC | 2021-12-24 | 7
RA-ST-2115 | CPK03-R3-IFC | 2021-12-24 | 7
RA-ST-2116 | CPK03-R3-IFC | 2021-12-24 | 7
RA-ST-2117 | CPK03-R3-IFC | 2021-12-24 | 7
RA-ST-0502 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-2119 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2121 | CPK03-R3-IFC | 2021-12-24 | 7
RA-ST-2122 | CPK03-R3-IFC | 2021-12-24 | 7
RA-ST-2130 | CPK03-R3-IFC | 2021-12-24 | 7
RA-ST-2132 | CPK03-R3-IFC | 2021-12-24 | 3
RA-ST-2135 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-0503 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-2145 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2159 | CPK03-R3-IFC | 2021-12-24 | 3
RA-ST-2162 | CPK03-R3-IFC | 2021-12-24 | 3
RA-ST-2163 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2167 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-0504 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-2176 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-2180 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2181 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-2183 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-2192 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-2197 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-2199 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-2200 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-2201 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-2204 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-2205 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-2206 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-2207 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-2208 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-2209 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-2210 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-2218 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-2219 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-2220 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-2222 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-2223 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-2230 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-2239 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-2242 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-2243 | CPK03-R3-IFC | 2021-12-24 | 6
RA-ST-2244 | CPK03-R3-IFC | 2021-12-24 | 4
RA-ST-0505 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-3009 | CPK03-R3-IFC | 2021-12-24 | 5
RA-PL-D001 | CPK03-R3-IFC | 2021-12-24 | 3
RA-PL-D002 | CPK03-R3-IFC | 2021-12-24 | 3
RA-PL-D003 | CPK03-R3-IFC | 2021-12-24 | 3
RA-PL-D004 | CPK03-R3-IFC | 2021-12-24 | 3
RA-PL-D005 | CPK03-R3-IFC | 2021-12-24 | 3
RA-PL-D006 | CPK03-R3-IFC | 2021-12-24 | 3
RA-PL-D007 | CPK03-R3-IFC | 2021-12-24 | 3
RA-PL-D008 | CPK03-R3-IFC | 2021-12-24 | 2
RA-PL-D101 | CPK03-R3-IFC | 2021-12-24 | 2
RA-PL-D102 | CPK03-R3-IFC | 2021-12-24 | 2
RA-PL-D103 | CPK03-R3-IFC | 2021-12-24 | 2
RA-PL-D104 | CPK03-R3-IFC | 2021-12-24 | 2
RA-PL-D106 | CPK03-R3-IFC | 2021-12-24 | 2
RA-PL-D108 | CPK03-R3-IFC | 2021-12-24 | 2
RA-PL-D112 | CPK03-R3-IFC | 2021-12-24 | 2
RA-PL-D114 | CPK03-R3-IFC | 2021-12-24 | 2
RA-PL-D115 | CPK03-R3-IFC | 2021-12-24 | 2
RA-PL-D116 | CPK03-R3-IFC | 2021-12-24 | 3
RA-PL-D117 | CPK03-R3-IFC | 2021-12-24 | 3
RA-PL-D118 | CPK03-R3-IFC | 2021-12-24 | 3
RA-PL-D119 | CPK03-R3-IFC | 2021-12-24 | 3
RA-PL-D120 | CPK03-R3-IFC | 2021-12-24 | 3
RA-PL-D121 | CPK03-R3-IFC | 2021-12-24 | 3
RA-PL-D122 | CPK03-R3-IFC | 2021-12-24 | 3
RA-PL-D123 | CPK03-R3-IFC | 2021-12-24 | 3
RA-PL-D126 | CPK03-R3-IFC | 2021-12-24 | 2
RA-PL-D127 | CPK03-R3-IFC | 2021-12-24 | 3
RA-PL-D128 | CPK03-R3-IFC | 2021-12-24 | 3
RA-PL-D129 | CPK03-R3-IFC | 2021-12-24 | 2
RA-PL-D131 | CPK03-R3-IFC | 2021-12-24 | 2
RA-PL-D132 | CPK03-R3-IFC | 2021-12-24 | 3
RA-PL-D133 | CPK03-R3-IFC | 2021-12-24 | 2
RA-PL-D134 | CPK03-R3-IFC | 2021-12-24 | 2
RA-PL-D136 | CPK03-R3-IFC | 2021-12-24 | 3
RA-PL-D137 | CPK03-R3-IFC | 2021-12-24 | 3
RA-PL-D138 | CPK03-R3-IFC | 2021-12-24 | 3
RA-PL-D139 | CPK03-R3-IFC | 2021-12-24 | 3
RA-PL-D140 | CPK03-R3-IFC | 2021-12-24 | 2
RA-PL-D141 | CPK03-R3-IFC | 2021-12-24 | 2
00_00_00_01 | CPK03-R3-IFC | 2021-12-24 | 6
45_43_13_67 | CPK03-R3-IFC | 2021-12-24 | 1
23-70-10-00-M01 | CPK03-R3-IFC | 2021-12-24 | 1
23-70-10-00-M02 | CPK03-R3-IFC | 2021-12-24 | 1
23-70-10-00-M03 | CPK03-R3-IFC | 2021-12-24 | 1
23-70-10-00-M04 | CPK03-R3-IFC | 2021-12-24 | 1
23_70_10_00 | CPK03-R3-IFC | 2021-12-24 | 1
23_82_16_61_dat | CPK03-R3-IFC | 2021-12-24 | 2
25_14_01_00_DAT_01 | CPK03-R3-IFC | 2021-12-24 | 1
25_14_01_00_DAT_03 | CPK03-R3-IFC | 2021-12-24 | 5
MSB1-RI0650-104-02 | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-RIO650-101-04 | CPK03-R3-IFC | 2021-12-24 | 3
MSB1-RIO650-102-04 | CPK03-R3-IFC | 2021-12-24 | 3
MSB1-RIO650-103-04 | CPK03-R3-IFC | 2021-12-24 | 3
26_24_16_43(16443)_dat | CPK03-R3-IFC | 2021-12-24 | 1
XMXR2Z50C | CPK03-R3-IFC | 2021-12-24 | 2
CMXL2G57A | CPK03-R3-IFC | 2021-12-24 | 2
CMLX2R50A | CPK03-R3-IFC | 2021-12-24 | 1
CMXL2Z50A | CPK03-R3-IFC | 2021-12-24 | 2
CMXR1AB53B | CPK03-R3-IFC | 2021-12-24 | 2
CMXR1M53B | CPK03-R3-IFC | 2021-12-24 | 2
CMXR1Q53B | CPK03-R3-IFC | 2021-12-24 | 3
CMXR1U53B | CPK03-R3-IFC | 2021-12-24 | 3
CMXR4M57A | CPK03-R3-IFC | 2021-12-24 | 3
MXD2R50C | CPK03-R3-IFC | 2021-12-24 | 2
MXD2R50D | CPK03-R3-IFC | 2021-12-24 | 2
MXD2R50E | CPK03-R3-IFC | 2021-12-24 | 2
MXD2T57D | CPK03-R3-IFC | 2021-12-24 | 2
MXD2T57E | CPK03-R3-IFC | 2021-12-24 | 2
MXD2X50G | CPK03-R3-IFC | 2021-12-24 | 2
MXD2X50H | CPK03-R3-IFC | 2021-12-24 | 2
MXD2X57A | CPK03-R3-IFC | 2021-12-24 | 2
MXL2R50A | CPK03-R3-IFC | 2021-12-24 | 2
MXL2T50A | CPK03-R3-IFC | 2021-12-24 | 2
MXL2X50A | CPK03-R3-IFC | 2021-12-24 | 2
MXL2T57A | CPK03-R3-IFC | 2021-12-24 | 2
MXR1U56A | CPK03-R3-IFC | 2021-12-24 | 2
MXR2X57A | CPK03-R3-IFC | 2021-12-24 | 3
XMXD2T57A | CPK03-R3-IFC | 2021-12-24 | 2
XMXD2X57B | CPK03-R3-IFC | 2021-12-24 | 2
XMXL2R50B | CPK03-R3-IFC | 2021-12-24 | 2
XMXL2Y57A | CPK03-R3-IFC | 2021-12-24 | 2
XMXL2Z50A | CPK03-R3-IFC | 2021-12-24 | 2
XMXR2T50B | CPK03-R3-IFC | 2021-12-24 | 2
27_15_00_00_MSB_SCC-RB314 | CPK03-R3-IFC | 2021-12-24 | 1
27_15_00_00_MSB_SCC-RB315 | CPK03-R3-IFC | 2021-12-24 | 1
27_15_00_00_MSB_SCC-RB316 | CPK03-R3-IFC | 2021-12-24 | 1
27_15_00_00_MSB_SCC-RB317 | CPK03-R3-IFC | 2021-12-24 | 1
27_15_00_00_MSB_SCC-RB318 | CPK03-R3-IFC | 2021-12-24 | 1
27_16_19_00_MSB_RB3 | CPK03-R3-IFC | 2021-12-24 | 1
27_16_19_00_MSB-RB3_CP_Outlets_Zones_317-118 | CPK03-R3-IFC | 2021-12-24 | 1
27_16_19_00_MSB_SCC-RB314 | CPK03-R3-IFC | 2021-12-24 | 1
27_16_19_00_MSB_SCC-RB315 | CPK03-R3-IFC | 2021-12-24 | 1
27_16_19_00_MSB_SCC-RB316 | CPK03-R3-IFC | 2021-12-24 | 1
27_16_19_00_MSB_SCC-RB317 | CPK03-R3-IFC | 2021-12-24 | 1
27_16_19_00_MSB_SCC-RB318 | CPK03-R3-IFC | 2021-12-24 | 1
40_05_15_16(15071) | CPK03-R3-IFC | 2021-12-24 | 1
40_05_15_16_tbl(15071) | CPK03-R3-IFC | 2021-12-24 | 1
40_05_15_34_DAT | CPK03-R3-IFC | 2021-12-24 | 3
MSB1-TCV102-1-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-1-52A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-2-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-2-52A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-3-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-3-52A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-4-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-4-52A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-5-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-5-52A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-6-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-6-52A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-7-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-7-52A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-8-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-8-52A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-9-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-9-52A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-10-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-10-52A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-11-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-12-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-13-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-14-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-15-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-16-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-17-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-18-22A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-18-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-19-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-20-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-21-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-22-22A | CPK03-R3-IFC | 2021-12-24 | 2
MSB1-TCV102-22-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-23-22A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-23-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-24-22A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-24-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-25-22A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-25-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-26-22A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-26-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-27-22A | CPK03-R3-IFC | 2021-12-24 | 2
MSB1-TCV102-27-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-28-22A | CPK03-R3-IFC | 2021-12-24 | 2
MSB1-TCV102-29-22A | CPK03-R3-IFC | 2021-12-24 | 2
MSB1-TCV102-29-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-30-22A | CPK03-R3-IFC | 2021-12-24 | 2
MSB1-TCV102-30-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-31-22A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-31-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-32-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-33-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-34-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-35-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-36-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-38-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-39-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-40-32A | CPK03-R3-IFC | 2021-12-24 | 1
MSB1-TCV102-41-32A | CPK03-R3-IFC | 2021-12-24 | 1
1255_SOO_029 | CPK03-R3-IFC | 2021-12-24 | 1
1257_SOO_06_MSB | CPK03-R3-IFC | 2021-12-24 | 2
1261_SOO_04_MSB | CPK03-R3-IFC | 2021-12-24 | 2
1283_SOO_01_D1BMSB | CPK03-R3-IFC | 2021-12-24 | 1
40_90_20_00_dat_ | CPK03-R3-IFC | 2021-12-24 | 1
45_43_13_65(13065)_dat | CPK03-R3-IFC | 2021-12-24 | 1
RA-ST-0506 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-1000 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-1001 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-1002 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-1003 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-1004 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-1008 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-1009 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-1011 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2000 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-2004 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2005 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2006 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-2007 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-2008 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-2009 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2010 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2011 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2012 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-2013 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-2014 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-2015 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-2016 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-2017 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2018 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2019 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2020 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2022 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2023 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2024 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-2025 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2026 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2027 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2028 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-2029 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2031 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2032 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-2033 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2034 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2035 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2036 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2037 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2040 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2041 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2042 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-2043 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2044 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-2045 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2046 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2048 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2051 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2052 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2053 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2054 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2055 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2056 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2057 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2058 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2059 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2060 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2061 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2062 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2063 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2064 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2065 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2066 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2067 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2068 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2069 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2070 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2071 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2072 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2073 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2074 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2075 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2076 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2077 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2078 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2079 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2080 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2081 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2082 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2083 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2084 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2085 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2086 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2087 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2088 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2089 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2090 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2091 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2092 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2093 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2094 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2095 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2097 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2100 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2102 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2105 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2106 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2107 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2108 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2109 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2110 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2111 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2112 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2113 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2114 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2118 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2120 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2126 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2127 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2128 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2129 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2131 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2136 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2137 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2138 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2139 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2140 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2141 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2142 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2143 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2144 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2147 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2148 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2149 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2150 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2151 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2157 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2158 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2160 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2161 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2164 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2165 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2166 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2168 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2169 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2170 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2171 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2172 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2173 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2174 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2175 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2177 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2178 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2179 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2182 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2184 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-2185 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-3000 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-3001 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-3002 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-3008 | CPK03-R3-IFC | 2021-12-24 | 8
RA-ST-4000 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-4001 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-4002 | CPK03-R3-IFC | 2021-12-24 | 9
RA-ST-4003 | CPK03-R3-IFC | 2021-12-24 | 9
00_01_00_00 | CPK03-R4-IFC | 2021-10-13 | 7
MS1-101-D0-A01 | CPK03-R4-IFC | 2021-10-13 | 2
MS1-101-D0-A02 | CPK03-R4-IFC | 2021-10-13 | 3
MS1-101-D0-A05 | CPK03-R4-IFC | 2021-10-13 | 2
MS1-101-D0-A06 | CPK03-R4-IFC | 2021-10-13 | 3
MS1-101-D0-A07 | CPK03-R4-IFC | 2021-10-13 | 2
MS1-101-D0-A08 | CPK03-R4-IFC | 2021-10-13 | 1
MS1-101-D0-A09 | CPK03-R4-IFC | 2021-10-13 | 2
1254_SOO_01_MSB | CPK03-R4-IFC | 2021-10-13 | 1
1254_SOO_02_MSB | CPK03-R4-IFC | 2021-10-13 | 1
1254_SOO_03_MSB | CPK03-R4-IFC | 2021-10-13 | 1
1254_SOO_05_MSB | CPK03-R4-IFC | 2021-10-13 | 1
1254_SOO_06_MSB | CPK03-R4-IFC | 2021-10-13 | 1
00_00_00_01 | CPK03-R4-IFC | 2021-10-13 | 6
40_90_15_00_DAT | CPK03-R4-IFC | 2021-10-13 | 1
45_43_13_69_SPT_01 | CPK03-R4-IFC | 2021-10-13 | 1
CL00A | CPK03-R4-IFC | 2021-10-13 | 1
CL04G | CPK03-R4-IFC | 2021-10-13 | 1
CL06A | CPK03-R4-IFC | 2021-10-13 | 1
CL08A | CPK03-R4-IFC | 2021-10-13 | 1
CL09A | CPK03-R4-IFC | 2021-10-13 | 1
CL10A | CPK03-R4-IFC | 2021-10-13 | 1
CL11A | CPK03-R4-IFC | 2021-10-13 | 1
CL13 | CPK03-R4-IFC | 2021-10-13 | 1
CL13A | CPK03-R4-IFC | 2021-10-13 | 1
CL15A | CPK03-R4-IFC | 2021-10-13 | 1
CL50A | CPK03-R4-IFC | 2021-10-13 | 1
MS1-S0-0010 | CPK03-R5-IFC | 2021-11-24 | 8
MS1-SS-5RC-B0000 | CPK03-R5-IFC | 2021-11-24 | 6
MS1-SS-5RC-C0000 | CPK03-R5-IFC | 2021-11-24 | 3
MS1-SS-5RC-D0000 | CPK03-R5-IFC | 2021-11-24 | 1
MS1-SS-5RE-B0000 | CPK03-R5-IFC | 2021-11-24 | 4
MS1-SS-5RE-D0000 | CPK03-R5-IFC | 2021-11-24 | 2
MS1-SS-5RF-C0000 | CPK03-R5-IFC | 2021-11-24 | 5
MS1-SS-5RJ-B0000 | CPK03-R5-IFC | 2021-11-24 | 2
MS1-SS-5RJ-C0000 | CPK03-R5-IFC | 2021-11-24 | 1
MS1-SS-5RJ-D0000 | CPK03-R5-IFC | 2021-11-24 | 2
MS1-SS-5RK-A0D00-D | CPK03-R5-IFC | 2021-11-24 | 2
MS1-SS-5RK-B0000 | CPK03-R5-IFC | 2021-11-24 | 2
MS1-SS-5RK-C0000 | CPK03-R5-IFC | 2021-11-24 | 1
MS1-SS-5RK-D0000 | CPK03-R5-IFC | 2021-11-24 | 2
MS1-SS-5RS-B0000 | CPK03-R5-IFC | 2021-11-24 | 4
MS1-SS-5RS-C0000 | CPK03-R5-IFC | 2021-11-24 | 1
MS1-SS-5RS-D0000 | CPK03-R5-IFC | 2021-11-24 | 2
MS1-S0-6211 | CPK03-R5-IFC | 2021-11-24 | 3
MS1-S0-6212 | CPK03-R5-IFC | 2021-11-24 | 2
MS1-S0-6213 | CPK03-R5-IFC | 2021-11-24 | 2
MS1-S0-6214-D | CPK03-R5-IFC | 2021-11-24 | 3
MS1-S0-6215 | CPK03-R5-IFC | 2021-11-24 | 1
RA-ST-0019 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2001 | CPK03-R5-IFC | 2021-11-24 | 7
RA-ST-2002 | CPK03-R5-IFC | 2021-11-24 | 7
RA-ST-2003 | CPK03-R5-IFC | 2021-11-24 | 7
RA-ST-2021 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2030 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2038 | CPK03-R5-IFC | 2021-11-24 | 3
RA-ST-2039 | CPK03-R5-IFC | 2021-11-24 | 5
RA-ST-2047 | CPK03-R5-IFC | 2021-11-24 | 7
RA-ST-2049 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2050 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2096 | CPK03-R5-IFC | 2021-11-24 | 7
RA-ST-2098 | CPK03-R5-IFC | 2021-11-24 | 7
RA-ST-2099 | CPK03-R5-IFC | 2021-11-24 | 7
RA-ST-2101 | CPK03-R5-IFC | 2021-11-24 | 7
RA-ST-2104 | CPK03-R5-IFC | 2021-11-24 | 7
RA-ST-2115 | CPK03-R5-IFC | 2021-11-24 | 7
RA-ST-2116 | CPK03-R5-IFC | 2021-11-24 | 7
RA-ST-2117 | CPK03-R5-IFC | 2021-11-24 | 7
RA-ST-2119 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2121 | CPK03-R5-IFC | 2021-11-24 | 7
RA-ST-2122 | CPK03-R5-IFC | 2021-11-24 | 7
RA-ST-2130 | CPK03-R5-IFC | 2021-11-24 | 7
RA-ST-2132 | CPK03-R5-IFC | 2021-11-24 | 3
RA-ST-2135 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2145 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2159 | CPK03-R5-IFC | 2021-11-24 | 3
RA-ST-2162 | CPK03-R5-IFC | 2021-11-24 | 3
RA-ST-2163 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2180 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-0001 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-0002 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-0003 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-0004 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-0005 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-0006 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-0007 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-0008 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-0009 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-0010 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-0011 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-0012 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-0013 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-0014 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-0015 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-0016 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-0017 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-0018 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-0020 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-0021 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-0022 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-0500 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-0501 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-0502 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-0503 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-0504 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-0505 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-0506 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-1000 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-1001 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-1002 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-1003 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-1004 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-1008 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-1009 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-1011 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2000 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-2004 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2005 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2006 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-2007 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-2008 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-2009 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2010 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2011 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2012 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-2013 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-2014 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-2015 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-2016 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-2017 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2018 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2019 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2020 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2022 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2023 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2024 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-2025 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2026 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2027 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2028 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-2029 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2031 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2032 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-2033 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2034 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2035 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2036 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2037 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2040 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2041 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2042 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-2043 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2044 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-2045 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2046 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2048 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2051 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2052 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2053 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2054 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2055 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2056 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2057 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2058 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2059 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2060 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2061 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2062 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2063 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2064 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2065 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2066 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2067 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2068 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2069 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2070 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2071 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2072 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2073 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2074 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2075 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2076 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2077 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2078 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2079 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2080 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2081 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2082 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2083 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2084 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2085 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2086 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2087 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2088 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2089 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2090 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2091 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2092 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2093 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2094 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2095 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2097 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2100 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2102 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2105 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2106 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2107 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2108 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2109 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2110 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2111 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2112 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2113 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2114 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2118 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2120 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2126 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2127 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2128 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2129 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2131 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2136 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2137 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2138 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2139 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2140 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2141 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2142 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2143 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2144 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2147 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2148 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2149 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2150 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2151 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2157 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2158 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2160 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2161 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2164 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2165 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2166 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2168 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2169 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2170 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2171 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2172 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2173 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2174 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2175 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2177 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2178 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2179 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2182 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2184 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-2185 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-3000 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-3001 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-3002 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-3008 | CPK03-R5-IFC | 2021-11-24 | 8
RA-ST-4000 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-4001 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-4002 | CPK03-R5-IFC | 2021-11-24 | 9
RA-ST-4003 | CPK03-R5-IFC | 2021-11-24 | 9
ISAT-MP-AT-CS-U1-B | CPK03-R6-IFC | 2021-12-28 | 6
ISAT-MP-AT-CS-U2-B | CPK03-R6-IFC | 2021-12-28 | 6
ISAT-MP-AT-PS-A1-U | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-CS-A1-I-PI | CPK03-R6-IFC | 2021-12-28 | 6
ISAT-MP-BM-CS-A1-I-VB | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-CS-A1-U | CPK03-R6-IFC | 2021-12-28 | 6
ISAT-MP-BM-CS-G1-I-PI | CPK03-R6-IFC | 2021-12-28 | 6
ISAT-MP-BM-CS-G1-I-VB | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-CS-G1-U | CPK03-R6-IFC | 2021-12-28 | 6
ISAT-MP-BM-CS-G2-I-PI | CPK03-R6-IFC | 2021-12-28 | 6
ISAT-MP-BM-CS-S1-I-PI | CPK03-R6-IFC | 2021-12-28 | 6
ISAT-MP-BM-CS-S1-U | CPK03-R6-IFC | 2021-12-28 | 6
ISAT-MP-BM-CS-S3-I-PI | CPK03-R6-IFC | 2021-12-28 | 6
ISAT-MP-BM-PS-A1-U | CPK03-R6-IFC | 2021-12-28 | 6
ISAT-MP-BM-PS-G1-U | CPK03-R6-IFC | 2021-12-28 | 6
ISAT-MP-BM-PS-S1-U | CPK03-R6-IFC | 2021-12-28 | 6
ISAT-MP-BM-SS-A1-U-VB | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-SS-A2-I-VB | CPK03-R6-IFC | 2021-12-28 | 4
ISAT-MP-BM-SS-A2-U-VB | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-SS-A3-I-VB | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-SS-A3-U-VB | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-SS-A5-I-VB | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-SS-A5-U-VB | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-SS-A7-I-VB | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-SS-G1-I-VB | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-SS-G1-U-VB | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-SS-G2-I-VB | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-SS-G2-U-VB | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-SS-G3-I-VB | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-SS-G3-U-VB | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-FM-SS-S1-U | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-OH-CS-S1-I | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-OH-CS-S2-I-PI | CPK03-R6-IFC | 2021-12-28 | 6
ISAT-MP-OH-CS-S2-I-VB | CPK03-R6-IFC | 2021-12-28 | 6
ISAT-MP-RS-CS-A1-I-VB | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-RS-CS-A1-U-VB | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-SS-CS-L1-B-VB | CPK03-R6-IFC | 2021-12-28 | 6
MP-AT-G-1 | CPK03-R6-IFC | 2021-12-28 | 5
MP-BM-A-1 | CPK03-R6-IFC | 2021-12-28 | 6
MP-BM-G-1 | CPK03-R6-IFC | 2021-12-28 | 6
MP-VB-S-1 | CPK03-R6-IFC | 2021-12-28 | 6
MP-VB-S-2 | CPK03-R6-IFC | 2021-12-28 | 6
MS1-S0-6219 | CPK03-R6-IFC | 2021-12-28 | 1
MS1-S0-6220 | CPK03-R6-IFC | 2021-12-28 | 1
MS1-S0-6256 | CPK03-R6-IFC | 2021-12-28 | 1
MS1-S0-6257 | CPK03-R6-IFC | 2021-12-28 | 1
MS1-SS-1SA-4002 | CPK03-R6-IFC | 2021-12-28 | 1
MS1-SS-1SA-4003 | CPK03-R6-IFC | 2021-12-28 | 1
MS1-SS-1SA-4004 | CPK03-R6-IFC | 2021-12-28 | 1
MS1-SS-1SA-4005 | CPK03-R6-IFC | 2021-12-28 | 2
MS1-SS-1SA-C0300 | CPK03-R6-IFC | 2021-12-28 | 2
MS1-202-D0-A01 | CPK03-R6-IFC | 2021-12-28 | 2
RA-ST-2500 | CPK03-R6-IFC | 2021-12-28 | 4
RA-ST-2501 | CPK03-R6-IFC | 2021-12-28 | 5
RA-ST-2502 | CPK03-R6-IFC | 2021-12-28 | 5
RA-ST-2504 | CPK03-R6-IFC | 2021-12-28 | 5
RA-ST-2505 | CPK03-R6-IFC | 2021-12-28 | 5
RA-ST-2506 | CPK03-R6-IFC | 2021-12-28 | 5
RA-ST-2507 | CPK03-R6-IFC | 2021-12-28 | 5
RA-ST-2508 | CPK03-R6-IFC | 2021-12-28 | 5
RA-ST-2509 | CPK03-R6-IFC | 2021-12-28 | 5
RA-ST-2510 | CPK03-R6-IFC | 2021-12-28 | 5
RA-ST-2511 | CPK03-R6-IFC | 2021-12-28 | 5
RA-ST-2512 | CPK03-R6-IFC | 2021-12-28 | 5
RA-ST-2513 | CPK03-R6-IFC | 2021-12-28 | 5
RA-ST-2514 | CPK03-R6-IFC | 2021-12-28 | 5
RA-ST-2515 | CPK03-R6-IFC | 2021-12-28 | 5
RA-ST-2516 | CPK03-R6-IFC | 2021-12-28 | 5
RA-ST-2517 | CPK03-R6-IFC | 2021-12-28 | 5
RA-ST-2518 | CPK03-R6-IFC | 2021-12-28 | 5
RA-ST-2519 | CPK03-R6-IFC | 2021-12-28 | 5
RA-ST-2520 | CPK03-R6-IFC | 2021-12-28 | 5
RA-ST-2521 | CPK03-R6-IFC | 2021-12-28 | 4
RA-ST-2522 | CPK03-R6-IFC | 2021-12-28 | 4
RA-ST-2523 | CPK03-R6-IFC | 2021-12-28 | 4
RA-ST-2524 | CPK03-R6-IFC | 2021-12-28 | 4
RA-ST-2525 | CPK03-R6-IFC | 2021-12-28 | 4
RA-ST-2526 | CPK03-R6-IFC | 2021-12-28 | 4
RA-ST-2527 | CPK03-R6-IFC | 2021-12-28 | 4
RA-ST-2528 | CPK03-R6-IFC | 2021-12-28 | 4
RA-ST-2529 | CPK03-R6-IFC | 2021-12-28 | 4
RA-ST-2530 | CPK03-R6-IFC | 2021-12-28 | 4
RA-ST-2531 | CPK03-R6-IFC | 2021-12-28 | 4
RA-ST-2532 | CPK03-R6-IFC | 2021-12-28 | 4
RA-ST-2533 | CPK03-R6-IFC | 2021-12-28 | 4
RA-ST-2534 | CPK03-R6-IFC | 2021-12-28 | 4
RA-ST-2535 | CPK03-R6-IFC | 2021-12-28 | 4
RA-ST-2536 | CPK03-R6-IFC | 2021-12-28 | 4
RA-ST-2537 | CPK03-R6-IFC | 2021-12-28 | 4
RA-ST-2538 | CPK03-R6-IFC | 2021-12-28 | 4
RA-ST-2539 | CPK03-R6-IFC | 2021-12-28 | 4
RA-ST-2540 | CPK03-R6-IFC | 2021-12-28 | 4
RA-ST-2541 | CPK03-R6-IFC | 2021-12-28 | 4
RA-ST-2542 | CPK03-R6-IFC | 2021-12-28 | 4
RA-ST-2543 | CPK03-R6-IFC | 2021-12-28 | 4
RA-ST-2544 | CPK03-R6-IFC | 2021-12-28 | 4
RA-ST-2545 | CPK03-R6-IFC | 2021-12-28 | 4
RA-ST-2546 | CPK03-R6-IFC | 2021-12-28 | 4
RA-ST-2547 | CPK03-R6-IFC | 2021-12-28 | 4
ISAT-MP-AT-NA-L1-B-VB | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-AT-NA-L3-B-VB | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-AT-CS-G1-B | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-AT-CS-G2-B | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-AT-CS-A1-B | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-AT-NA-A1-B | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-AT-NA-A2-B | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-AT-NA-U1-B | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-AT-NA-U2-B | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-CS-S1-U-VB | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-CS-S1-I-VB | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-SS-S1-U-VB | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-SS-S1-I-VB | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-CS-A4-I-VB | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-SS-A4-I-VB | CPK03-R6-IFC | 2021-12-28 | 4
ISAT-MP-BM-SS-A4-U-VB | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-SS-S1-U | CPK03-R6-IFC | 2021-12-28 | 4
ISAT-MP-BM-SS-G1-U | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-SS-G1-I | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-SS-G2-U | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-CS-G3-U | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-SS-G3-U | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-SS-A1-U | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-SS-A1-I | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-SS-A2-U | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-SS-A2-I | CPK03-R6-IFC | 2021-12-28 | 1
ISAT-MP-BM-CS-A4-U | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-SS-A4-U | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-BM-SS-A6-U | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-OH-SS-S2-U-VB | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-OH-PS-S1-U | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-OH-SS-S1-U | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-OH-PS-G1-U | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-OH-NA-U1-B | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-RS-SS-G2-U | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-RS-SS-A1-U | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-SS-SS-L2-B-VB | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-SS-CS-L1-B | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-SS-CS-L2-B | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-SS-CS-L3-B | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-SS-NA-U1-B | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-SS-NA-U2-B | CPK03-R6-IFC | 2021-12-28 | 5
AT-VB-A-1 | CPK03-R6-IFC | 2021-12-28 | 5
MP-BM-A-6 | CPK03-R6-IFC | 2021-12-28 | 5
MP-OH-S-5 | CPK03-R6-IFC | 2021-12-28 | 5
MP-RS-G-1 | CPK03-R6-IFC | 2021-12-28 | 5
MP-SS-S-2 | CPK03-R6-IFC | 2021-12-28 | 5
MP-VB-A-2 | CPK03-R6-IFC | 2021-12-28 | 5
MP-VB-S-3 | CPK03-R6-IFC | 2021-12-28 | 5
RA-ST-2503 | CPK03-R6-IFC | 2021-12-28 | 5
ISAT-MP-AT-CS-U1-B | CPK03-R7-IFC | 2022-01-17 | 6
ISAT-MP-AT-CS-U2-B | CPK03-R7-IFC | 2022-01-17 | 6
ISAT-MP-AT-PS-A1-U | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-CS-A1-I-PI | CPK03-R7-IFC | 2022-01-17 | 6
ISAT-MP-BM-CS-A1-I-VB | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-CS-A1-U | CPK03-R7-IFC | 2022-01-17 | 6
ISAT-MP-BM-CS-G1-I-PI | CPK03-R7-IFC | 2022-01-17 | 6
ISAT-MP-BM-CS-G1-I-VB | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-CS-G1-U | CPK03-R7-IFC | 2022-01-17 | 6
ISAT-MP-BM-CS-G2-I-PI | CPK03-R7-IFC | 2022-01-17 | 6
ISAT-MP-BM-CS-G2-I-VB | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-BM-CS-G7-U | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-BM-CS-S1-I-PI | CPK03-R7-IFC | 2022-01-17 | 6
ISAT-MP-BM-CS-S1-U | CPK03-R7-IFC | 2022-01-17 | 6
ISAT-MP-BM-CS-S3-I-PI | CPK03-R7-IFC | 2022-01-17 | 6
ISAT-MP-BM-PS-A1-U | CPK03-R7-IFC | 2022-01-17 | 6
ISAT-MP-BM-PS-G1-U | CPK03-R7-IFC | 2022-01-17 | 6
ISAT-MP-BM-PS-S1-U | CPK03-R7-IFC | 2022-01-17 | 6
ISAT-MP-BM-SS-A1-U-VB | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-SS-A2-I-VB | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-BM-SS-A2-U-VB | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-SS-A3-I-VB | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-SS-A3-U-VB | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-SS-A5-I-VB | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-SS-A5-U-VB | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-SS-A7-I-VB | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-SS-A7-U | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-BM-SS-G1-I-VB | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-SS-G1-U-VB | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-SS-G2-I-VB | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-SS-G2-U-VB | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-SS-G3-I-VB | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-SS-G3-U-VB | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-FM-CS-S1-I-VB | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-FM-SS-S1-U | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-OH-CS-S1-I | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-OH-CS-S2-I-PI | CPK03-R7-IFC | 2022-01-17 | 6
ISAT-MP-OH-CS-S2-I-VB | CPK03-R7-IFC | 2022-01-17 | 6
ISAT-MP-RS-CS-A1-I-VB | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-RS-CS-A1-U | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-RS-CS-A1-U-VB | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-RS-SS-S1-U | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-SS-CS-L1-B-VB | CPK03-R7-IFC | 2022-01-17 | 6
MP-AT-G-1 | CPK03-R7-IFC | 2022-01-17 | 5
MP-BM-A-1 | CPK03-R7-IFC | 2022-01-17 | 6
MP-BM-G-1 | CPK03-R7-IFC | 2022-01-17 | 6
MP-VB-S-1 | CPK03-R7-IFC | 2022-01-17 | 6
MP-VB-S-2 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-0001 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-0002 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-0003 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-0004 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-0005 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-0006 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-0007 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-0008 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-0009 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-0010 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-0011 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-0012 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-0013 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-0014 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-0015 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-0016 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-0017 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-0018 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-0020 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-0021 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-0022 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-0500 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-0501 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-0502 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-0503 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-0504 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-0505 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-0506 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-1000 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-1001 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-1002 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-1003 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-1004 | CPK03-R7-IFC | 2022-01-17 | 8
MS1-GZ-6000 | CPK03-R7-IFC | 2022-01-17 | 1
MS1-GZ-6001 | CPK03-R7-IFC | 2022-01-17 | 1
MS1-GZ-6002 | CPK03-R7-IFC | 2022-01-17 | 1
MS1-GZ-6003 | CPK03-R7-IFC | 2022-01-17 | 1
MS1-GZ-6004 | CPK03-R7-IFC | 2022-01-17 | 1
MS1-GZ-6005 | CPK03-R7-IFC | 2022-01-17 | 1
RAC-GN-0001 | CPK03-R7-IFC | 2022-01-17 | 5
RAC-GN-0002 | CPK03-R7-IFC | 2022-01-17 | 5
RAC-GN-0003 | CPK03-R7-IFC | 2022-01-17 | 5
RAC-GN-0004 | CPK03-R7-IFC | 2022-01-17 | 5
RAC-GN-0005 | CPK03-R7-IFC | 2022-01-17 | 5
RAC-GN-0006 | CPK03-R7-IFC | 2022-01-17 | 5
RAC-GN-0007 | CPK03-R7-IFC | 2022-01-17 | 5
RAC-GN-0008 | CPK03-R7-IFC | 2022-01-17 | 5
RAC-GN-0009 | CPK03-R7-IFC | 2022-01-17 | 5
RAC-GN-0010 | CPK03-R7-IFC | 2022-01-17 | 5
RAC-C0-0000 | CPK03-R7-IFC | 2022-01-17 | 1
RAC-C0-1AA-B31D0 | CPK03-R7-IFC | 2022-01-17 | 1
RAC-C0-1AA-B31D0-D | CPK03-R7-IFC | 2022-01-17 | 1
RAC-C0-9000 | CPK03-R7-IFC | 2022-01-17 | 1
RAC-C0-9001 | CPK03-R7-IFC | 2022-01-17 | 1
D1X-S0-6253 | CPK03-R7-IFC | 2022-01-17 | 1
D1X-SS-2SA-4000 | CPK03-R7-IFC | 2022-01-17 | 1
PB1-SS-10A-4004 | CPK03-R7-IFC | 2022-01-17 | 1
PB1-S0-6209 | CPK03-R7-IFC | 2022-01-17 | 1
MS1-S0-0010 | CPK03-R7-IFC | 2022-01-17 | 8
MS1-SS-1SA-4000 | CPK03-R7-IFC | 2022-01-17 | 1
MS1-SS-1SA-4005 | CPK03-R7-IFC | 2022-01-17 | 2
MS1-SS-1SA-D0200 | CPK03-R7-IFC | 2022-01-17 | 1
MS1-SS-1SA-B0300 | CPK03-R7-IFC | 2022-01-17 | 1
MS1-SS-1SF-B0000 | CPK03-R7-IFC | 2022-01-17 | 3
MS1-SS-1SF-4000 | CPK03-R7-IFC | 2022-01-17 | 1
MS1-SS-1SG-4000 | CPK03-R7-IFC | 2022-01-17 | 1
MS1-SS-1SH-4000 | CPK03-R7-IFC | 2022-01-17 | 1
MS1-SS-2FA-4000 | CPK03-R7-IFC | 2022-01-17 | 1
MS1-SS-2FC-4000 | CPK03-R7-IFC | 2022-01-17 | 1
MS1-SS-2FD-4000 | CPK03-R7-IFC | 2022-01-17 | 1
MS1-SS-2FE-4000 | CPK03-R7-IFC | 2022-01-17 | 1
MS1-S0-6222 | CPK03-R7-IFC | 2022-01-17 | 1
MS1-S0-6223 | CPK03-R7-IFC | 2022-01-17 | 1
MS1-S0-6258 | CPK03-R7-IFC | 2022-01-17 | 1
MS1-261-PW-Z10 | CPK03-R7-IFC | 2022-01-17 | 2
MS1-270-PW-Z10 | CPK03-R7-IFC | 2022-01-17 | 2
MS1-IE-1025 | CPK03-R7-IFC | 2022-01-17 | 2
MS1-IE-1SA-B0000 | CPK03-R7-IFC | 2022-01-17 | 4
MS1-IE-1SA-C0000 | CPK03-R7-IFC | 2022-01-17 | 5
MS1-IE-1SA-D0000 | CPK03-R7-IFC | 2022-01-17 | 5
D1X-138-D0-A29 | CPK03-R7-IFC | 2022-01-17 | 3
MS1-132-D0-Z02 | CPK03-R7-IFC | 2022-01-17 | 2
MS1-132-D0-Z03 | CPK03-R7-IFC | 2022-01-17 | 3 | Y
MS1-133-D0-A04 | CPK03-R7-IFC | 2022-01-17 | 2
MS1-138-D0-Z02 | CPK03-R7-IFC | 2022-01-17 | 2
MS1-147-D0-Z01 | CPK03-R7-IFC | 2022-01-17 | 3
MS1-147-D0-Z02 | CPK03-R7-IFC | 2022-01-17 | 3
MS1-402-D0-Z01 | CPK03-R7-IFC | 2022-01-17 | 3
MS1-404-D0-Z01 | CPK03-R7-IFC | 2022-01-17 | 2
RA-ST-1008 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-1009 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-0019 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-1011 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-1005 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-1006 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-1010 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-1012 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-1013 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-1014 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-1015 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-1018 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-1023 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-1024 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-1025 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-1026 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-1027 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-1028 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2001 | CPK03-R7-IFC | 2022-01-17 | 7
RA-ST-2002 | CPK03-R7-IFC | 2022-01-17 | 7
RA-ST-2003 | CPK03-R7-IFC | 2022-01-17 | 7
RA-ST-2000 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-2004 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2021 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2005 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2030 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2006 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-2047 | CPK03-R7-IFC | 2022-01-17 | 7
RA-ST-2049 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2050 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2007 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-2008 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-2009 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2010 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2096 | CPK03-R7-IFC | 2022-01-17 | 7
RA-ST-2098 | CPK03-R7-IFC | 2022-01-17 | 7
RA-ST-2099 | CPK03-R7-IFC | 2022-01-17 | 7
RA-ST-2101 | CPK03-R7-IFC | 2022-01-17 | 7
RA-ST-2103 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-2104 | CPK03-R7-IFC | 2022-01-17 | 7
RA-ST-2011 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2115 | CPK03-R7-IFC | 2022-01-17 | 7
RA-ST-2116 | CPK03-R7-IFC | 2022-01-17 | 7
RA-ST-2117 | CPK03-R7-IFC | 2022-01-17 | 7
RA-ST-2119 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2121 | CPK03-R7-IFC | 2022-01-17 | 7
RA-ST-2122 | CPK03-R7-IFC | 2022-01-17 | 7
RA-ST-2012 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-2130 | CPK03-R7-IFC | 2022-01-17 | 7
RA-ST-2135 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2145 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2013 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-2163 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2167 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-2014 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-2176 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-2180 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2181 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-2183 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-2192 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-2197 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-2199 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-2200 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-2201 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-2203 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2204 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-2205 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-2206 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-2207 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-2208 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-2209 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-2210 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-2211 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2212 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2213 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2214 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2215 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2216 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2217 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2218 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-2219 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-2220 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-2221 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2222 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-2223 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-2226 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2227 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2228 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2229 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2230 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-2231 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2232 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2235 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2237 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2238 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2239 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-2242 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-2243 | CPK03-R7-IFC | 2022-01-17 | 6
RA-ST-2244 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2245 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2246 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2247 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2249 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2250 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2251 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2253 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2254 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2255 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2256 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2257 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2258 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2260 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2261 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2262 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2263 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2264 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2265 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2266 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2267 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2268 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2269 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2270 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2277 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2278 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2279 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2280 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2281 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2282 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2283 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2285 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2286 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2288 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2289 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2291 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2292 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2293 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2294 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2295 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2296 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2297 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2298 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2299 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2015 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-3009 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-4008 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-4010 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-4011 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-4012 | CPK03-R7-IFC | 2022-01-17 | 5
RA-P0-9001 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9002 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9003 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9004 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9005 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9006 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9007 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9008 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9009 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9010 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9011 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9012 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9013 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9014 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9015 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9016 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9017 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9018 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9019 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9020 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9021 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9022 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9023 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9024 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9025 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9026 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9027 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9028 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9029 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9030 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9031 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9032 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9033 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9034 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9035 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9036 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9037 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9038 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9039 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9040 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9041 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9043 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9044 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9045 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9046 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9047 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9048 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9049 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9050 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9051 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9052 | CPK03-R7-IFC | 2022-01-17 | 3
RA-P0-9053 | CPK03-R7-IFC | 2022-01-17 | 2
RA-P0-9054 | CPK03-R7-IFC | 2022-01-17 | 2
RA-P0-9055 | CPK03-R7-IFC | 2022-01-17 | 2
RA-P0-9056 | CPK03-R7-IFC | 2022-01-17 | 2
RA-P0-9057 | CPK03-R7-IFC | 2022-01-17 | 2
RA-ST-2500 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2501 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2502 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2504 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2505 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2506 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2507 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2508 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2509 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2510 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2511 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2512 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2513 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2514 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2515 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2516 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2517 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2518 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2519 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2520 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2521 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2522 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2523 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2524 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2525 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2526 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2527 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2528 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2529 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2530 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2531 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2532 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2533 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2534 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2535 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2536 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2537 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2538 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2539 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2540 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2541 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2542 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2543 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2544 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2545 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2546 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2547 | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2548 | CPK03-R7-IFC | 2022-01-17 | 3
RA-ST-2549 | CPK03-R7-IFC | 2022-01-17 | 3
RA-ST-2550 | CPK03-R7-IFC | 2022-01-17 | 3
RA-ST-2551 | CPK03-R7-IFC | 2022-01-17 | 3
RA-ST-2552 | CPK03-R7-IFC | 2022-01-17 | 3
RA-ST-2553 | CPK03-R7-IFC | 2022-01-17 | 3
RA-ST-2554 | CPK03-R7-IFC | 2022-01-17 | 3
RA-ST-2555 | CPK03-R7-IFC | 2022-01-17 | 3
RA-ST-2556 | CPK03-R7-IFC | 2022-01-17 | 3
RA-ST-2557 | CPK03-R7-IFC | 2022-01-17 | 3
RA-ST-2558 | CPK03-R7-IFC | 2022-01-17 | 3
RA-ST-2559 | CPK03-R7-IFC | 2022-01-17 | 3
RA-ST-2560 | CPK03-R7-IFC | 2022-01-17 | 3
RA-ST-2561 | CPK03-R7-IFC | 2022-01-17 | 3
RA-ST-2562 | CPK03-R7-IFC | 2022-01-17 | 3
RA-ST-2563 | CPK03-R7-IFC | 2022-01-17 | 3
RA-ST-2564 | CPK03-R7-IFC | 2022-01-17 | 3
RA-ST-2565 | CPK03-R7-IFC | 2022-01-17 | 3
RA-ST-2566 | CPK03-R7-IFC | 2022-01-17 | 3
RA-ST-2567 | CPK03-R7-IFC | 2022-01-17 | 3
RA-ST-2568 | CPK03-R7-IFC | 2022-01-17 | 3
RA-ST-2569 | CPK03-R7-IFC | 2022-01-17 | 3
RA-ST-2570 | CPK03-R7-IFC | 2022-01-17 | 3
RA-ST-2571 | CPK03-R7-IFC | 2022-01-17 | 3
ISAT-MP-AT-NA-L1-B-VB | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-AT-NA-L3-B-VB | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-AT-CS-G1-B | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-AT-CS-G2-B | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-AT-CS-G3-B | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-AT-CS-A1-B | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-AT-NA-A1-B | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-AT-NA-A2-B | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-AT-CS-A3-B | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-AT-CS-A4-B | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-AT-NA-U1-B | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-AT-NA-U2-B | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-AT-NA-U3-B | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-AT-NA-U4-B | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-BM-PF-G1-B-FL | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-BM-PF-A1-B-FL | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2016 | CPK03-R7-IFC | 2022-01-17 | 9
ISAT-MP-BM-CS-S1-I-VB | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-CS-S1-U-VB | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-SS-S1-I-VB | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-SS-S1-U-VB | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2017 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2018 | CPK03-R7-IFC | 2022-01-17 | 8
ISAT-BM-CS-A2-I-VB | CPK03-R7-IFC | 2022-01-17 | 1
RA-ST-2019 | CPK03-R7-IFC | 2022-01-17 | 8
ISAT-MP-BM-CS-A4-I-VB | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-SS-A4-I-VB | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-BM-SS-A4-U-VB | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-CS-S1-I | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-BM-PF-S1-I | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-BM-PF-S1-U | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2020 | CPK03-R7-IFC | 2022-01-17 | 8
ISAT-MP-BM-SS-S1-U | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-BM-CS-S7-U | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-BM-CS-G1-I | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-BM-CU-G1-U | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-BM-PF-G1-I | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-BM-PF-G1-U | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-BM-PS-G1-I | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-BM-SS-G1-U | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-SS-G1-I | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-SS-G2-U | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-CS-G3-U | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-SS-G3-U | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-CS-A1-I | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-BM-CU-A1-U | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-BM-PF-A1-I | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-BM-PF-A1-U | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-BM-PS-A1-I | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-BM-SS-A1-U | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-SS-A1-I | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-PF-A2-I | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-BM-PF-A2-U | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-BM-PS-A2-U | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-BM-SS-A2-U | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-CS-A4-U | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-SS-A4-I | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-BM-SS-A4-U | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-CS-A6-U | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-BM-SS-A6-U | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-BM-CS-A7-U | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-BM-CS-A8-U | CPK03-R7-IFC | 2022-01-17 | 4
RA-ST-2022 | CPK03-R7-IFC | 2022-01-17 | 8
ISAT-MP-OH-SS-S2-U-VB | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-OH-CS-S3-I-VB | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-OH-CS-S1-U | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-OH-PF-S1-I | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-OH-PF-S1-U | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-OH-PS-S1-U | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-OH-PS-S1-I | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-OH-SS-S1-U | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-OH-SS-S1-I | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-OH-PS-G1-U | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-OH-PF-G2-I | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-OH-PF-G2-U | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-OH-NA-U1-B | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2023 | CPK03-R7-IFC | 2022-01-17 | 8
ISAT-MP-RS-CS-S1-U | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-RS-PF-S1-U | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-RS-CS-G2-I | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-RS-SS-G2-U | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-RS-CS-A1-I | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-RS-PF-A1-U | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-RS-SS-A1-U | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-SS-SS-L2-B-VB | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-SS-CS-L1-B | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-SS-CS-L2-B | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-SS-CS-L3-B | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-SS-NA-U1-B | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-SS-NA-U2-B | CPK03-R7-IFC | 2022-01-17 | 5
ISAT-MP-WM-NA-W1-B | CPK03-R7-IFC | 2022-01-17 | 4
ISAT-MP-WM-NA-W2-B | CPK03-R7-IFC | 2022-01-17 | 4
AT-VB-A-1 | CPK03-R7-IFC | 2022-01-17 | 5
MP-AT-A-2 | CPK03-R7-IFC | 2022-01-17 | 4
MP-BM-A-6 | CPK03-R7-IFC | 2022-01-17 | 5
MP-BM-A-7 | CPK03-R7-IFC | 2022-01-17 | 4
MP-BM-A-8 | CPK03-R7-IFC | 2022-01-17 | 4
MP-FL-A-1 | CPK03-R7-IFC | 2022-01-17 | 4
MP-OH-S-1 | CPK03-R7-IFC | 2022-01-17 | 4
MP-OH-S-5 | CPK03-R7-IFC | 2022-01-17 | 5
MP-RS-G-1 | CPK03-R7-IFC | 2022-01-17 | 5
MP-RS-S-3 | CPK03-R7-IFC | 2022-01-17 | 4
MP-SS-S-2 | CPK03-R7-IFC | 2022-01-17 | 5
MP-VB-A-2 | CPK03-R7-IFC | 2022-01-17 | 5
MP-VB-S-3 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-2024 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-2025 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2026 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2027 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2028 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-2029 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2031 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2032 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-2033 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2034 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2035 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2036 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2037 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2040 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2041 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2042 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-2043 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2044 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-2045 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2046 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2048 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2051 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2052 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2053 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2054 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2055 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2056 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2057 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2058 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2059 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2060 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2061 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2062 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2063 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2064 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2065 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2066 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2067 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2068 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2069 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2070 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2071 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2072 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2073 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2074 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2075 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2076 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2077 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2078 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2079 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2080 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2081 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2082 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2083 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2084 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2085 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2086 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2087 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2088 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2089 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2090 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2091 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2092 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2093 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2094 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2095 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2097 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2100 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2102 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2105 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2106 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2107 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2108 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2109 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2110 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2111 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2112 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2113 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2114 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2118 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2120 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2126 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2127 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2128 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2129 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2131 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2136 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2137 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2138 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2139 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2140 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2141 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2142 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2143 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2144 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2147 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2148 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2149 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2150 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2151 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2157 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2158 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2160 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2161 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2164 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2165 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2166 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2168 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2169 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2170 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2171 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2172 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2173 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2174 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2175 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2177 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2178 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2179 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2182 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2184 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2185 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-2503 | CPK03-R7-IFC | 2022-01-17 | 5
RA-ST-3000 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-3001 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-3002 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-3008 | CPK03-R7-IFC | 2022-01-17 | 8
RA-ST-4000 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-4001 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-4002 | CPK03-R7-IFC | 2022-01-17 | 9
RA-ST-4003 | CPK03-R7-IFC | 2022-01-17 | 9
ISAT-MP-AT-CS-U1-B | CPK03-R8-IFC | 2022-01-22 | 6
ISAT-MP-AT-CS-U2-B | CPK03-R8-IFC | 2022-01-22 | 6
ISAT-MP-AT-PS-A1-U | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-CS-A1-I-PI | CPK03-R8-IFC | 2022-01-22 | 6
ISAT-MP-BM-CS-A1-I-VB | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-CS-A1-U | CPK03-R8-IFC | 2022-01-22 | 6
ISAT-MP-BM-CS-G1-I-PI | CPK03-R8-IFC | 2022-01-22 | 6
ISAT-MP-BM-CS-G1-I-VB | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-CS-G1-U | CPK03-R8-IFC | 2022-01-22 | 6
ISAT-MP-BM-CS-G2-I-PI | CPK03-R8-IFC | 2022-01-22 | 6
ISAT-MP-BM-CS-G2-I-VB | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-BM-CS-G7-U | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-BM-CS-S1-I-PI | CPK03-R8-IFC | 2022-01-22 | 6
ISAT-MP-BM-CS-S1-U | CPK03-R8-IFC | 2022-01-22 | 6
ISAT-MP-BM-CS-S3-I-PI | CPK03-R8-IFC | 2022-01-22 | 6
ISAT-MP-BM-PS-A1-U | CPK03-R8-IFC | 2022-01-22 | 6
ISAT-MP-BM-PS-G1-U | CPK03-R8-IFC | 2022-01-22 | 6
ISAT-MP-BM-PS-S1-U | CPK03-R8-IFC | 2022-01-22 | 6
ISAT-MP-BM-SS-A1-U-VB | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-SS-A2-I-VB | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-BM-SS-A2-U-VB | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-SS-A3-I-VB | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-SS-A3-U-VB | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-SS-A5-I-VB | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-SS-A5-U-VB | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-SS-A7-I-VB | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-SS-A7-U | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-BM-SS-G1-I-VB | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-SS-G1-U-VB | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-SS-G2-I-VB | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-SS-G2-U-VB | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-SS-G3-I-VB | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-SS-G3-U-VB | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-FM-CS-S1-I-VB | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-FM-SS-S1-U | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-OH-CS-S1-I | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-OH-CS-S2-I-PI | CPK03-R8-IFC | 2022-01-22 | 6
ISAT-MP-OH-CS-S2-I-VB | CPK03-R8-IFC | 2022-01-22 | 6
ISAT-MP-RS-CS-A1-I-VB | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-RS-CS-A1-U | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-RS-CS-A1-U-VB | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-RS-SS-S1-U | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-SS-CS-L1-B-VB | CPK03-R8-IFC | 2022-01-22 | 6
MP-AT-G-1 | CPK03-R8-IFC | 2022-01-22 | 5
MP-BM-A-1 | CPK03-R8-IFC | 2022-01-22 | 6
MP-BM-G-1 | CPK03-R8-IFC | 2022-01-22 | 6
MP-VB-S-1 | CPK03-R8-IFC | 2022-01-22 | 6
MP-VB-S-2 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-0001 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-0002 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-0003 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-0004 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-0005 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-0006 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-0007 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-0008 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-0009 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-0010 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-0011 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-0012 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-0013 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-0014 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-0015 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-0016 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-0017 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-0018 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-0020 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-0021 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-0022 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-0500 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-0501 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-0502 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-0503 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-0504 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-0505 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-0506 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-1000 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-1001 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-1002 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-1003 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-1004 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-1008 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-1009 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-1011 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2000 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-2004 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2005 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2006 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-2007 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-2008 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-2009 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2010 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2011 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2012 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-2013 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-2014 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-2015 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-2016 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-2017 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2018 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2019 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2020 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2022 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2023 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2024 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-2025 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2026 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2027 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2028 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-2029 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2031 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2032 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-2033 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2034 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2035 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2036 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2037 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2040 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2041 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2042 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-2043 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2044 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-2045 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2046 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2048 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2051 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2052 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2053 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2054 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2055 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2056 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2057 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2058 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2059 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2060 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2061 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2062 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2063 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2064 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2065 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2066 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2067 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2068 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2069 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2070 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2071 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2072 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2073 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2074 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2075 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2076 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2077 | CPK03-R8-IFC | 2022-01-22 | 8
MS1-SS-2FA-4006 | CPK03-R8-IFC | 2022-01-22 | 1
MS1-SS-2FA-4007 | CPK03-R8-IFC | 2022-01-22 | 1
MS1-SS-2FA-4008 | CPK03-R8-IFC | 2022-01-22 | 1
MS1-S0-0010 | CPK03-R8-IFC | 2022-01-22 | 8
MS1-S0-1SA-4002 | CPK03-R8-IFC | 2022-01-22 | 1
MS1-SS-1SF-C0000 | CPK03-R8-IFC | 2022-01-22 | 3
MS1-SS-1SF-4001 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-SS-1SJ-4000 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-S0-1SD-4000 | CPK03-R8-IFC | 2022-01-22 | 1
MS1-SS-2FG-C02B0 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-SS-2FK-C02B0 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-S0-6218 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-S0-6260 | CPK03-R8-IFC | 2022-01-22 | 1
MS1-AC-2FA-A0D00 | CPK03-R8-IFC | 2022-01-22 | 3
MS1-AC-2FA-B0000 | CPK03-R8-IFC | 2022-01-22 | 4
MS1-AC-2FA-C0000 | CPK03-R8-IFC | 2022-01-22 | 3
MS1-AC-2FA-D0000 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-AC-2FH-4001 | CPK03-R8-IFC | 2022-01-22 | 4
MS1-AC-2FH-B0000 | CPK03-R8-IFC | 2022-01-22 | 5
MS1-AC-2FH-B0000-S | CPK03-R8-IFC | 2022-01-22 | 5
MS1-AC-2FH-B0D00-S | CPK03-R8-IFC | 2022-01-22 | 4
MS1-AC-2FH-C0000 | CPK03-R8-IFC | 2022-01-22 | 4
MS1-AC-2FH-C0000-S | CPK03-R8-IFC | 2022-01-22 | 4
MS1-AC-2FH-D0000 | CPK03-R8-IFC | 2022-01-22 | 4
MS1-AC-2FH-D0000-S | CPK03-R8-IFC | 2022-01-22 | 4
MS1-AC-2FI-4002 | CPK03-R8-IFC | 2022-01-22 | 3
MS1-AC-2FI-B0C00-S | CPK03-R8-IFC | 2022-01-22 | 3
MS1-AC-2FN-A0D00 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-AC-2FN-B0000 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-AC-2FN-C0000 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-AI-0107 | CPK03-R8-IFC | 2022-01-22 | 4
MS1-AR-2FB-A0D00 | CPK03-R8-IFC | 2022-01-22 | 3
MS1-AR-2FB-B0000 | CPK03-R8-IFC | 2022-01-22 | 3
MS1-AR-2FB-C0000 | CPK03-R8-IFC | 2022-01-22 | 3
MS1-AR-2FB-D0000 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-AW-1SA-C0000-D | CPK03-R8-IFC | 2022-01-22 | 3
MS1-AW-2FA-A0D00 | CPK03-R8-IFC | 2022-01-22 | 4
MS1-AW-2FA-B0000 | CPK03-R8-IFC | 2022-01-22 | 4
MS1-AW-2FA-C0000 | CPK03-R8-IFC | 2022-01-22 | 3
MS1-AW-2FA-D0000 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-AW-2FA-D0000-D | CPK03-R8-IFC | 2022-01-22 | 2
MS1-AW-6115 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-AW-6116 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-AW-6117 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-AW-6118 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-AW-6119 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-AW-6120 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-AW-6121 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-AW-6122 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-AW-6123 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-AW-6124 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-AZ-2FA-A0D00 | CPK03-R8-IFC | 2022-01-22 | 3
MS1-117-MW-A01 | CPK03-R8-IFC | 2022-01-22 | 1
MS1-117-MW-A01-D | CPK03-R8-IFC | 2022-01-22 | 1
MS1-102-D0-A05 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-102-D0-A07 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-102-D0-A08 | CPK03-R8-IFC | 2022-01-22 | 2
RA-AR-D1606 | CPK03-R8-IFC | 2022-01-22 | 3
RA-AR-D1619 | CPK03-R8-IFC | 2022-01-22 | 1
RA-AR-D1705 | CPK03-R8-IFC | 2022-01-22 | 3
RA-AR-D1713 | CPK03-R8-IFC | 2022-01-22 | 3
RA-AR-D1714 | CPK03-R8-IFC | 2022-01-22 | 3
RA-AR-D1715 | CPK03-R8-IFC | 2022-01-22 | 3
RA-AR-D1808 | CPK03-R8-IFC | 2022-01-22 | 3
RA-AR-D1912 | CPK03-R8-IFC | 2022-01-22 | 3
RA-AR-D1915 | CPK03-R8-IFC | 2022-01-22 | 3
RA-AR-D2500 | CPK03-R8-IFC | 2022-01-22 | 3
RA-AR-D2506 | CPK03-R8-IFC | 2022-01-22 | 3
MS1-A0-0700 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0701 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0702 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0703 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0704 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0705 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0706 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0707 | CPK03-R8-IFC | 2022-01-22 | 1
MS1-A0-0708 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0709 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0710 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0711 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0712 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0713 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0714 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0715 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0716 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0717 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0718 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0719 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0720 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0721 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0722 | CPK03-R8-IFC | 2022-01-22 | 3
MS1-A0-0723 | CPK03-R8-IFC | 2022-01-22 | 3
MS1-A0-0724 | CPK03-R8-IFC | 2022-01-22 | 3
MS1-A0-0725 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0726 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0727 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0728 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0729 | CPK03-R8-IFC | 2022-01-22 | 1
MS1-A0-0730 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0731 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0732 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0733 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0734 | CPK03-R8-IFC | 2022-01-22 | 1
MS1-A0-0735 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0736 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0737 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0738 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0739 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0740 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0741 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0742 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0743 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0744 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0745 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0746 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0747 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0748 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0749 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0750 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0751 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0752 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0753 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0754 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0755 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0756 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0757 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0758 | CPK03-R8-IFC | 2022-01-22 | 1
MS1-A0-0759 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0760 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0761 | CPK03-R8-IFC | 2022-01-22 | 2
MS1-A0-0762 | CPK03-R8-IFC | 2022-01-22 | 1
MS1-A0-0763 | CPK03-R8-IFC | 2022-01-22 | 1
MS1-A0-0764 | CPK03-R8-IFC | 2022-01-22 | 1
MS1-A0-0765 | CPK03-R8-IFC | 2022-01-22 | 1
MS1-A0-0766 | CPK03-R8-IFC | 2022-01-22 | 1
ISAT-MP-AT-NA-L1-B-VB | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-AT-NA-L3-B-VB | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-AT-CS-G1-B | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-AT-CS-G2-B | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-AT-CS-G3-B | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-AT-CS-G4-B | CPK03-R8-IFC | 2022-01-22 | 3
ISAT-MP-AT-CS-A1-B | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-AT-NA-A1-B | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-AT-NA-A2-B | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-AT-CS-A3-B | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-AT-CS-A4-B | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-AT-NA-U1-B | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-AT-NA-U2-B | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-AT-NA-U3-B | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-AT-NA-U4-B | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-AT-NA-U5-B | CPK03-R8-IFC | 2022-01-22 | 3
ISAT-MP-BM-PF-G1-B-FL | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-BM-PF-A1-B-FL | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2078 | CPK03-R8-IFC | 2022-01-22 | 8
ISAT-MP-BM-SS-A1-I-PI | CPK03-R8-IFC | 2022-01-22 | 3
ISAT-MP-BM-CS-S1-I-VB | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-CS-S1-U-VB | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-SS-S1-I-VB | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-SS-S1-U-VB | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2079 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2080 | CPK03-R8-IFC | 2022-01-22 | 8
ISAT-MP-BM-CS-A2-I-VB | CPK03-R8-IFC | 2022-01-22 | 3
ISAT-MP-BM-CS-A4-I-VB | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-SS-A4-I-VB | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-BM-SS-A4-U-VB | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2081 | CPK03-R8-IFC | 2022-01-22 | 8
ISAT-MP-BM-CS-S1-I | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-BM-PF-S1-I | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-BM-PF-S1-U | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-BM-PS-S1-I | CPK03-R8-IFC | 2022-01-22 | 3
ISAT-MP-BM-SS-S1-U | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-BM-CS-S7-U | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-BM-CS-G1-I | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-BM-CU-G1-U | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-BM-PF-G1-I | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-BM-PF-G1-U | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-BM-PS-G1-I | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-BM-SS-G1-U | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-SS-G1-I | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-CS-G2-U | CPK03-R8-IFC | 2022-01-22 | 3
ISAT-MP-BM-SS-G2-U | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-CS-G3-U | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-SS-G3-U | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-CS-A1-I | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2082 | CPK03-R8-IFC | 2022-01-22 | 8
ISAT-MP-BM-CU-A1-U | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-BM-PF-A1-I | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-BM-PF-A1-U | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-BM-PS-A1-I | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-BM-SS-A1-U | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-SS-A1-I | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-PF-A2-I | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-BM-PF-A2-U | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-BM-PS-A2-U | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-BM-SS-A2-U | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-CS-A4-U | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-SS-A4-I | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-BM-SS-A4-U | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-CS-A6-U | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-BM-SS-A6-U | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-BM-CS-A7-U | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-BM-CS-A8-U | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-OH-PF-S1-B-FL | CPK03-R8-IFC | 2022-01-22 | 3
RA-ST-2083 | CPK03-R8-IFC | 2022-01-22 | 8
ISAT-MP-OH-SS-S2-U-VB | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-OH-SS-S2-I-VB | CPK03-R8-IFC | 2022-01-22 | 3
ISAT-MP-OH-CS-S3-I-VB | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-OH-CS-S1-U | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-OH-PF-S1-I | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-OH-PF-S1-U | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-OH-PS-S1-U | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-OH-PS-S1-I | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-OH-SS-S1-U | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-OH-SS-S1-I | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-OH-PS-G1-U | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-OH-PF-G2-I | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-OH-PF-G2-U | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-OH-PS-G2-U | CPK03-R8-IFC | 2022-01-22 | 3
ISAT-MP-OH-SS-G2-U | CPK03-R8-IFC | 2022-01-22 | 3
ISAT-MP-OH-PF-A2-I | CPK03-R8-IFC | 2022-01-22 | 3
ISAT-MP-OH-PF-A2-U | CPK03-R8-IFC | 2022-01-22 | 3
ISAT-MP-OH-SS-A2-U | CPK03-R8-IFC | 2022-01-22 | 3
ISAT-MP-OH-PF-A3-U | CPK03-R8-IFC | 2022-01-22 | 3
ISAT-MP-OH-SS-A3-U | CPK03-R8-IFC | 2022-01-22 | 3
ISAT-MP-OH-NA-U1-B | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-RS-CS-S1-U | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-RS-PF-S1-U | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-RS-CS-G2-I | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-RS-SS-G2-U | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2084 | CPK03-R8-IFC | 2022-01-22 | 8
ISAT-MP-RS-CS-A2-I-VB | CPK03-R8-IFC | 2022-01-22 | 3
ISAT-MP-RS-CS-A1-I | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-RS-PF-A1-U | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-RS-SS-A1-U | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-SS-SS-L2-B-VB | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-SS-CS-L1-B | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-SS-CS-L2-B | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-SS-CS-L3-B | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-SS-NA-U1-B | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-SS-NA-U2-B | CPK03-R8-IFC | 2022-01-22 | 5
ISAT-MP-SS-NA-U3-B | CPK03-R8-IFC | 2022-01-22 | 3
ISAT-MP-SS-NA-U4-B | CPK03-R8-IFC | 2022-01-22 | 3
ISAT-MP-WM-NA-W1-B | CPK03-R8-IFC | 2022-01-22 | 4
ISAT-MP-WM-NA-W2-B | CPK03-R8-IFC | 2022-01-22 | 4
AT-VB-A-1 | CPK03-R8-IFC | 2022-01-22 | 5
MP-AT-A-2 | CPK03-R8-IFC | 2022-01-22 | 4
MP-BM-A-6 | CPK03-R8-IFC | 2022-01-22 | 5
MP-BM-A-7 | CPK03-R8-IFC | 2022-01-22 | 4
MP-BM-A-8 | CPK03-R8-IFC | 2022-01-22 | 4
MP-BM-A-9 | CPK03-R8-IFC | 2022-01-22 | 3
MP-BM-G-3 | CPK03-R8-IFC | 2022-01-22 | 3
MP-FL-A-1 | CPK03-R8-IFC | 2022-01-22 | 4
MP-OH-S-1 | CPK03-R8-IFC | 2022-01-22 | 4
MP-OH-S-3 | CPK03-R8-IFC | 2022-01-22 | 3
MP-OH-S-5 | CPK03-R8-IFC | 2022-01-22 | 5
MP-RS-G-1 | CPK03-R8-IFC | 2022-01-22 | 5
MP-RS-S-3 | CPK03-R8-IFC | 2022-01-22 | 4
MP-SS-S-2 | CPK03-R8-IFC | 2022-01-22 | 5
MP-VB-A-2 | CPK03-R8-IFC | 2022-01-22 | 5
MP-VB-S-3 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2501 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2502 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2504 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2505 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2506 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2507 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2508 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2509 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2510 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2511 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2512 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2513 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2514 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2515 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2516 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2517 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2518 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2519 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2520 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2521 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2522 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2523 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2524 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2525 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2526 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2527 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2528 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2529 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2530 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2531 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2532 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2533 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2534 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2535 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2536 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2537 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2538 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2539 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2540 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2541 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2542 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2543 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2544 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2545 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2546 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2547 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2548 | CPK03-R8-IFC | 2022-01-22 | 3
RA-ST-2549 | CPK03-R8-IFC | 2022-01-22 | 3
RA-ST-2550 | CPK03-R8-IFC | 2022-01-22 | 3
RA-ST-2551 | CPK03-R8-IFC | 2022-01-22 | 3
RA-ST-2552 | CPK03-R8-IFC | 2022-01-22 | 3
RA-ST-2553 | CPK03-R8-IFC | 2022-01-22 | 3
RA-ST-2554 | CPK03-R8-IFC | 2022-01-22 | 3
RA-ST-2555 | CPK03-R8-IFC | 2022-01-22 | 3
RA-ST-2556 | CPK03-R8-IFC | 2022-01-22 | 3
RA-ST-2557 | CPK03-R8-IFC | 2022-01-22 | 3
RA-ST-2558 | CPK03-R8-IFC | 2022-01-22 | 3
RA-ST-2559 | CPK03-R8-IFC | 2022-01-22 | 3
RA-ST-2560 | CPK03-R8-IFC | 2022-01-22 | 3
RA-ST-2561 | CPK03-R8-IFC | 2022-01-22 | 3
RA-ST-2562 | CPK03-R8-IFC | 2022-01-22 | 3
RA-ST-2563 | CPK03-R8-IFC | 2022-01-22 | 3
RA-ST-2564 | CPK03-R8-IFC | 2022-01-22 | 3
RA-ST-2565 | CPK03-R8-IFC | 2022-01-22 | 3
RA-ST-2566 | CPK03-R8-IFC | 2022-01-22 | 3
RA-ST-2567 | CPK03-R8-IFC | 2022-01-22 | 3
RA-ST-2568 | CPK03-R8-IFC | 2022-01-22 | 3
RA-ST-2569 | CPK03-R8-IFC | 2022-01-22 | 3
RA-ST-2570 | CPK03-R8-IFC | 2022-01-22 | 3
RA-ST-2571 | CPK03-R8-IFC | 2022-01-22 | 3
RA-ST-2572 | CPK03-R8-IFC | 2022-01-22 | 2
RA-ST-2573 | CPK03-R8-IFC | 2022-01-22 | 2
RA-ST-2574 | CPK03-R8-IFC | 2022-01-22 | 2
RA-ST-2575 | CPK03-R8-IFC | 2022-01-22 | 2
RA-ST-2576 | CPK03-R8-IFC | 2022-01-22 | 2
RA-ST-2577 | CPK03-R8-IFC | 2022-01-22 | 2
RA-ST-2578 | CPK03-R8-IFC | 2022-01-22 | 2
RA-ST-2579 | CPK03-R8-IFC | 2022-01-22 | 2
RA-ST-2580 | CPK03-R8-IFC | 2022-01-22 | 2
RA-ST-2581 | CPK03-R8-IFC | 2022-01-22 | 2
RA-ST-2582 | CPK03-R8-IFC | 2022-01-22 | 2
RA-ST-2583 | CPK03-R8-IFC | 2022-01-22 | 2
RA-ST-2085 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2086 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-0019 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2087 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-1005 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-1006 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-2088 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-1010 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-1012 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-1013 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-1014 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-1015 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-1016 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-1017 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-1018 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-1022 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-1023 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-1024 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-1025 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-1026 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-1027 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-1028 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2001 | CPK03-R8-IFC | 2022-01-22 | 7
RA-ST-2002 | CPK03-R8-IFC | 2022-01-22 | 7
RA-ST-2003 | CPK03-R8-IFC | 2022-01-22 | 7
RA-ST-2089 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2021 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2090 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2030 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2091 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2092 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2047 | CPK03-R8-IFC | 2022-01-22 | 7
RA-ST-2049 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2050 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2093 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2094 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2095 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2097 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2096 | CPK03-R8-IFC | 2022-01-22 | 7
RA-ST-2098 | CPK03-R8-IFC | 2022-01-22 | 7
RA-ST-2099 | CPK03-R8-IFC | 2022-01-22 | 7
RA-ST-2101 | CPK03-R8-IFC | 2022-01-22 | 7
RA-ST-2100 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2103 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-2104 | CPK03-R8-IFC | 2022-01-22 | 7
RA-ST-2115 | CPK03-R8-IFC | 2022-01-22 | 7
RA-ST-2116 | CPK03-R8-IFC | 2022-01-22 | 7
RA-ST-2117 | CPK03-R8-IFC | 2022-01-22 | 7
RA-ST-2102 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2119 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2121 | CPK03-R8-IFC | 2022-01-22 | 7
RA-ST-2122 | CPK03-R8-IFC | 2022-01-22 | 7
RA-ST-2130 | CPK03-R8-IFC | 2022-01-22 | 7
RA-ST-2135 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2105 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2145 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2106 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2163 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2167 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-2107 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2176 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-2180 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2181 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-2183 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-2108 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2186 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2187 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2188 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2189 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2190 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2191 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2192 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-2193 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2194 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2195 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2196 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2197 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-2198 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2199 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-2200 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-2201 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-2203 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2204 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-2205 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-2206 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-2207 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-2208 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-2209 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-2210 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-2211 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2212 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2213 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2214 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2215 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2216 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2217 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2218 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-2219 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-2220 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-2221 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2222 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-2223 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-2225 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2226 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2227 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2228 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2229 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2230 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-2231 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2232 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2233 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2234 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2235 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2237 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2238 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2239 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-2240 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2241 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2242 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-2243 | CPK03-R8-IFC | 2022-01-22 | 6
RA-ST-2244 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2245 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2246 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2247 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2248 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2249 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2250 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2251 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2252 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2253 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2254 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2255 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2256 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2257 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2258 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2260 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2261 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2262 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2263 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2264 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2265 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2266 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2267 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2268 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2269 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2270 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2277 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2278 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2279 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2280 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2281 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2282 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2283 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2284 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-2285 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2286 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2288 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2289 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2291 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2292 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2293 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2294 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2295 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2296 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2297 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2298 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2299 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-3009 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-4005 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-4006 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-4007 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-4008 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-4009 | CPK03-R8-IFC | 2022-01-22 | 4
RA-ST-4010 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-4011 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-4012 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-2109 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2110 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2111 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2112 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2113 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2114 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2118 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2120 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2126 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2127 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2128 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2129 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2131 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2136 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2137 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2138 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2139 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2140 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2141 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2142 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2143 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2144 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2147 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2148 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2149 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2150 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2151 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2157 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2158 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2160 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2161 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2164 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2165 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2166 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2168 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2169 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2170 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2171 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2172 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2173 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2174 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2175 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2177 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2178 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2179 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2182 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2184 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2185 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-2503 | CPK03-R8-IFC | 2022-01-22 | 5
RA-ST-3000 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-3001 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-3002 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-3008 | CPK03-R8-IFC | 2022-01-22 | 8
RA-ST-4000 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-4001 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-4002 | CPK03-R8-IFC | 2022-01-22 | 9
RA-ST-4003 | CPK03-R8-IFC | 2022-01-22 | 9
ISAT-MP-AT-CS-U1-B | CPK03-R9-IFC | 2022-02-03 | 6
ISAT-MP-AT-CS-U2-B | CPK03-R9-IFC | 2022-02-03 | 6
ISAT-MP-AT-PS-A1-U | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-CS-A1-I-PI | CPK03-R9-IFC | 2022-02-03 | 6
ISAT-MP-BM-CS-A1-I-VB | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-CS-A1-U | CPK03-R9-IFC | 2022-02-03 | 6
ISAT-MP-BM-CS-G1-I-PI | CPK03-R9-IFC | 2022-02-03 | 6
ISAT-MP-BM-CS-G1-I-VB | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-CS-G1-U | CPK03-R9-IFC | 2022-02-03 | 6
ISAT-MP-BM-CS-G2-I-PI | CPK03-R9-IFC | 2022-02-03 | 6
ISAT-MP-BM-CS-G2-I-VB | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-BM-CS-G7-U | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-BM-CS-S1-I-PI | CPK03-R9-IFC | 2022-02-03 | 6
ISAT-MP-BM-CS-S1-U | CPK03-R9-IFC | 2022-02-03 | 6
ISAT-MP-BM-CS-S3-I-PI | CPK03-R9-IFC | 2022-02-03 | 6
ISAT-MP-BM-PS-A1-U | CPK03-R9-IFC | 2022-02-03 | 6
ISAT-MP-BM-PS-G1-U | CPK03-R9-IFC | 2022-02-03 | 6
ISAT-MP-BM-PS-S1-U | CPK03-R9-IFC | 2022-02-03 | 6
ISAT-MP-BM-SS-A1-U-VB | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-SS-A2-I-VB | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-BM-SS-A2-U-VB | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-SS-A3-I-VB | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-SS-A3-U-VB | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-SS-A5-I-VB | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-SS-A5-U-VB | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-SS-A7-I-VB | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-SS-A7-U | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-BM-SS-G1-I-VB | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-SS-G1-U-VB | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-SS-G2-I-VB | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-SS-G2-U-VB | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-SS-G3-I-VB | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-SS-G3-U-VB | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-FM-CS-S1-I-VB | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-FM-SS-S1-U | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-OH-CS-S1-I | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-OH-CS-S2-I-PI | CPK03-R9-IFC | 2022-02-03 | 6
ISAT-MP-OH-CS-S2-I-VB | CPK03-R9-IFC | 2022-02-03 | 6
ISAT-MP-RS-CS-A1-I-VB | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-RS-CS-A1-U | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-RS-CS-A1-U-VB | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-RS-SS-S1-U | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-SS-CS-L1-B-VB | CPK03-R9-IFC | 2022-02-03 | 6
MP-AT-G-1 | CPK03-R9-IFC | 2022-02-03 | 5
MP-BM-A-1 | CPK03-R9-IFC | 2022-02-03 | 6
MP-BM-G-1 | CPK03-R9-IFC | 2022-02-03 | 6
MP-VB-S-1 | CPK03-R9-IFC | 2022-02-03 | 6
MP-VB-S-2 | CPK03-R9-IFC | 2022-02-03 | 6
MXR2X57B | CPK03-R9-IFC | 2022-02-03 | 2
RA-ST-0001 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-0002 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-0003 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-0004 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-0005 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-0006 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-0007 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-0008 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-0009 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-0010 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-0011 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-0012 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-0013 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-0014 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-0015 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-0016 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-0017 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-0018 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-0020 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-0021 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-0022 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-0500 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-0501 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-0502 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-0503 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-0504 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-0505 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-0506 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-1000 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-1001 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-1002 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-1003 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-1004 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-1008 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-1009 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-1011 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2000 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-2004 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2005 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2006 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-2007 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-2008 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-2009 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2010 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2011 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2012 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-2013 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-2014 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-2015 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-2016 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-2017 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2018 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2019 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2020 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2022 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2023 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2024 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-2025 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2026 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2027 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2028 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-2029 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2031 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2032 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-2033 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2034 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2035 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2036 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2037 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2040 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2041 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2042 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-2043 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2044 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-2045 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2046 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2048 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2051 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2052 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2053 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2054 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2055 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2056 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2057 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2058 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2059 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2060 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2061 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2062 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2063 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2064 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2065 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2066 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2067 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2068 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2069 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2070 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2071 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2072 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2073 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2074 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2075 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2076 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2077 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2078 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2079 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2080 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2081 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2082 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2083 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2084 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2085 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2086 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2087 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2088 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2089 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2090 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2091 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2092 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2093 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2094 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2095 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2097 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2100 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2102 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2105 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2106 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2107 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2108 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2109 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2110 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2111 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2112 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2113 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2114 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2118 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2120 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2126 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2127 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2128 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2129 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2131 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2136 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2137 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2138 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2139 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2140 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2141 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2142 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2143 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2144 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2147 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2148 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2149 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2150 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2151 | CPK03-R9-IFC | 2022-02-03 | 8
AT-VB-A-1 | CPK03-R9-IFC | 2022-02-03 | 5
CDXR1X28A | CPK03-R9-IFC | 2022-02-03 | 2
CMXD1AB53A | CPK03-R9-IFC | 2022-02-03 | 2
CMXD1K52A | CPK03-R9-IFC | 2022-02-03 | 2
CMXD1M53A | CPK03-R9-IFC | 2022-02-03 | 2
CMXD1M55A | CPK03-R9-IFC | 2022-02-03 | 2
CMXD1Q53A | CPK03-R9-IFC | 2022-02-03 | 2
CMXD1Q55A | CPK03-R9-IFC | 2022-02-03 | 2
CMXD1T53A | CPK03-R9-IFC | 2022-02-03 | 2
CMXD1U53A | CPK03-R9-IFC | 2022-02-03 | 2
CMXD2S57B | CPK03-R9-IFC | 2022-02-03 | 2
CMXD2S57C | CPK03-R9-IFC | 2022-02-03 | 2
CMXD2S57D | CPK03-R9-IFC | 2022-02-03 | 1
CMXL2G57A | CPK03-R9-IFC | 2022-02-03 | 2
CMXL2R50A | CPK03-R9-IFC | 2022-02-03 | 1
CMXL2Z50A | CPK03-R9-IFC | 2022-02-03 | 2
CMXR0N56A | CPK03-R9-IFC | 2022-02-03 | 1
CMXR0Z56A | CPK03-R9-IFC | 2022-02-03 | 1
CMXR1AA56A | CPK03-R9-IFC | 2022-02-03 | 1
CMXR1AA56B | CPK03-R9-IFC | 2022-02-03 | 1
CMXR1AB53B | CPK03-R9-IFC | 2022-02-03 | 2
CMXR1M53B | CPK03-R9-IFC | 2022-02-03 | 2
CMXR1N56A | CPK03-R9-IFC | 2022-02-03 | 2
CMXR1Q53B | CPK03-R9-IFC | 2022-02-03 | 3
CMXR1Q56A | CPK03-R9-IFC | 2022-02-03 | 1
CMXR1Q56B | CPK03-R9-IFC | 2022-02-03 | 1
CMXR1U53B | CPK03-R9-IFC | 2022-02-03 | 3
CMXR2R50A | CPK03-R9-IFC | 2022-02-03 | 2
CMXR2R57B | CPK03-R9-IFC | 2022-02-03 | 1
CMXR2T50A | CPK03-R9-IFC | 2022-02-03 | 2
CMXR2Z50A | CPK03-R9-IFC | 2022-02-03 | 2
CMXR2Z57A | CPK03-R9-IFC | 2022-02-03 | 1
CMXR3W57A | CPK03-R9-IFC | 2022-02-03 | 2
CMXR4M57A | CPK03-R9-IFC | 2022-02-03 | 3
CMXR4N54C | CPK03-R9-IFC | 2022-02-03 | 2
CMXR4N57A | CPK03-R9-IFC | 2022-02-03 | 2
CMXR4Z54A | CPK03-R9-IFC | 2022-02-03 | 1
CMXR4Z56A | CPK03-R9-IFC | 2022-02-03 | 2
CPS-MXA | CPK03-R9-IFC | 2022-02-03 | 2
CPS-MXB | CPK03-R9-IFC | 2022-02-03 | 2
CPS-MXC | CPK03-R9-IFC | 2022-02-03 | 2
CPS-MXD | CPK03-R9-IFC | 2022-02-03 | 2
D-H-1840-LSS-MDP-H33 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1840-LSS-MDP-H34 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1840-LSS-MDP-H35 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-001-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-100-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-101-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-105-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-110-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-115-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-200-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-201-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-202-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-204-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-206-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-207-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-210-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-211-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-215-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-250-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-255-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-256-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-260-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-261-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-270-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-271-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-275-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-276-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-300-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-301-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-302-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-303-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-304-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-305-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-306-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-310-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-311-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-312-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-350-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-360-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-365-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-366-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-FIRE-375-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-LSS-MDP-F01 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-LSS-MDP-F02 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-LSS-MDP-F03 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-LSS-MDP-F04 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-LSS-MDP-F05 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1841-LSS-MDP-F06 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1842-LSS-MDP-H09-D-H-1842-LSS-MDP-H09 | CPK03-R9-IFC | 2022-02-03 | 1
D-H-1842-LSS-MDP-H52A-D-H-1842-LSS-MDP-H52A | CPK03-R9-IFC | 2022-02-03 | 1
D-H-1842-LSS-MDP-H52-D-H-1842-LSS-MDP-H52 | CPK03-R9-IFC | 2022-02-03 | 1
D-H-1842-LSS-MDP-H70A-Layout1 | CPK03-R9-IFC | 2022-02-03 | 1
D-H-1842-LSS-MDP-H70-D-H-1842-LSS-MDP-H70 | CPK03-R9-IFC | 2022-02-03 | 1
D-H-1842-LSS-MDP-H71-D-H-1842-LSS-MDP-H71 | CPK03-R9-IFC | 2022-02-03 | 1
D-H-1842-LSS-MDP-H72A-D-H-1842-LSS-MDP-H72A | CPK03-R9-IFC | 2022-02-03 | 1
D-H-1842-LSS-MDP-H72-D-H-1842-LSS-MDP-H72 | CPK03-R9-IFC | 2022-02-03 | 1
D-H-1842-TAS-100-MDP-D-H-1842-TAS-100-MDP | CPK03-R9-IFC | 2022-02-03 | 1
D-H-1842-TAS-200-MDP-D-H-1842-TAS-200-MDP | CPK03-R9-IFC | 2022-02-03 | 1
D-H-1842-TAS-201-MDP-D-H-1842-TAS-201-MDP | CPK03-R9-IFC | 2022-02-03 | 1
D-H-1842-TAS-202-MDP-D-H-1842-TAS-202-MDP | CPK03-R9-IFC | 2022-02-03 | 1
D-H-1842-TAS-203-MDP-D-H-1842-TAS-203-MDP | CPK03-R9-IFC | 2022-02-03 | 1
D-H-1844-HPM-001-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-HPM-320-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-HPM-322-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-HPM-323-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-HPM-325-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-HPM-326-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-HPM-327-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-HPM-328-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-HPM-329-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-HPM-330-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-HPM-538-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-HPM-539-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-HPM-540-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-HPM-585-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-HPM-703-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-HPM-704-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-HPM-705-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-HPM-707-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-HPM-708-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-HPM-711-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-HPM-713-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-HPM-714-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-HPM-715-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-HPM-716-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-HPM-717-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-HPM-718-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-HPM-719-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-HPM-725-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-HPM-726-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H01 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H02 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H03 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H05 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H06 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H07 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H08 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H15 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H16 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H20 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H21 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H22 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H23 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H24 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H25 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H26 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H27 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H30 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H31 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H32 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H33 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H34 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H35 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H50 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H50A | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H55 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H55A | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H55B | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H56 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H56A | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H56B | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H57 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H58 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H58A | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H58B | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H59 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H59A | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H60 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H60A | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H61 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H61A | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H61B | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H61C | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H62 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H62A | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H62B | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H63 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H63A | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H63B | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H64 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H64A | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H64B | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H80 | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1844-LSS-MDP-H80A | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1845-HPM-402-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1845-HPM-403-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1845-HPM-404-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1845-HPM-405-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1845-HPM-406-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1845-HPM-410-MDP | CPK03-R9-IFC | 2022-02-03 | 4
D-H-1845-HPM-411-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1846-EWS-100-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1846-EWS-201-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1846-EWS-202-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1846-EWS-204-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1846-EWS-205-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1846-EWS-301-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1846-FIRE-150-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1846-FIRE-151-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1846-FIRE-152-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1846-FIRE-155-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1846-FIRE-156-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1846-FIRE-157-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1846-FIRE-158-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1846-FIRE-160-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1846-FIRE-161-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1846-FIRE-162-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1846-FIRE-163-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1846-FIRE-164-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1846-FIRE-165-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1846-FIRE-166-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1846-FIRE-167-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1846-FIRE-168-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1846-FIRE-170-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1846-FIRE-171-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1846-FIRE-172-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1846-FIRE-173-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1846-FIRE-174-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-126-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-128-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-130-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-146-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-160-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-161-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-162-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-163-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-164E-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-164-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-164M-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-165E-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-165-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-165M-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-166-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-167-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-168-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-169-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-170-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-171-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-172-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-173-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-174-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-203-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-252E-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-252-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-252M-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-253-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-254-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-255-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-261-MDP | CPK03-R9-IFC | 2022-02-03 | 3
D-H-1848-HPM-270-MDP | CPK03-R9-IFC | 2022-02-03 | 3
DXR1T23G | CPK03-R9-IFC | 2022-02-03 | 2
DXR1Y23A | CPK03-R9-IFC | 2022-02-03 | 2
ISAT-MP-AT-CS-A1-B | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-AT-CS-A3-B | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-AT-CS-A4-B | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-AT-CS-G1-B | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-AT-CS-G2-B | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-AT-CS-G3-B | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-AT-CS-G4-B | CPK03-R9-IFC | 2022-02-03 | 3
ISAT-MP-AT-NA-A1-B | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-AT-NA-A2-B | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-AT-NA-L1-B | CPK03-R9-IFC | 2022-02-03 | 2
ISAT-MP-AT-NA-L1-B-VB | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-AT-NA-L3-B-VB | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-AT-NA-U1-B | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-AT-NA-U2-B | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-AT-NA-U3-B | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-AT-NA-U4-B | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-AT-NA-U5-B | CPK03-R9-IFC | 2022-02-03 | 3
ISAT-MP-AT-NA-U6-B | CPK03-R9-IFC | 2022-02-03 | 2
ISAT-MP-BM-CS-A1-I | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-2157 | CPK03-R9-IFC | 2022-02-03 | 8
ISAT-MP-BM-CS-A2-I-VB | CPK03-R9-IFC | 2022-02-03 | 3
ISAT-MP-BM-CS-A3-I-PI | CPK03-R9-IFC | 2022-02-03 | 2
ISAT-MP-BM-CS-A4-I-PI | CPK03-R9-IFC | 2022-02-03 | 2
ISAT-MP-BM-CS-A4-I-VB | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-CS-A4-U | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-CS-A5-I-PI | CPK03-R9-IFC | 2022-02-03 | 2
ISAT-MP-BM-CS-A6-U | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-BM-CS-A7-U | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-BM-CS-A8-U | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-BM-CS-G1-I | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-2158 | CPK03-R9-IFC | 2022-02-03 | 8
ISAT-MP-BM-CS-G2-U | CPK03-R9-IFC | 2022-02-03 | 3
ISAT-MP-BM-CS-G3-I-PI | CPK03-R9-IFC | 2022-02-03 | 2
ISAT-MP-BM-CS-G3-U | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-CS-G4-I-PI | CPK03-R9-IFC | 2022-02-03 | 2
ISAT-MP-BM-CS-S1-I | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-BM-CS-S1-I-VB | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-CS-S1-U-VB | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-CS-S7-U | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-BM-CU-A1-U | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-BM-CU-G1-U | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-BM-PF-A1-B-FL | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-BM-PF-A1-I | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-BM-PF-A1-U | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-BM-PF-A2-I | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-BM-PF-A2-U | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-BM-PF-A3-I | CPK03-R9-IFC | 2022-02-03 | 2
ISAT-MP-BM-PF-A3-U | CPK03-R9-IFC | 2022-02-03 | 2
ISAT-MP-BM-PF-G1-B-FL | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-BM-PF-G1-I | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-BM-PF-G1-U | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-BM-PF-S1-B-FL | CPK03-R9-IFC | 2022-02-03 | 2
ISAT-MP-BM-PF-S1-I | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-BM-PF-S1-U | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-BM-PS-A1-I | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-BM-PS-A2-U | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-BM-PS-G1-I | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-BM-PS-S1-I | CPK03-R9-IFC | 2022-02-03 | 3
ISAT-MP-BM-SS-A1-I | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-SS-A1-I-PI | CPK03-R9-IFC | 2022-02-03 | 3
ISAT-MP-BM-SS-A1-U | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2160 | CPK03-R9-IFC | 2022-02-03 | 8
ISAT-MP-BM-SS-A2-U | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-SS-A4-I | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-BM-SS-A4-I-VB | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-BM-SS-A4-U | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-SS-A4-U-VB | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2161 | CPK03-R9-IFC | 2022-02-03 | 8
ISAT-MP-BM-SS-A6-U | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-SS-A9-U | CPK03-R9-IFC | 2022-02-03 | 2
ISAT-MP-BM-SS-G1-I | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-SS-G1-U | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2164 | CPK03-R9-IFC | 2022-02-03 | 8
ISAT-MP-BM-SS-G2-U | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-SS-G3-U | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-SS-G9-U | CPK03-R9-IFC | 2022-02-03 | 2
ISAT-MP-BM-SS-S1-I-VB | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-SS-S1-U | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-BM-SS-S1-U-VB | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-BM-SS-S9-U | CPK03-R9-IFC | 2022-02-03 | 2
RA-ST-2165 | CPK03-R9-IFC | 2022-02-03 | 8
ISAT-MP-OH-CS-S1-U | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-OH-CS-S3-I-VB | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-OH-NA-U1-B | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-OH-PF-A2-I | CPK03-R9-IFC | 2022-02-03 | 3
ISAT-MP-OH-PF-A2-U | CPK03-R9-IFC | 2022-02-03 | 3
ISAT-MP-OH-PF-A3-U | CPK03-R9-IFC | 2022-02-03 | 3
ISAT-MP-OH-PF-G2-I | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-OH-PF-G2-U | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-OH-PF-S1-B-FL | CPK03-R9-IFC | 2022-02-03 | 3
ISAT-MP-OH-PF-S1-I | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-OH-PF-S1-U | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-OH-PS-G1-U | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-OH-PS-G2-U | CPK03-R9-IFC | 2022-02-03 | 3
ISAT-MP-OH-PS-S1-I | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-OH-PS-S1-U | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-OH-SS-A2-U | CPK03-R9-IFC | 2022-02-03 | 3
ISAT-MP-OH-SS-A3-U | CPK03-R9-IFC | 2022-02-03 | 3
ISAT-MP-OH-SS-G2-U | CPK03-R9-IFC | 2022-02-03 | 3
ISAT-MP-OH-SS-S1-I | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-OH-SS-S1-U | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-OH-SS-S2-I-VB | CPK03-R9-IFC | 2022-02-03 | 3
ISAT-MP-OH-SS-S2-U-VB | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-RS-CS-A1-I | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-2166 | CPK03-R9-IFC | 2022-02-03 | 8
ISAT-MP-RS-CS-A2-I-VB | CPK03-R9-IFC | 2022-02-03 | 3
ISAT-MP-RS-CS-G2-I | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-RS-CS-S1-U | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-RS-PF-A1-U | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-RS-PF-S1-U | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-RS-SS-A1-U | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-RS-SS-G2-U | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-SS-CS-L1-B | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-SS-CS-L2-B | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-SS-CS-L3-B | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-SS-NA-U1-B | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-SS-NA-U2-B | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-SS-NA-U3-B | CPK03-R9-IFC | 2022-02-03 | 3
ISAT-MP-SS-NA-U4-B | CPK03-R9-IFC | 2022-02-03 | 3
ISAT-MP-SS-SS-L2-B-VB | CPK03-R9-IFC | 2022-02-03 | 5
ISAT-MP-WM-NA-W1-B | CPK03-R9-IFC | 2022-02-03 | 4
ISAT-MP-WM-NA-W2-B | CPK03-R9-IFC | 2022-02-03 | 4
MP-AT-A-2 | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-2168 | CPK03-R9-IFC | 2022-02-03 | 8
MP-BM-A-6 | CPK03-R9-IFC | 2022-02-03 | 5
MP-BM-A-7 | CPK03-R9-IFC | 2022-02-03 | 4
MP-BM-A-8 | CPK03-R9-IFC | 2022-02-03 | 4
MP-BM-A-9 | CPK03-R9-IFC | 2022-02-03 | 3
MP-BM-G-3 | CPK03-R9-IFC | 2022-02-03 | 3
MP-FL-A-1 | CPK03-R9-IFC | 2022-02-03 | 4
MP-OH-S-1 | CPK03-R9-IFC | 2022-02-03 | 4
MP-OH-S-3 | CPK03-R9-IFC | 2022-02-03 | 3
MP-OH-S-5 | CPK03-R9-IFC | 2022-02-03 | 5
MP-RS-G-1 | CPK03-R9-IFC | 2022-02-03 | 5
MP-RS-S-3 | CPK03-R9-IFC | 2022-02-03 | 4
MP-SS-S-2 | CPK03-R9-IFC | 2022-02-03 | 5
MP-VB-A-2 | CPK03-R9-IFC | 2022-02-03 | 5
MP-VB-S-3 | CPK03-R9-IFC | 2022-02-03 | 5
MS1-133-D0-Z02 | CPK03-R9-IFC | 2022-02-03 | 3
MS1-147-D0-A01 | CPK03-R9-IFC | 2022-02-03 | 3
MS1-245-D0-A01 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-261-D0-B01 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-261-D0-B01-D | CPK03-R9-IFC | 2022-02-03 | 2
MS1-261-D0-Z01 | CPK03-R9-IFC | 2022-02-03 | 3
MS1-261-D0-Z01-D | CPK03-R9-IFC | 2022-02-03 | 3
MS1-299-D0-A01 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-299-D0-Z01 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-AC-2FH-B0000-S | CPK03-R9-IFC | 2022-02-03 | 5
MS1-AC-2FH-B0D00-S | CPK03-R9-IFC | 2022-02-03 | 4
MS1-AC-2FH-C0000-S | CPK03-R9-IFC | 2022-02-03 | 4
MS1-AC-2FH-D0000-S | CPK03-R9-IFC | 2022-02-03 | 4
MS1-AC-2FI-B0C00-S | CPK03-R9-IFC | 2022-02-03 | 3
MS1-AW-0BA-A0D00 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-AW-0BA-B0000 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-EE-0BA-B0000 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-ES-1250A | CPK03-R9-IFC | 2022-02-03 | 3
MS1-ES-1300 | CPK03-R9-IFC | 2022-02-03 | 3
MS1-ES-1301 | CPK03-R9-IFC | 2022-02-03 | 3
MS1-ES-1308 | CPK03-R9-IFC | 2022-02-03 | 3
MS1-ES-1314B | CPK03-R9-IFC | 2022-02-03 | 3
MS1-ES-1326B | CPK03-R9-IFC | 2022-02-03 | 3
MS1-ES-1344B | CPK03-R9-IFC | 2022-02-03 | 3
MS1-H0-5001 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-H0-5001-D | CPK03-R9-IFC | 2022-02-03 | 1
MS1-H0-5002 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-H0-5002-D | CPK03-R9-IFC | 2022-02-03 | 1
MS1-H0-5102 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-H0-5102-D | CPK03-R9-IFC | 2022-02-03 | 1
MS1-H0-5103 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-H0-5103-D | CPK03-R9-IFC | 2022-02-03 | 1
MS1-H0-5105-D | CPK03-R9-IFC | 2022-02-03 | 1
MS1-H0-5106-D | CPK03-R9-IFC | 2022-02-03 | 1
MS1-H0-5109 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-H0-5113 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-H0-6002 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-H0-6002-D | CPK03-R9-IFC | 2022-02-03 | 1
MS1-H0-6003 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-H0-6003-D | CPK03-R9-IFC | 2022-02-03 | 1
MS1-H0-6102 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-H0-6102-D | CPK03-R9-IFC | 2022-02-03 | 1
MS1-H0-6103 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-H0-6103-D | CPK03-R9-IFC | 2022-02-03 | 1
MS1-H0-6105-D | CPK03-R9-IFC | 2022-02-03 | 1
MS1-H0-6106-D | CPK03-R9-IFC | 2022-02-03 | 1
MS1-H0-6109 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-H0-6113 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HC-1SA-B0000 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-HC-1SA-C0000 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HF-0100 | CPK03-R9-IFC | 2022-02-03 | 3
MS1-HF-0101 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-HF-0102 | CPK03-R9-IFC | 2022-02-03 | 3
MS1-HF-0154 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-HF-0156 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HF-0157 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-HF-0158 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-HF-1081 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HF-1082 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-HF-1084 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-HF-1SA-B0000 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-HF-1SA-C0000 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-HF-1SA-D0000 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-HF-2FA-B0000 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HF-2FA-B0000-D | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HF-2FA-C0000 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-HF-2FA-C0000-D | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HF-2FA-D0000 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-HF-2FA-D0000-D | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HF-3000D | CPK03-R9-IFC | 2022-02-03 | 2
MS1-HF-3001B | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HF-3001C | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HF-5RA-B0000 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-HH-1001 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HH-1SB-B0000 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-HH-1SB-C0000 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HH-1SB-D0000 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HL-1SA-A0D00 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-0151 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-0151-D | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-0152 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-0152-D | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-0153 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-0153-D | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-0154 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-0154-D | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-0155 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-0155-D | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-0156 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-0156-D | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-0157 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-0157-D | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-0158 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-0158-D | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-0159 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-1057 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-1100 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-1101 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-1101-D | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-1107 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-1108 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-1SA-B0000 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-HS-1SA-C0000 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-1SA-D0000 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-2FA-B0000-D | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-2FB-B0000 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-2FB-C0000 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-2FB-D0000 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-3FA-B0000 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-3FA-C0000 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-4DA-B0000 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-4DA-C0000 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HS-5RA-B0000 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HW-1SA-B0000 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-HW-1SA-C0000 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HW-1SA-D0000 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HW-2FA-B0000 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HW-2FA-C0000 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-HW-2FA-D0000 | CPK03-R9-IFC | 2022-02-03 | 1
MS1-IE-0BA-B0000 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-IE-1SA-B0000 | CPK03-R9-IFC | 2022-02-03 | 4
MS1-IE-1SA-C0000 | CPK03-R9-IFC | 2022-02-03 | 5
MS1-IE-2FA-C0000 | CPK03-R9-IFC | 2022-02-03 | 4
MS1-PE-0211 | CPK03-R9-IFC | 2022-02-03 | 4
MS1-PE-0BA-A0D00 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-PE-0BA-B0000 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-S0-0BA-B0400 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-S0-0BA-B0400-D | CPK03-R9-IFC | 2022-02-03 | 2
MS1-S0-6210 | CPK03-R9-IFC | 2022-02-03 | 6
MS1-S0-6211 | CPK03-R9-IFC | 2022-02-03 | 3
MS1-S0-6212 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-S0-6213 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-S0-6214-D | CPK03-R9-IFC | 2022-02-03 | 3
MS1-SS-2FK-B0000 | CPK03-R9-IFC | 2022-02-03 | 4
MS1-SS-2FK-C0000 | CPK03-R9-IFC | 2022-02-03 | 3
MS1-SS-2FK-D0000 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-SS-2FL-B0000 | CPK03-R9-IFC | 2022-02-03 | 3
MS1-SS-2FL-C0000 | CPK03-R9-IFC | 2022-02-03 | 3
MS1-SS-2FL-D0000 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-SS-2FM-B0000 | CPK03-R9-IFC | 2022-02-03 | 3
MS1-SS-2FM-B0300 | CPK03-R9-IFC | 2022-02-03 | 4
MS1-SS-2FM-C0000 | CPK03-R9-IFC | 2022-02-03 | 3
MS1-SS-2FM-D0000 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-SS-5RC-B0000 | CPK03-R9-IFC | 2022-02-03 | 6
MS1-SS-5RC-C0000 | CPK03-R9-IFC | 2022-02-03 | 3
MS1-SS-5RE-B0000 | CPK03-R9-IFC | 2022-02-03 | 4
MS1-SS-5RE-D0000 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-SS-5RF-4000 | CPK03-R9-IFC | 2022-02-03 | 3
MS1-SS-5RF-C0000 | CPK03-R9-IFC | 2022-02-03 | 5
MS1-SS-5RJ-D0000 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-SS-5RK-A0D00-D | CPK03-R9-IFC | 2022-02-03 | 2
MS1-SS-5RK-D0000 | CPK03-R9-IFC | 2022-02-03 | 2
MS1-SS-5RS-B0000 | CPK03-R9-IFC | 2022-02-03 | 4
MS1-SS-5RS-D0000 | CPK03-R9-IFC | 2022-02-03 | 2
MXD1AA52A | CPK03-R9-IFC | 2022-02-03 | 2
MXD1AA53A | CPK03-R9-IFC | 2022-02-03 | 2
MXD1AB55A | CPK03-R9-IFC | 2022-02-03 | 2
MXD1AC53A | CPK03-R9-IFC | 2022-02-03 | 2
MXD1AD53A | CPK03-R9-IFC | 2022-02-03 | 2
MXD1L53A | CPK03-R9-IFC | 2022-02-03 | 2
MXD1N52A | CPK03-R9-IFC | 2022-02-03 | 2
MXD1N53A | CPK03-R9-IFC | 2022-02-03 | 2
MXD1P53A | CPK03-R9-IFC | 2022-02-03 | 2
MXD1R51A | CPK03-R9-IFC | 2022-02-03 | 1
MXD1R51B | CPK03-R9-IFC | 2022-02-03 | 1
MXD1R53A | CPK03-R9-IFC | 2022-02-03 | 2
MXD1S52A | CPK03-R9-IFC | 2022-02-03 | 2
MXD1S53A | CPK03-R9-IFC | 2022-02-03 | 2
MXD1V53A | CPK03-R9-IFC | 2022-02-03 | 2
MXD1W53A | CPK03-R9-IFC | 2022-02-03 | 2
MXD1X53A | CPK03-R9-IFC | 2022-02-03 | 2
MXD1X55A | CPK03-R9-IFC | 2022-02-03 | 2
MXD1Y53A | CPK03-R9-IFC | 2022-02-03 | 1
MXD1Z53A | CPK03-R9-IFC | 2022-02-03 | 2
MXD2H57B | CPK03-R9-IFC | 2022-02-03 | 2
MXD2H57C | CPK03-R9-IFC | 2022-02-03 | 2
MXD2R50A | CPK03-R9-IFC | 2022-02-03 | 2
MXD2R50B | CPK03-R9-IFC | 2022-02-03 | 2
MXD2R50C | CPK03-R9-IFC | 2022-02-03 | 2
MXD2R50D | CPK03-R9-IFC | 2022-02-03 | 2
MXD2R50E | CPK03-R9-IFC | 2022-02-03 | 2
MXD2S50C | CPK03-R9-IFC | 2022-02-03 | 2
MXD2S50D | CPK03-R9-IFC | 2022-02-03 | 2
MXD2S57A | CPK03-R9-IFC | 2022-02-03 | 2
MXD2T50C | CPK03-R9-IFC | 2022-02-03 | 1
MXD2T57A | CPK03-R9-IFC | 2022-02-03 | 2
MXD2T57D | CPK03-R9-IFC | 2022-02-03 | 2
MXD2T57E | CPK03-R9-IFC | 2022-02-03 | 2
MXD2X50F | CPK03-R9-IFC | 2022-02-03 | 2
MXD2X50G | CPK03-R9-IFC | 2022-02-03 | 2
MXD2X50H | CPK03-R9-IFC | 2022-02-03 | 2
MXD2X57A | CPK03-R9-IFC | 2022-02-03 | 2
MXD4M50C | CPK03-R9-IFC | 2022-02-03 | 2
MXD4V56A | CPK03-R9-IFC | 2022-02-03 | 2
MXL2H57A | CPK03-R9-IFC | 2022-02-03 | 1
MXL2R50A | CPK03-R9-IFC | 2022-02-03 | 2
MXL2T50A | CPK03-R9-IFC | 2022-02-03 | 2
MXL2T57A | CPK03-R9-IFC | 2022-02-03 | 2
MXL2X50A | CPK03-R9-IFC | 2022-02-03 | 2
MXL2X57A | CPK03-R9-IFC | 2022-02-03 | 1
MXR1AA53B | CPK03-R9-IFC | 2022-02-03 | 2
MXR1AC53B | CPK03-R9-IFC | 2022-02-03 | 2
MXR1N53B | CPK03-R9-IFC | 2022-02-03 | 2
MXR1N57A | CPK03-R9-IFC | 2022-02-03 | 2
MXR1R53B | CPK03-R9-IFC | 2022-02-03 | 1
MXR1U56A | CPK03-R9-IFC | 2022-02-03 | 2
MXR1V53B | CPK03-R9-IFC | 2022-02-03 | 2
MXR1W53B | CPK03-R9-IFC | 2022-02-03 | 2
MXR1Z53B | CPK03-R9-IFC | 2022-02-03 | 2
MXR2R50A | CPK03-R9-IFC | 2022-02-03 | 2
MXR2R50B | CPK03-R9-IFC | 2022-02-03 | 1
MXR2T50A | CPK03-R9-IFC | 2022-02-03 | 2
MXR2T57A | CPK03-R9-IFC | 2022-02-03 | 2
MXR2X50A | CPK03-R9-IFC | 2022-02-03 | 2
MXR2X50B | CPK03-R9-IFC | 2022-02-03 | 1
MXR2X57A | CPK03-R9-IFC | 2022-02-03 | 3
RA-ST-2169 | CPK03-R9-IFC | 2022-02-03 | 8
MXR4M54B | CPK03-R9-IFC | 2022-02-03 | 2
MXR4Q54F | CPK03-R9-IFC | 2022-02-03 | 2
MXR4T52A | CPK03-R9-IFC | 2022-02-03 | 2
MXS4H56A | CPK03-R9-IFC | 2022-02-03 | 2
MXS4H56B | CPK03-R9-IFC | 2022-02-03 | 2
MXS4H56C | CPK03-R9-IFC | 2022-02-03 | 2
RA3-HF-3000C | CPK03-R9-IFC | 2022-02-03 | 3
RAC-HF-0001 | CPK03-R9-IFC | 2022-02-03 | 3
RAC-HH-0001 | CPK03-R9-IFC | 2022-02-03 | 2
RAC-HS-0001 | CPK03-R9-IFC | 2022-02-03 | 2
RA-P0-9001 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9002 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9003 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9004 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9005 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9006 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9007 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9008 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9009 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9010 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9011 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9012 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9013 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9014 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9015 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9016 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9017 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9018 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9019 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9020 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9021 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9022 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9023 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9024 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9025 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9026 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9027 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9028 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9029 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9030 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9031 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9032 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9033 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9034 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9035 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9036 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9037 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9038 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9039 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9040 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9041 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9042 | CPK03-R9-IFC | 2022-02-03 | 2
RA-P0-9043 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9044 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9045 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9046 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9047 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9048 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9049 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9050 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9051 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9052 | CPK03-R9-IFC | 2022-02-03 | 3
RA-P0-9053 | CPK03-R9-IFC | 2022-02-03 | 2
RA-P0-9054 | CPK03-R9-IFC | 2022-02-03 | 2
RA-P0-9055 | CPK03-R9-IFC | 2022-02-03 | 2
RA-P0-9056 | CPK03-R9-IFC | 2022-02-03 | 2
RA-P0-9057 | CPK03-R9-IFC | 2022-02-03 | 2
RA-P0-9058 | CPK03-R9-IFC | 2022-02-03 | 1
RA-ST-2170 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-0019 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2171 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2172 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-1005 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-1006 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-1010 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-1012 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-1013 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-1014 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-1015 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-1016 | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-1017 | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-1018 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-1022 | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-1023 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-1024 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-1025 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-1026 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-1027 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-1028 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2001 | CPK03-R9-IFC | 2022-02-03 | 7
RA-ST-2002 | CPK03-R9-IFC | 2022-02-03 | 7
RA-ST-2003 | CPK03-R9-IFC | 2022-02-03 | 7
RA-ST-2173 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2174 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2021 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2175 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2030 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2177 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2047 | CPK03-R9-IFC | 2022-02-03 | 7
RA-ST-2049 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2050 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2178 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2179 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2182 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2184 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2185 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2096 | CPK03-R9-IFC | 2022-02-03 | 7
RA-ST-2098 | CPK03-R9-IFC | 2022-02-03 | 7
RA-ST-2099 | CPK03-R9-IFC | 2022-02-03 | 7
RA-ST-2101 | CPK03-R9-IFC | 2022-02-03 | 7
RA-ST-2103 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-2104 | CPK03-R9-IFC | 2022-02-03 | 7
RA-ST-2115 | CPK03-R9-IFC | 2022-02-03 | 7
RA-ST-2116 | CPK03-R9-IFC | 2022-02-03 | 7
RA-ST-2117 | CPK03-R9-IFC | 2022-02-03 | 7
RA-ST-2119 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2121 | CPK03-R9-IFC | 2022-02-03 | 7
RA-ST-2122 | CPK03-R9-IFC | 2022-02-03 | 7
RA-ST-2130 | CPK03-R9-IFC | 2022-02-03 | 7
RA-ST-2135 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-3000 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-2145 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-3001 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-2163 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2167 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-2176 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-3002 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-2180 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-2181 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-2183 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-2186 | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-2187 | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-2188 | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-2189 | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-2190 | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-2191 | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-2192 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-2193 | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-2194 | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-2195 | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-2196 | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-2197 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-2198 | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-2199 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-2200 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-2201 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-2203 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2204 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-2205 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-2206 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-2207 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-2208 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-2209 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-2210 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-2211 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2212 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2213 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2214 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2215 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2216 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2217 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2218 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-2219 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-2220 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-2221 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2222 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-2223 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-2224 | CPK03-R9-IFC | 2022-02-03 | 3
RA-ST-2225 | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-2226 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2227 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2228 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2229 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2230 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-2231 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2232 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2233 | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-2234 | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-2235 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2237 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2238 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2239 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-2240 | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-2241 | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-2242 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-2243 | CPK03-R9-IFC | 2022-02-03 | 6
RA-ST-2244 | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-2245 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2246 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2247 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2248 | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-2249 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2250 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2251 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2252 | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-2253 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2254 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2255 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2256 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2257 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2258 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2260 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2261 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2262 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2263 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2264 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2265 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2266 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2267 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2268 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2269 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2270 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2271 | CPK03-R9-IFC | 2022-02-03 | 3
RA-ST-2272 | CPK03-R9-IFC | 2022-02-03 | 3
RA-ST-2277 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2278 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2279 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2280 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2281 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2282 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2283 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2284 | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-2285 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2286 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2288 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2289 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2291 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2292 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2293 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2294 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2295 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2296 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2297 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2298 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2299 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-2300 | CPK03-R9-IFC | 2022-02-03 | 3
RA-ST-2301 | CPK03-R9-IFC | 2022-02-03 | 3
RA-ST-2304 | CPK03-R9-IFC | 2022-02-03 | 3
RA-ST-2305 | CPK03-R9-IFC | 2022-02-03 | 3
RA-ST-3009 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-3008 | CPK03-R9-IFC | 2022-02-03 | 8
RA-ST-4005 | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-4006 | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-4007 | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-4008 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-4009 | CPK03-R9-IFC | 2022-02-03 | 4
RA-ST-4010 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-4011 | CPK03-R9-IFC | 2022-02-03 | 5
RA-ST-4012 | CPK03-R9-IFC | 2022-02-03 | 5
XD4D2A06A | CPK03-R9-IFC | 2022-02-03 | 2
XMXD2G57A | CPK03-R9-IFC | 2022-02-03 | 2
XMXD2R50A | CPK03-R9-IFC | 2022-02-03 | 2
XMXD2R50B | CPK03-R9-IFC | 2022-02-03 | 2
XMXD2S57B | CPK03-R9-IFC | 2022-02-03 | 2
XMXD2S57C | CPK03-R9-IFC | 2022-02-03 | 2
XMXD2T50B | CPK03-R9-IFC | 2022-02-03 | 2
XMXD2T57A | CPK03-R9-IFC | 2022-02-03 | 2
XMXD2X57B | CPK03-R9-IFC | 2022-02-03 | 2
XMXD2Z50A | CPK03-R9-IFC | 2022-02-03 | 2
XMXD5AA53A | CPK03-R9-IFC | 2022-02-03 | 1
XMXD5AA53C | CPK03-R9-IFC | 2022-02-03 | 1
XMXD5G52A | CPK03-R9-IFC | 2022-02-03 | 2
XMXD5G52B | CPK03-R9-IFC | 2022-02-03 | 2
XMXD5H52A | CPK03-R9-IFC | 2022-02-03 | 2
XMXD5H52B | CPK03-R9-IFC | 2022-02-03 | 2
XMXD5H52C | CPK03-R9-IFC | 2022-02-03 | 2
XMXD5H52D | CPK03-R9-IFC | 2022-02-03 | 2
XMXL2G57A | CPK03-R9-IFC | 2022-02-03 | 1
XMXL2R50A | CPK03-R9-IFC | 2022-02-03 | 1
XMXL2R50B | CPK03-R9-IFC | 2022-02-03 | 2
XMXL2Y57A | CPK03-R9-IFC | 2022-02-03 | 2
XMXL2Z50A | CPK03-R9-IFC | 2022-02-03 | 2
XMXR2T50B | CPK03-R9-IFC | 2022-02-03 | 2
XMXR2Z50C | CPK03-R9-IFC | 2022-02-03 | 2
XMXR4Z54A | CPK03-R9-IFC | 2022-02-03 | 1
XMXS4J56B | CPK03-R9-IFC | 2022-02-03 | 2
XMXS4J56C | CPK03-R9-IFC | 2022-02-03 | 2
RA-ST-4000 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-4001 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-4002 | CPK03-R9-IFC | 2022-02-03 | 9
RA-ST-4003 | CPK03-R9-IFC | 2022-02-03 | 9
RA4-A0-0731 | LLE01-IFC | 2021-07-20 | 1
RA4-A0-7120-ZGF | LLE01-IFC | 2021-07-20 | 1
RA4-A0-7129-ZGF | LLE01-IFC | 2021-07-20 | 1
RA4-AF-10A-M0000-ZGF | LLE01-IFC | 2021-07-20 | 1
RA4-AF-20C-M0000-ZGF | LLE01-IFC | 2021-07-20 | 1
00_01_00_00 | LLE01-IFC | 2021-07-20 | 7
25_14_01_00_DCPLC_DATASHEET | LLE01-IFC | 2021-07-20 | 1
25_14_01_00_HDRIO_DATASHEET | LLE01-IFC | 2021-07-20 | 1
RAC-GN-0001 | LLE01-IFC | 2021-07-20 | 5
RAC-GN-0002 | LLE01-IFC | 2021-07-20 | 5
RAC-GN-0003 | LLE01-IFC | 2021-07-20 | 5
RAC-GN-0004 | LLE01-IFC | 2021-07-20 | 5
RAC-GN-0005 | LLE01-IFC | 2021-07-20 | 5
RAC-GN-0006 | LLE01-IFC | 2021-07-20 | 5
RAC-GN-0007 | LLE01-IFC | 2021-07-20 | 5
RAC-GN-0008 | LLE01-IFC | 2021-07-20 | 5
RAC-GN-0009 | LLE01-IFC | 2021-07-20 | 5
RAC-GN-0010 | LLE01-IFC | 2021-07-20 | 5
MS1-PE-0210 | LLE01-IFC | 2021-07-20 | 2
MS1-TK275-1-00 | LLE01-IFC | 2021-07-20 | 1
MS1-TK275-2-00 | LLE01-IFC | 2021-07-20 | 1
MS1-PE-0211 | LLE01-IFC | 2021-07-20 | 4
MS1-TK299-1-00 | LLE01-IFC | 2021-07-20 | 2
MS1-TK299-2-00 | LLE01-IFC | 2021-07-20 | 2
RA4-PE-0230 | LLE01-IFC | 2021-07-20 | 2
RA4-TK276-1-00 | LLE01-IFC | 2021-07-20 | 1
RA4-TK276-2-00 | LLE01-IFC | 2021-07-20 | 1
RA4-PE-0250 | LLE01-IFC | 2021-07-20 | 1
RA4-TK252-1-10 | LLE01-IFC | 2021-07-20 | 1
MS1-IE-1001 | LLE01-IFC | 2021-07-20 | 3
MS1-IE-1004 | LLE01-IFC | 2021-07-20 | 2
MS1-IE-1005 | LLE01-IFC | 2021-07-20 | 2
MS1-IE-1220 | LLE01-IFC | 2021-07-20 | 2
MS1-IE-3005A | LLE01-IFC | 2021-07-20 | 1
MS1-IE-3005B | LLE01-IFC | 2021-07-20 | 1
MS1-IE-3014A | LLE01-IFC | 2021-07-20 | 1
MS1-IE-3014B | LLE01-IFC | 2021-07-20 | 1
MS1-IE-3014C | LLE01-IFC | 2021-07-20 | 1
MS1-IE-3014D | LLE01-IFC | 2021-07-20 | 1
MS1-IE-3015 | LLE01-IFC | 2021-07-20 | 1
RA4-I0-1041 | LLE01-IFC | 2021-07-20 | 1
RA4-I0-1042 | LLE01-IFC | 2021-07-20 | 1
RA4-I0-1043 | LLE01-IFC | 2021-07-20 | 1
RA4-IE-3004 | LLE01-IFC | 2021-07-20 | 2
MS1-269-D0-A01 | LLE01-IFC | 2021-07-20 | 2
MS1-270-D0-A01 | LLE01-IFC | 2021-07-20 | 2
RA4-248-D0-A01 | LLE01-IFC | 2021-07-20 | 1
RA4-275-D0-A01 | LLE01-IFC | 2021-07-20 | 2
RA4-299-D0-Z08 | LLE01-IFC | 2021-07-20 | 1
RA4-299-D0-Z09 | LLE01-IFC | 2021-07-20 | 1
RA4-299-D0-Z10 | LLE01-IFC | 2021-07-20 | 1
0110-00-0269 | LLE01-IFC | 2021-07-20 | 1
0110-00-0270 | LLE01-IFC | 2021-07-20 | 1
0525-01-0478 | LLE01-IFC | 2021-07-20 | 1
0525-01-0479 | LLE01-IFC | 2021-07-20 | 1
0525-01-0480 | LLE01-IFC | 2021-07-20 | 1
1810_CMS_04_01 | LLE01-IFC | 2021-07-20 | 2
1810_CMS_04_02 | LLE01-IFC | 2021-07-20 | 2
1810_VFD_08 | LLE01-IFC | 2021-07-20 | 4
25_14_01_00_BETAP_0 | LLE01-IFC | 2021-07-20 | 1
25_14_01_00_BETAP_1 | LLE01-IFC | 2021-07-20 | 1
25_14_01_00_BETAP_2 | LLE01-IFC | 2021-07-20 | 1
25_14_01_00_COMPCTLX.0.dwg | LLE01-IFC | 2021-07-20 | 1
25_14_01_00_COMPCTLX_1 | LLE01-IFC | 2021-07-20 | 1
25_14_01_00_COMPCTLX.2.dwg | LLE01-IFC | 2021-07-20 | 1
25_14_01_00_COMPCTLX.3.dwg | LLE01-IFC | 2021-07-20 | 1
25_14_01_00_COMPCTLX.4.dwg | LLE01-IFC | 2021-07-20 | 1
25_14_01_00_DCPLC_0 | LLE01-IFC | 2021-07-20 | 1
25_14_01_00_DCPLC_1 | LLE01-IFC | 2021-07-20 | 1
25_14_01_00_DCPLC_2 | LLE01-IFC | 2021-07-20 | 1
25_14_01_00_DCPLC_3 | LLE01-IFC | 2021-07-20 | 1
25_14_01_00_ETAP_0 | LLE01-IFC | 2021-07-20 | 2
25_14_01_00_HDRIO_0 | LLE01-IFC | 2021-07-20 | 2
25_14_01_00_HDRIO_1 | LLE01-IFC | 2021-07-20 | 2
25_14_01_00_HDRIO_2 | LLE01-IFC | 2021-07-20 | 2
25_14_01_00_HDRIO_3 | LLE01-IFC | 2021-07-20 | 2
25_14_01_00_LDRIO_0 | LLE01-IFC | 2021-07-20 | 1
25_14_01_00_LDRIO_1 | LLE01-IFC | 2021-07-20 | 1
25_14_01_00_LDRIO_2 | LLE01-IFC | 2021-07-20 | 1
25_14_01_00_LDRIO_3 | LLE01-IFC | 2021-07-20 | 1
25_14_01_00_LIOPLC_0 | LLE01-IFC | 2021-07-20 | 2
25_14_01_00_LIOPLC_1 | LLE01-IFC | 2021-07-20 | 2
25_14_01_00_LIOPLC_2 | LLE01-IFC | 2021-07-20 | 2
25_14_01_00_LIOPLC_3 | LLE01-IFC | 2021-07-20 | 2
25_14_01_00_PBDP_0 | LLE01-IFC | 2021-07-20 | 2
D-I-1910_08 | LLE01-IFC | 2021-07-20 | 3
D-I-1910_23 | LLE01-IFC | 2021-07-20 | 4
00_00_00_01 | LLE01-IFC | 2021-07-20 | 6
01_11_00_00 | LLE01-IFC | 2021-07-20 | 3
01_72_10_00 | LLE01-IFC | 2021-07-20 | 2
14_21_00_00 | LLE01-IFC | 2021-07-20 | 1
14_93_31_00 | LLE01-IFC | 2021-07-20 | 1
25_14_01_00_DAT_03 | LLE01-IFC | 2021-07-20 | 5
MSB1-PLC102-2-00 | LLE01-IFC | 2021-07-20 | 2
MSB1-PLC650-104-00 | LLE01-IFC | 2021-07-20 | 3
25_14_01_00_COMPCTLX_DATASHEET | LLE01-IFC | 2021-07-20 | 1
MSB1-PLC101-7-00 | LLE01-IFC | 2021-07-20 | 2
MSB1-PLC101-8-00 | LLE01-IFC | 2021-07-20 | 2
25_14_01_00_XXXX_DATASHEET | LLE01-IFC | 2021-07-20 | 1
MSB1-RIO102-2-01 | LLE01-IFC | 2021-07-20 | 2
MSB1-RIO102-2-02 | LLE01-IFC | 2021-07-20 | 2
MSB1-RIO650-104-01 | LLE01-IFC | 2021-07-20 | 2
MSB1-RIO650-104-02 | LLE01-IFC | 2021-07-20 | 2
MSB1-RIO650-101-04 | LLE01-IFC | 2021-07-20 | 3
MSB1-RIO650-102-04 | LLE01-IFC | 2021-07-20 | 3
MSB1-RIO650-103-04 | LLE01-IFC | 2021-07-20 | 3
MSB1-RIO650-101-03 | LLE01-IFC | 2021-07-20 | 2
MSB1-RIO650-102-03 | LLE01-IFC | 2021-07-20 | 2
MSB1-RIO650-103-03 | LLE01-IFC | 2021-07-20 | 2
25_14_01_00_LDRIO_DATASHEET | LLE01-IFC | 2021-07-20 | 1
MSB1-RIO650-101-05 | LLE01-IFC | 2021-07-20 | 2
MSB1-RIO650-102-05 | LLE01-IFC | 2021-07-20 | 2
MSB1-RIO650-103-05 | LLE01-IFC | 2021-07-20 | 2
25_14_01_00_BETAP_DATASHEET | LLE01-IFC | 2021-07-20 | 1
MSB1-ETP650-1A-00 | LLE01-IFC | 2021-07-20 | 2
MSB1-ETP650-1B-00 | LLE01-IFC | 2021-07-20 | 2
25_14_01_00_ETAP_DATASHEET | LLE01-IFC | 2021-07-20 | 1
MSB1-ETAP650-1-01 | LLE01-IFC | 2021-07-20 | 2
25_14_01_00_STX_DATASHEET | LLE01-IFC | 2021-07-20 | 1
MSB1-LCP102-101-00 | LLE01-IFC | 2021-07-20 | 2
MSB1-LCP102-102-00 | LLE01-IFC | 2021-07-20 | 2
MSB1-LCP102-103-00 | LLE01-IFC | 2021-07-20 | 2
MSB1-LCP102-104-00 | LLE01-IFC | 2021-07-20 | 2
25_14_01_00_PBDP_DATASHEET | LLE01-IFC | 2021-07-20 | 1
MSB1-GTW650-2-90 | LLE01-IFC | 2021-07-20 | 2
25_14_01_00_PBSP_DATASHEET | LLE01-IFC | 2021-07-20 | 1
MSB1-JB650-X-90 | LLE01-IFC | 2021-07-20 | 2
MSB1-JB650-Y-90 | LLE01-IFC | 2021-07-20 | 2
MSB1-JB650-Z-90 | LLE01-IFC | 2021-07-20 | 2
MSB1-JB650-W-90 | LLE01-IFC | 2021-07-20 | 2
RA4-PLC101-X-00 | LLE01-IFC | 2021-07-20 | 2
RA4-PLC101-Y-00 | LLE01-IFC | 2021-07-20 | 2
RA4-PLC101-Z-00 | LLE01-IFC | 2021-07-20 | 2
25_14_01_00_LIOPLC_DATASHEET | LLE01-IFC | 2021-07-20 | 1
RA4-PLC299-03-00 | LLE01-IFC | 2021-07-20 | 2
RA4-PLC299-04-00 | LLE01-IFC | 2021-07-20 | 1
RA4-RIO650-101-08 | LLE01-IFC | 2021-07-20 | 2
RA4-RIO650-102-08 | LLE01-IFC | 2021-07-20 | 2
RA4-RIO299-03-01 | LLE01-IFC | 2021-07-20 | 2
RA4-RIO299-04-01 | LLE01-IFC | 2021-07-20 | 1
RA4-ETP650-1A-00 | LLE01-IFC | 2021-07-20 | 2
RA4-ETP650-1B-00 | LLE01-IFC | 2021-07-20 | 2
RA4-ETAP650-1-01 | LLE01-IFC | 2021-07-20 | 2
RA4-ETAP650-1-02 | LLE01-IFC | 2021-07-20 | 2
RA4-ETAP650-2-01 | LLE01-IFC | 2021-07-20 | 2
RA4-ETAP650-3-01 | LLE01-IFC | 2021-07-20 | 2
RA4-ETAP650-3-02 | LLE01-IFC | 2021-07-20 | 2
RA4-LCP102-101-00 | LLE01-IFC | 2021-07-20 | 2
RA4-GTW650-X-90 | LLE01-IFC | 2021-07-20 | 2
RA4-JB650-X-90 | LLE01-IFC | 2021-07-20 | 2
RA4-JB650-Y-90 | LLE01-IFC | 2021-07-20 | 2
D1X1A-ETAP650-1-01 | LLE01-IFC | 2021-07-20 | 1
D1X1A-ETAP650-1-02 | LLE01-IFC | 2021-07-20 | 1
D1X1A-RIO650-XX-YY | LLE01-IFC | 2021-07-20 | 1
D1X1A-RIO650-XX-ZZ | LLE01-IFC | 2021-07-20 | 1
RA4-RIO650-104-02 | LLE01-IFC | 2021-07-20 | 2
MSB1_PLC650_1A_00 | LLE01-IFC | 2021-07-20 | 2
MSB1-PLC650-1A-00 | LLE01-IFC | 2021-07-20 | 1
MSB1_PLC650_1B_00 | LLE01-IFC | 2021-07-20 | 2
MSB1-PLC650-1B-00 | LLE01-IFC | 2021-07-20 | 1
RA4-PLC650-1A-00 | LLE01-IFC | 2021-07-20 | 2
RA4-PLC650-1B-00 | LLE01-IFC | 2021-07-20 | 2
MSB1_PLC650_101_00 | LLE01-IFC | 2021-07-20 | 3
MSB1-PLC650-101-00 | LLE01-IFC | 2021-07-20 | 1
MSB1_PLC650_102_00 | LLE01-IFC | 2021-07-20 | 3
MSB1-PLC650-102-00 | LLE01-IFC | 2021-07-20 | 1 |  | Issued via RFI-0132
MSB1_PLC650_103_00 | LLE01-IFC | 2021-07-20 | 3
MSB1-PLC650-103-00 | LLE01-IFC | 2021-07-20 | 1
RA4-PLC650-101-00 | LLE01-IFC | 2021-07-20 | 2
RA4-PLC650-102-00 | LLE01-IFC | 2021-07-20 | 2
RA4-PLC650-103-00 | LLE01-IFC | 2021-07-20 | 2
RA4-PLC650-104-00 | LLE01-IFC | 2021-07-20 | 2
26_29_13_21_app | LLE01-IFC | 2021-07-20 | 2
26_29_65_00_app | LLE01-IFC | 2021-07-20 | 3
27_30_73_84 | LLE01-IFC | 2021-07-20 | 1
40_05_15_16 | LLE01-IFC | 2021-07-20 | 1
40_05_15_21_DAT | LLE01-IFC | 2021-07-20 | 1
MSB1-TK-202-1-03 | LLE01-IFC | 2021-07-20 | 1
MSB1-TK-202-2-03 | LLE01-IFC | 2021-07-20 | 1
40_05_15_34_DAT | LLE01-IFC | 2021-07-20 | 3
MSB1-PCV245-3-00A | LLE01-IFC | 2021-07-20 | 1
MSB1-PCV245-3-00B | LLE01-IFC | 2021-07-20 | 1
MSB1-PCV245-4-00A | LLE01-IFC | 2021-07-20 | 1
MSB1-PCV245-4-00B | LLE01-IFC | 2021-07-20 | 1
40_05_15_51_DAT | LLE01-IFC | 2021-07-20 | 3
RA4-PMP276-1-10 | LLE01-IFC | 2021-07-20 | 1
RA4-PMP276-2-10 | LLE01-IFC | 2021-07-20 | 1
RA4-PMP252-1-20 | LLE01-IFC | 2021-07-20 | 1
RA4-PMP252-2-20 | LLE01-IFC | 2021-07-20 | 1
MSB1-PMP275-1-10 | LLE01-IFC | 2021-07-20 | 1
MSB1-PMP275-2-10 | LLE01-IFC | 2021-07-20 | 1
MSB1-PMP299-1-05 | LLE01-IFC | 2021-07-20 | 2
MSB1-PMP299-2-05 | LLE01-IFC | 2021-07-20 | 2
RA4-PMP299-3A-10 | LLE01-IFC | 2021-07-20 | 2
RA4-PMP299-3B-10 | LLE01-IFC | 2021-07-20 | 2
MSB-PMP202-1-10 | LLE01-IFC | 2021-07-20 | 1
MSB-PMP202-2-10 | LLE01-IFC | 2021-07-20 | 1
MSB-PMP202-3-10 | LLE01-IFC | 2021-07-20 | 1
RA4-PMP2248-IC-07 | LLE01-IFC | 2021-07-20 | 1
CUB4-PMP111-17-00 | LLE01-IFC | 2021-07-20 | 2
40_05_15_51 | LLE01-IFC | 2021-07-20 | 1
42_13_10_66_DAT | LLE01-IFC | 2021-07-20 | 1
MSB-HX202-1-30 | LLE01-IFC | 2021-07-20 | 1
MSB-HX202-2-30 | LLE01-IFC | 2021-07-20 | 1
MSB-HX202-3-30 | LLE01-IFC | 2021-07-20 | 1
RA4-HX248-1C-16 | LLE01-IFC | 2021-07-20 | 1
43_21_16_21_DAT | LLE01-IFC | 2021-07-20 | 3
RA4‐PMP252‐0‐40 | LLE01-IFC | 2021-07-20 | 1
RA4‐PMP253‐0‐30 | LLE01-IFC | 2021-07-20 | 1
MSB1‐PMP276‐0‐10 | LLE01-IFC | 2021-07-20 | 1
RA4‐PMP276‐0‐10 | LLE01-IFC | 2021-07-20 | 1
MSB1‐PMP275‐0‐10 | LLE01-IFC | 2021-07-20 | 1
RA4‐PMP275‐0‐60 | LLE01-IFC | 2021-07-20 | 1
43_22_16_55_DAT | LLE01-IFC | 2021-07-20 | 1
MSB1-MX299-1-01 | LLE01-IFC | 2021-07-20 | 1
MSB1-MX299-2-01 | LLE01-IFC | 2021-07-20 | 1
43_31_00_10_DAT | LLE01-IFC | 2021-07-20 | 1
RA4-FL248-1C-09 | LLE01-IFC | 2021-07-20 | 1
MSB-FL202-1-20 | LLE01-IFC | 2021-07-20 | 1
MSB-FL202-2-20 | LLE01-IFC | 2021-07-20 | 1
43_41_16_01_DAT | LLE01-IFC | 2021-07-20 | 2
MSB1-TK275-1-00 | LLE01-IFC | 2021-07-20 | 1
MSB1-TK275-2-00 | LLE01-IFC | 2021-07-20 | 1
MSB1-TK299-1-00 | LLE01-IFC | 2021-07-20 | 2
MSB1-TK299-2-00 | LLE01-IFC | 2021-07-20 | 2
43_41_16_02_DAT | LLE01-IFC | 2021-07-20 | 2
43_41_16_04_DAT | LLE01-IFC | 2021-07-20 | 2
00_01_00_00 | LLE01-R1-IFC | 2021-10-08 | 7
MS1-PE-0210 | LLE01-R1-IFC | 2021-10-08 | 2
MS1-PE-0211 | LLE01-R1-IFC | 2021-10-08 | 4
MS1-TK299-1-00 | LLE01-R1-IFC | 2021-10-08 | 2
MS1-TK299-2-00 | LLE01-R1-IFC | 2021-10-08 | 2
RA4-PE-0230 | LLE01-R1-IFC | 2021-10-08 | 2
RA4-275-D0-A01 | LLE01-R1-IFC | 2021-10-08 | 2
00_00_00_01 | LLE01-R1-IFC | 2021-10-08 | 6
25_14_01_00_DAT_03 | LLE01-R1-IFC | 2021-10-08 | 5
MSB1-PLC102-2-00 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1-PLC650-104-00 | LLE01-R1-IFC | 2021-10-08 | 3
MSB1-PLC101-7-00 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1-PLC101-8-00 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1-RIO102-2-01 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1-RIO102-2-02 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1-RIO650-104-01 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1-RIO650-104-02 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1-RIO650-101-04 | LLE01-R1-IFC | 2021-10-08 | 3
MSB1-RIO650-102-04 | LLE01-R1-IFC | 2021-10-08 | 3
MSB1-RIO650-103-04 | LLE01-R1-IFC | 2021-10-08 | 3
MSB1-RIO650-101-03 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1-RIO650-102-03 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1-RIO650-103-03 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1-RIO650-101-05 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1-RIO650-102-05 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1-RIO650-103-05 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1-ETP650-1A-00 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1-ETP650-1B-00 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1-ETAP650-1-01 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1-LCP102-101-00 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1-LCP102-102-00 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1-LCP102-103-00 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1-LCP102-104-00 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1-GTW650-2-90 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1-JB650-X-90 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1-JB650-Y-90 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1-JB650-Z-90 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1-JB650-W-90 | LLE01-R1-IFC | 2021-10-08 | 2
RA4-PLC101-X-00 | LLE01-R1-IFC | 2021-10-08 | 2
RA4-PLC101-Y-00 | LLE01-R1-IFC | 2021-10-08 | 2
RA4-PLC101-Z-00 | LLE01-R1-IFC | 2021-10-08 | 2
RA4-PLC299-03-00 | LLE01-R1-IFC | 2021-10-08 | 2
RA4-RIO650-101-08 | LLE01-R1-IFC | 2021-10-08 | 2
RA4-RIO650-102-08 | LLE01-R1-IFC | 2021-10-08 | 2
RA4-RIO299-03-01 | LLE01-R1-IFC | 2021-10-08 | 2
RA4-ETP650-1A-00 | LLE01-R1-IFC | 2021-10-08 | 2
RA4-ETP650-1B-00 | LLE01-R1-IFC | 2021-10-08 | 2
RA4-ETAP650-1-01 | LLE01-R1-IFC | 2021-10-08 | 2
RA4-ETAP650-1-02 | LLE01-R1-IFC | 2021-10-08 | 2
RA4-ETAP650-2-01 | LLE01-R1-IFC | 2021-10-08 | 2
RA4-ETAP650-3-01 | LLE01-R1-IFC | 2021-10-08 | 2
RA4-ETAP650-3-02 | LLE01-R1-IFC | 2021-10-08 | 2
RA4-LCP102-101-00 | LLE01-R1-IFC | 2021-10-08 | 2
RA4-GTW650-X-90 | LLE01-R1-IFC | 2021-10-08 | 2
RA4-JB650-X-90 | LLE01-R1-IFC | 2021-10-08 | 2
RA4-JB650-Y-90 | LLE01-R1-IFC | 2021-10-08 | 2
RA4-RIO650-104-02 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1_PLC650_1A_00 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1_PLC650_1B_00 | LLE01-R1-IFC | 2021-10-08 | 2
RA4-PLC650-1A-00 | LLE01-R1-IFC | 2021-10-08 | 2
RA4-PLC650-1B-00 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1_PLC650_101_00 | LLE01-R1-IFC | 2021-10-08 | 3
MSB1_PLC650_102_00 | LLE01-R1-IFC | 2021-10-08 | 3
MSB1_PLC650_103_00 | LLE01-R1-IFC | 2021-10-08 | 3
RA4-PLC650-101-00 | LLE01-R1-IFC | 2021-10-08 | 2
RA4-PLC650-102-00 | LLE01-R1-IFC | 2021-10-08 | 2
RA4-PLC650-103-00 | LLE01-R1-IFC | 2021-10-08 | 2
RA4-PLC650-104-00 | LLE01-R1-IFC | 2021-10-08 | 2
26_29_13_21_app | LLE01-R1-IFC | 2021-10-08 | 2
26_29_65_00_app | LLE01-R1-IFC | 2021-10-08 | 3
40_05_15_16_tbl | LLE01-R1-IFC | 2021-10-08 | 2
40_05_15_51_dat | LLE01-R1-IFC | 2021-10-08 | 3
MSB1-PMP299-1-05 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1-PMP299-2-05 | LLE01-R1-IFC | 2021-10-08 | 2
RA4-PMP299-3A-10 | LLE01-R1-IFC | 2021-10-08 | 2
RA4-PMP299-3B-10 | LLE01-R1-IFC | 2021-10-08 | 2
MS1-PMP202-1-10 | LLE01-R1-IFC | 2021-10-08 | 1
MS1-PMP202-2-10 | LLE01-R1-IFC | 2021-10-08 | 1
MS1-PMP202-3-10 | LLE01-R1-IFC | 2021-10-08 | 1
RA4-PMP248-1C-07 | LLE01-R1-IFC | 2021-10-08 | 1
CUB4-PMP111-17-00 | LLE01-R1-IFC | 2021-10-08 | 2
43_21_16_21_dat | LLE01-R1-IFC | 2021-10-08 | 3
RA4‐PMP252‐0‐40 | LLE01-R1-IFC | 2021-10-08 | 1
43_41_16_01_dat | LLE01-R1-IFC | 2021-10-08 | 2
MSB1-TK299-1-00 | LLE01-R1-IFC | 2021-10-08 | 2
MSB1-TK299-2-00 | LLE01-R1-IFC | 2021-10-08 | 2
43_41_16_02_dat | LLE01-R1-IFC | 2021-10-08 | 2
00_01_00_00 | LLP02-IFC | 2021-08-20 | 7
MS1-PE-0200 | LLP02-IFC | 2021-08-20 | 1
MSB1-TK221-1-60 | LLP02-IFC | 2021-08-20 | 1
MS1-PE-0250 | LLP02-IFC | 2021-08-20 | 1
MSB1-TK133-1-07 | LLP02-IFC | 2021-08-20 | 2
RA4-PE-0251 | LLP02-IFC | 2021-08-20 | 1
RA4-TK252-1-30 | LLP02-IFC | 2021-08-20 | 1
MS1-PE-0300 | LLP02-IFC | 2021-08-20 | 1
MS1-TK276-1-00 | LLP02-IFC | 2021-08-20 | 1
RA4-I0-3009B | LLP02-IFC | 2021-08-20 | 1
RA4-LCP299-3-00 | LLP02-IFC | 2021-08-20 | 1
1810_VFD_08 | LLP02-IFC | 2021-08-20 | 4
1810_VFD_09 | LLP02-IFC | 2021-08-20 | 3
25_14_01_00_LIOPLC_0 | LLP02-IFC | 2021-08-20 | 2
25_14_01_00_LIOPLC_1 | LLP02-IFC | 2021-08-20 | 2
25_14_01_00_LIOPLC_2 | LLP02-IFC | 2021-08-20 | 2
25_14_01_00_LIOPLC_3 | LLP02-IFC | 2021-08-20 | 2
25_14_01_00_ETAP_0 | LLP02-IFC | 2021-08-20 | 2
RAC-HS-9005-HID | LLP02-IFC | 2021-08-20 | 1
LSS-MDP-H55 | LLP02-IFC | 2021-08-20 | 1
LSS-MDP-H55A | LLP02-IFC | 2021-08-20 | 1
LSS-MDP-H70 | LLP02-IFC | 2021-08-20 | 1
LSS-MDP-H70A | LLP02-IFC | 2021-08-20 | 1
LSS-MDP-H72 | LLP02-IFC | 2021-08-20 | 1
LSS-MDP-H72A | LLP02-IFC | 2021-08-20 | 1
D-H-1845-HPM-410-MDP | LLP02-IFC | 2021-08-20 | 4
00_00_00_01 | LLP02-IFC | 2021-08-20 | 6
01_11_00_00 | LLP02-IFC | 2021-08-20 | 3
01_72_10_00 | LLP02-IFC | 2021-08-20 | 2
23_82_16_61_dat | LLP02-IFC | 2021-08-20 | 2
MS1-CC102-01-30 | LLP02-IFC | 2021-08-20 | 1
MS1-CC102-001-20 | LLP02-IFC | 2021-08-20 | 1
MS1-GAH104-28-00 | LLP02-IFC | 2021-08-20 | 1
25_14_01_00_dat_03 | LLP02-IFC | 2021-08-20 | 5
RA4-PLC252-1-00 | LLP02-IFC | 2021-08-20 | 2
RA4-ETAP252-1-00 | LLP02-IFC | 2021-08-20 | 2
RA4-PLC253-1-00 | LLP02-IFC | 2021-08-20 | 1
26_29_65_00_app | LLP02-IFC | 2021-08-20 | 3
40_05_15_16_TBL | LLP02-IFC | 2021-08-20 | 2
40_05_15_34_DAT | LLP02-IFC | 2021-08-20 | 3
MSB1-PCV202-1-00A | LLP02-IFC | 2021-08-20 | 1
MSB1-PCV202-1-00B | LLP02-IFC | 2021-08-20 | 1
MSB1-PCV202-1-00C | LLP02-IFC | 2021-08-20 | 1
MSB1-PCV202-1-00D | LLP02-IFC | 2021-08-20 | 1
MSB1-PCV202-1-00E | LLP02-IFC | 2021-08-20 | 1
MSB1-PCV249-1-00A | LLP02-IFC | 2021-08-20 | 1
MSB1-PCV249-1-00B | LLP02-IFC | 2021-08-20 | 1
MSB1-PCZ132-0-04A | LLP02-IFC | 2021-08-20 | 1
MSB1-PCZ132-0-04C | LLP02-IFC | 2021-08-20 | 1
MSB1-PCZ132-0-04D | LLP02-IFC | 2021-08-20 | 1
MSB1-PCZ132-0-04E | LLP02-IFC | 2021-08-20 | 1
MSB1-PCZ132-0-04F | LLP02-IFC | 2021-08-20 | 1
MSB1-PCZ133-0-04A | LLP02-IFC | 2021-08-20 | 1
MSB1-PCZ133-0-04B | LLP02-IFC | 2021-08-20 | 1
MSB1-PCZ133-0-04C | LLP02-IFC | 2021-08-20 | 1
MSB1-PCZ133-0-04D | LLP02-IFC | 2021-08-20 | 1
MSB1-PCZ133-0-04E | LLP02-IFC | 2021-08-20 | 1
MSB1-PCZ133-0-04F | LLP02-IFC | 2021-08-20 | 1
MSB1-PCZ133-1-04G | LLP02-IFC | 2021-08-20 | 1
MSB1-PCZ133-2-04G | LLP02-IFC | 2021-08-20 | 1
MSB1-PCZ133-3-04G | LLP02-IFC | 2021-08-20 | 1
MSB1-PCZ138-0-04A | LLP02-IFC | 2021-08-20 | 2
MSB1-PCZ138-0-04B | LLP02-IFC | 2021-08-20 | 2
MSB1-PCZ138-0-04C | LLP02-IFC | 2021-08-20 | 2
MSB1-PCZ138-0-04D | LLP02-IFC | 2021-08-20 | 2
MSB1-PCZ138-0-04E | LLP02-IFC | 2021-08-20 | 2
MSB1-PCZ138-0-04F | LLP02-IFC | 2021-08-20 | 2
MSB1-PCZ142-0-04A | LLP02-IFC | 2021-08-20 | 1
MSB1-PCZ142-0-04B | LLP02-IFC | 2021-08-20 | 1
MSB1-PCZ147-0-04A | LLP02-IFC | 2021-08-20 | 1
MSB1-PCZ147-0-04B | LLP02-IFC | 2021-08-20 | 1
MSB1-TCV113-51-05A | LLP02-IFC | 2021-08-20 | 1
MSB1-TCV113-51-05B | LLP02-IFC | 2021-08-20 | 1
MSB1-TCV202-1A-30A | LLP02-IFC | 2021-08-20 | 1
MSB1-TCV201-1A-30B | LLP02-IFC | 2021-08-20 | 1
MSB1-TCV202-1B-30A | LLP02-IFC | 2021-08-20 | 1
MSB1-TCV202-1B-30B | LLP02-IFC | 2021-08-20 | 1
RA4-PCZ132-0-04A | LLP02-IFC | 2021-08-20 | 1
RA4-PCZ132-0-04B | LLP02-IFC | 2021-08-20 | 1
RA4-PCZ132-0-04C | LLP02-IFC | 2021-08-20 | 1
RA4-PCZ132-204-04G | LLP02-IFC | 2021-08-20 | 1
RA4-PCZ138-0-04A | LLP02-IFC | 2021-08-20 | 1
40_05_15_51_dat | LLP02-IFC | 2021-08-20 | 3
MS1-PMP113-4-00 | LLP02-IFC | 2021-08-20 | 1
MS1-PMP113-5-00 | LLP02-IFC | 2021-08-20 | 1
MS1-PMP113-6-00 | LLP02-IFC | 2021-08-20 | 1
RA4-PMP113-5-00 | LLP02-IFC | 2021-08-20 | 1
RA4-PMP113-6-00 | LLP02-IFC | 2021-08-20 | 1
RA4-PMP252-1-40 | LLP02-IFC | 2021-08-20 | 1
RA4-PMP252-2-40 | LLP02-IFC | 2021-08-20 | 1
43_11_29_61_dat | LLP02-IFC | 2021-08-20 | 1
RA4-VP221-03-00 | LLP02-IFC | 2021-08-20 | 1
43_21_16_21_dat | LLP02-IFC | 2021-08-20 | 3
MS1-PMP276-1-10 | LLP02-IFC | 2021-08-20 | 1
MS1-PMP276-2-10 | LLP02-IFC | 2021-08-20 | 1
43_41_13_10_dat | LLP02-IFC | 2021-08-20 | 1
43_41_16_03 | LLP02-IFC | 2021-08-20 | 1
43_41_16_04_dat | LLP02-IFC | 2021-08-20 | 2
D1X-249-D0-A01 | LLP02-R1-IFC | 2021-10-08 | 1
RA4-249-D0-A01 | LLP02-R1-IFC | 2021-10-08 | 1
25_14_01_00_DAT | LLP02-R1-IFC | 2021-10-08 | 1
RA4-PLC252-1-00 | LLP02-R1-IFC | 2021-10-08 | 2
RA4-ETAP252-1-00 | LLP02-R1-IFC | 2021-10-08 | 2
43_41_16_04 | LLP02-R1-IFC | 2021-10-08 | 1
MSB1-TK133-1-07 | LLP02-R1-IFC | 2021-10-08 | 2
00_01_00_00 | LLP03-IFC | 2021-10-26 | 7
MS1-400-D0-A02 | LLP03-IFC | 2021-10-26 | 3
MS1-402-D0-Z01 | LLP03-IFC | 2021-10-26 | 3
RA4-400-D0-A01 | LLP03-IFC | 2021-10-26 | 1
400-KSI-INTEL-AP-001 | LLP03-IFC | 2021-10-26 | 2
APOLLO-INTEL-AP-003 | LLP03-IFC | 2021-10-26 | 1
DM-UHP-FMS-G-V-BKT-9IN | LLP03-IFC | 2021-10-26 | 1
00_00_00_01 | LLP03-IFC | 2021-10-26 | 6
01_11_00_00 | LLP03-IFC | 2021-10-26 | 3
00_01_00_00 | LLP04-IFC | 2021-12-21 | 7
RA4-IE-3004 | LLP04-IFC | 2021-12-21 | 2
1810_VFD_09 | LLP04-IFC | 2021-12-21 | 3
25_14_01_00_HDRIO_0 | LLP04-IFC | 2021-12-21 | 2
25_14_01_00_HDRIO_1 | LLP04-IFC | 2021-12-21 | 2
25_14_01_00_HDRIO_2 | LLP04-IFC | 2021-12-21 | 2
25_14_01_00_HDRIO_3 | LLP04-IFC | 2021-12-21 | 2
25_14_01_00_PBDP_0 | LLP04-IFC | 2021-12-21 | 2
D-I-1910_23 | LLP04-IFC | 2021-12-21 | 4
00_00_00_01(00001) | LLP04-IFC | 2021-12-21 | 1
01_11_00_00(01110) | LLP04-IFC | 2021-12-21 | 1
25_14_01_00_DAT_03 | LLP04-IFC | 2021-12-21 | 5
RA4-RIO650-1A-09 | LLP04-IFC | 2021-12-21 | 1
RA4-RIO650-1B-09 | LLP04-IFC | 2021-12-21 | 1
RA4-LCP102-2-00 | LLP04-IFC | 2021-12-21 | 1
RA4-LCP650-4-90 | LLP04-IFC | 2021-12-21 | 1
RA4-JB650-11-90 | LLP04-IFC | 2021-12-21 | 1
RA4-JB650-15-90 | LLP04-IFC | 2021-12-21 | 1
RA4-JB650-16-90 | LLP04-IFC | 2021-12-21 | 1
RA4-JB650-17-90 | LLP04-IFC | 2021-12-21 | 1
RA4-JB650-18-90 | LLP04-IFC | 2021-12-21 | 1
26_29_65_00_app(16265) | LLP04-IFC | 2021-12-21 | 1
40_05_15_51_dat(15131) | LLP04-IFC | 2021-12-21 | 1
40_90_20_00_DAT | LLP04-IFC | 2021-12-21 | 2
MSB1-PDIT132-0-91FA | LLP04-IFC | 2021-12-21 | 1
MSB1-PDIT147-0-91FD | LLP04-IFC | 2021-12-21 | 1
MSB1-PDIT147-0-91FG | LLP04-IFC | 2021-12-21 | 1
DX-SA-4000 | MS01-IFC | 2021-07-02 | 3
DX-SA-4001 | MS01-IFC | 2021-07-02 | 3
DX-SA-4002 | MS01-IFC | 2021-07-02 | 3
DX-SA-4003 | MS01-IFC | 2021-07-02 | 3
DX-SA-4004 | MS01-IFC | 2021-07-02 | 3
DX-SA-4005 | MS01-IFC | 2021-07-02 | 3
MS1-SF-1SF-B0000 | MS01-IFC | 2021-07-02 | 2
MS1-SF-1SF-C0000 | MS01-IFC | 2021-07-02 | 2
MS1-SF-1SF-D0000 | MS01-IFC | 2021-07-02 | 2
MS1-SF-1SH-B0000 | MS01-IFC | 2021-07-02 | 2
MS1-SF-1SH-C0000 | MS01-IFC | 2021-07-02 | 2
MS1-SF-1SH-D0000 | MS01-IFC | 2021-07-02 | 2
MS1-SF-5RF-B0000 | MS01-IFC | 2021-07-02 | 2
MS1-SF-5RF-C0000 | MS01-IFC | 2021-07-02 | 2
MS1-SF-5RF-D0000 | MS01-IFC | 2021-07-02 | 2
RA4-SS-20A-D0000 | MS01-IFC | 2021-07-02 | 2
RA4-SS-20A-E0000 | MS01-IFC | 2021-07-02 | 2
RA4-SS-20A-F0000 | MS01-IFC | 2021-07-02 | 2
RA4-SS-20A-L0000 | MS01-IFC | 2021-07-02 | 2
RA4-SS-20A-M0000 | MS01-IFC | 2021-07-02 | 2
MS1-S0-1SF-4000 | MS01-IFC | 2021-07-02 | 4
MS1-S0-5RF-4000 | MS01-IFC | 2021-07-02 | 2
MS1-S0-6200 - SE | MS01-IFC | 2021-07-02 | 1
DX-SA-4000 | MS01-R1-IFC | 2021-07-23 | 3
DX-SA-4001 | MS01-R1-IFC | 2021-07-23 | 3
DX-SA-4002 | MS01-R1-IFC | 2021-07-23 | 3
DX-SA-4003 | MS01-R1-IFC | 2021-07-23 | 3
DX-SA-4004 | MS01-R1-IFC | 2021-07-23 | 3
DX-SA-4005 | MS01-R1-IFC | 2021-07-23 | 3
MS1-SF-1SF-B0000 | MS01-R1-IFC | 2021-07-23 | 2
MS1-SF-1SF-C0000 | MS01-R1-IFC | 2021-07-23 | 2
MS1-SF-1SF-D0000 | MS01-R1-IFC | 2021-07-23 | 2
MS1-SF-1SH-B0000 | MS01-R1-IFC | 2021-07-23 | 2
MS1-SF-1SH-C0000 | MS01-R1-IFC | 2021-07-23 | 2
MS1-SF-1SH-D0000 | MS01-R1-IFC | 2021-07-23 | 2
MS1-SF-5RF-B0000 | MS01-R1-IFC | 2021-07-23 | 2
MS1-SF-5RF-C0000 | MS01-R1-IFC | 2021-07-23 | 2
MS1-SF-5RF-D0000 | MS01-R1-IFC | 2021-07-23 | 2
RA4-SS-20A-D0000 | MS01-R1-IFC | 2021-07-23 | 2
RA4-SS-20A-E0000 | MS01-R1-IFC | 2021-07-23 | 2
RA4-SS-20A-F0000 | MS01-R1-IFC | 2021-07-23 | 2
RA4-SS-20A-L0000 | MS01-R1-IFC | 2021-07-23 | 2
RA4-SS-20A-M0000 | MS01-R1-IFC | 2021-07-23 | 2
MS1-S0-1SF-4000 | MS01-R1-IFC | 2021-07-23 | 4
MS1-S0-5RF-4000 | MS01-R1-IFC | 2021-07-23 | 2
MS1-S0-6200 | MS01-R1-IFC | 2021-07-23 | 1
DX-SA-4000 | MS02-IFC | 2021-08-13 | 3
DX-SA-4001 | MS02-IFC | 2021-08-13 | 3
DX-SA-4002 | MS02-IFC | 2021-08-13 | 3
DX-SA-4003 | MS02-IFC | 2021-08-13 | 3
DX-SA-4004 | MS02-IFC | 2021-08-13 | 3
DX-SA-4005 | MS02-IFC | 2021-08-13 | 3
MS1-SS-5RC-B0000 | MS02-IFC | 2021-08-13 | 6
MS1-SS-5RF-B0000 | MS02-IFC | 2021-08-13 | 1
MS1-SS-5RF-C0000 | MS02-IFC | 2021-08-13 | 5
MS1-SS-5RF-D0000 | MS02-IFC | 2021-08-13 | 1
MS1-SS-5RL-B0000 | MS02-IFC | 2021-08-13 | 1
MS1-SS-5RL-D0000 | MS02-IFC | 2021-08-13 | 1
MS1-SS-5RM-B0000 | MS02-IFC | 2021-08-13 | 1
MS1-SS-5RM-C0000 | MS02-IFC | 2021-08-13 | 1
MS1-SS-5RM-D0000 | MS02-IFC | 2021-08-13 | 1
MS1-SS-5RO-B0000 | MS02-IFC | 2021-08-13 | 2
MS1-SS-5RS-B0000 | MS02-IFC | 2021-08-13 | 4
MS1-SS-5RW-B0000 | MS02-IFC | 2021-08-13 | 1
MS1-SS-5RW-C0000 | MS02-IFC | 2021-08-13 | 1
MS1-SS-5RW-D0000 | MS02-IFC | 2021-08-13 | 1
MS1-SS-5RZ-B0000 | MS02-IFC | 2021-08-13 | 1
MS1-S0-6201 | MS02-IFC | 2021-08-13 | 2
MS1-S0-6210 | MS02-IFC | 2021-08-13 | 6
MS1-S0-6211 | MS02-IFC | 2021-08-13 | 3
RA4-SS-40A-D0000 | MS02-IFC | 2021-08-13 | 1
RA4-SS-40A-K0000 | MS02-IFC | 2021-08-13 | 1
RA4-SS-40B-D0000 | MS02-IFC | 2021-08-13 | 1
RA4-SS-40B-K0000 | MS02-IFC | 2021-08-13 | 1
RA4-SS-40C-K0000 | MS02-IFC | 2021-08-13 | 1
RA4-SS-40E-K0000 | MS02-IFC | 2021-08-13 | 1
RA4-SS-40F-D0000 | MS02-IFC | 2021-08-13 | 1
RA4-SS-40G-D0000 | MS02-IFC | 2021-08-13 | 1
RA4-SS-40G-K0000 | MS02-IFC | 2021-08-13 | 1
RA4-SS-50A-D0000 | MS02-IFC | 2021-08-13 | 1
RA4-SS-50A-K0000 | MS02-IFC | 2021-08-13 | 1
RA4-S0-6210 | MS02-IFC | 2021-08-13 | 1
RA4-S0-6211 | MS02-IFC | 2021-08-13 | 1
RA4-S0-6212 | MS02-IFC | 2021-08-13 | 1
RA4-S0-6213 | MS02-IFC | 2021-08-13 | 1
RA4-S0-6230 | MS02-IFC | 2021-08-13 | 1
MS1-SS-3IA-A0D00 | CPK03-R11-IFC | 2022-03-04 | 1
MS1-S0-6228 | CPK03-R11-IFC | 2022-03-04 | 1
MS1-S0-6229 | CPK03-R11-IFC | 2022-03-04 | 1
MS1-S0-6230 | CPK03-R11-IFC | 2022-03-04 | 1
MS1-S0-6231 | CPK03-R11-IFC | 2022-03-04 | 1
MS1-SS-2FA-B01A0 | CPK03-R11-IFC | 2022-03-04 | 1
MS1-SS-3IA-4000 | CPK03-R11-IFC | 2022-03-04 | 1
MS1-S0-0010 | CPK03-R11-IFC | 2022-03-04 | 8
MS1-SS-2FD-C0100 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-SS-2FD-D0200 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-SS-2FK-B0000 | CPK03-R11-IFC | 2022-03-04 | 4
MS1-SS-2FM-B0300 | CPK03-R11-IFC | 2022-03-04 | 4
MS1-SS-3FB-4000 | CPK03-R11-IFC | 2022-03-04 | 1
MS1-SS-4DA-C0100 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-SS-5RC-B0000 | CPK03-R11-IFC | 2022-03-04 | 6
MS1-S0-5RC-B0400 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-SS-5RE-B0000 | CPK03-R11-IFC | 2022-03-04 | 4
MS1-SS-5RE-4000 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-SS-5RE-4001 | CPK03-R11-IFC | 2022-03-04 | 1
MS1-SS-5RK-B0000 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-SS-5RW-4000 | CPK03-R11-IFC | 2022-03-04 | 1
MS1-SS-5RX-4000 | CPK03-R11-IFC | 2022-03-04 | 1
MS1-S0-6210 | CPK03-R11-IFC | 2022-03-04 | 6
MS1-S0-6225 | CPK03-R11-IFC | 2022-03-04 | 1
MS1-S0-6226 | CPK03-R11-IFC | 2022-03-04 | 1
MS1-S0-6227 | CPK03-R11-IFC | 2022-03-04 | 1
MS1-AO-0723 | CPK03-R11-IFC | 2022-03-04 | 1
MS1-AC-2FA-B0000 | CPK03-R11-IFC | 2022-03-04 | 4
MS1-AI-0107 | CPK03-R11-IFC | 2022-03-04 | 4
MS1-AW-1SA-A0D00 | CPK03-R11-IFC | 2022-03-04 | 3
MS1-AW-1SA-B0000 | CPK03-R11-IFC | 2022-03-04 | 3
MS1-AW-1SA-C0000 | CPK03-R11-IFC | 2022-03-04 | 3
MS1-AW-2FA-A0D00 | CPK03-R11-IFC | 2022-03-04 | 4
MS1-AW-2FA-B0000 | CPK03-R11-IFC | 2022-03-04 | 4
MS1-AW-2FM-B0000 | CPK03-R11-IFC | 2022-03-04 | 3
MS1-AW-2FM-C0000 | CPK03-R11-IFC | 2022-03-04 | 3
MS1-AW-2FM-D0000 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-AZ-0200 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-AZ-0201 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-AZ-0202 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-AZ-0203 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-AZ-0204 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-AZ-0205 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-138-MX-A01 | CPK03-R11-IFC | 2022-03-04 | 1
MS1-138-MX-A01-D | CPK03-R11-IFC | 2022-03-04 | 1
MS1-MH-0150 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-ES-1153D | CPK03-R11-IFC | 2022-03-04 | 2
MS1-ES-1154D | CPK03-R11-IFC | 2022-03-04 | 2
MS1-ES-1301 | CPK03-R11-IFC | 2022-03-04 | 3
MS1-ES-1304 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-ES-1314B | CPK03-R11-IFC | 2022-03-04 | 3
MS1-ES-1326B | CPK03-R11-IFC | 2022-03-04 | 3
MS1-ES-1343A | CPK03-R11-IFC | 2022-03-04 | 2
MS1-ES-1344B | CPK03-R11-IFC | 2022-03-04 | 3
MS1-HF-0100-D | CPK03-R11-IFC | 2022-03-04 | 1
RAC-HF-0001 | CPK03-R11-IFC | 2022-03-04 | 3
RAC-HH-0001 | CPK03-R11-IFC | 2022-03-04 | 2
RAC-HS-0001 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-H0-5103 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-H0-5109 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-H0-6103 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-H0-6109 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-HC-1SA-B0000 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-HF-1SA-B0000 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-HF-1SA-C0000 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-HF-1SA-C0000-D | CPK03-R11-IFC | 2022-03-04 | 1
MS1-HF-1SA-D0000 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-HF-1SA-D0000-D | CPK03-R11-IFC | 2022-03-04 | 1
MS1-HF-2FA-C0000 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-HF-2FA-D0000 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-HF-5RA-B0000 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-HF-5RA-C0000 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-HW-1SA-B0000 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-HH-1SB-B0000 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-HS-1SA-B0000 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-HF-0100 | CPK03-R11-IFC | 2022-03-04 | 3
MS1-HF-0101 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-HF-0102 | CPK03-R11-IFC | 2022-03-04 | 3
MS1-HF-0154 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-HF-0157 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-HF-0158 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-HF-1082 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-HF-1084 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-HF-3000C | CPK03-R11-IFC | 2022-03-04 | 2
MS1-HF-3001A | CPK03-R11-IFC | 2022-03-04 | 1
RA3-HF-3000C | CPK03-R11-IFC | 2022-03-04 | 3
MS1-IE-1SA-C0000 | CPK03-R11-IFC | 2022-03-04 | 5
MS1-IE-1SA-D0000 | CPK03-R11-IFC | 2022-03-04 | 5
MS1-IE-3FA-B0000 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-IE-3FA-C0000 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-IE-3FA-D0000 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-IE-4DA-B0000 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-IE-4DA-C0000 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-IE-4DA-D0000 | CPK03-R11-IFC | 2022-03-04 | 1
MS1-TC-1SA-B0000 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-TC-1SA-C0000 | CPK03-R11-IFC | 2022-03-04 | 3
MS1-TC-1SA-D0000 | CPK03-R11-IFC | 2022-03-04 | 3
MS1-TC-2FA-B0000 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-TC-2FA-C0000 | CPK03-R11-IFC | 2022-03-04 | 3
MS1-TC-2FA-D0000 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-TT-1SA-C0000 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-TT-1SA-D0000 | CPK03-R11-IFC | 2022-03-04 | 2
RAC-T0-0001 | CPK03-R11-IFC | 2022-03-04 | 4
RAC-T0-9001 | CPK03-R11-IFC | 2022-03-04 | 4
RAC-T0-9002 | CPK03-R11-IFC | 2022-03-04 | 3
RAC-T0-9004 | CPK03-R11-IFC | 2022-03-04 | 3
MS1-TC-1454 | CPK03-R11-IFC | 2022-03-04 | 2
D1X-138-D0-A29 | CPK03-R11-IFC | 2022-03-04 | 3
D1X-138-D0-Z01 | CPK03-R11-IFC | 2022-03-04 | 1
D1X-138-D0-Z01-D | CPK03-R11-IFC | 2022-03-04 | 1
D1X-245-D0-B01 | CPK03-R11-IFC | 2022-03-04 | 2
D1X-245-D0-B02 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-101-D0-A06 | CPK03-R11-IFC | 2022-03-04 | 3
MS1-132-D0-A01 | CPK03-R11-IFC | 2022-03-04 | 1
MS1-132-D0-A02 | CPK03-R11-IFC | 2022-03-04 | 1
MS1-132-D0-A02-D | CPK03-R11-IFC | 2022-03-04 | 1
MS1-132-D0-Z01 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-132-D0-Z03 | CPK03-R11-IFC | 2022-03-04 | 3
MS1-138-D0-Z01 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-138-D0-Z01-D | CPK03-R11-IFC | 2022-03-04 | 1
MS1-138-D0-Z03 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-237-D0-Z01 | CPK03-R11-IFC | 2022-03-04 | 3
MS1-237-D0-Z01-D | CPK03-R11-IFC | 2022-03-04 | 1
MS1-245-D0-Z01 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-245-D0-Z07 | CPK03-R11-IFC | 2022-03-04 | 2
MS1-608-D0-A01 | CPK03-R11-IFC | 2022-03-04 | 2
RA4-138-D0-Z01 | CPK03-R11-IFC | 2022-03-04 | 1
RA4-138-D0-Z02 | CPK03-R11-IFC | 2022-03-04 | 1
RA-ST-0001 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-0002 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-0003 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-0004 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-0005 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-0006 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-0007 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-0008 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-0009 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-0010 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-0011 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-0012 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-0013 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-0014 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-0015 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-0016 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-0017 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-0018 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-0019 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-0020 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-0021 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-0022 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-0500 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-0501 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-0502 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-0503 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-0504 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-0505 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-0506 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-1000 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-1001 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-1002 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-1003 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-1004 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-1005 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-1006 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-1008 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-1009 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-1010 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-1011 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-1012 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-1013 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-1014 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-1015 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-1016 | CPK03-R11-IFC | 2022-03-04 | 4
RA-ST-1017 | CPK03-R11-IFC | 2022-03-04 | 4
RA-ST-1018 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-1022 | CPK03-R11-IFC | 2022-03-04 | 4
RA-ST-1023 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-1024 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-1025 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-1026 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-1027 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-1028 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-1029 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-1030 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-1031 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-1032 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-1033 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2000 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-2001 | CPK03-R11-IFC | 2022-03-04 | 7
RA-ST-2002 | CPK03-R11-IFC | 2022-03-04 | 7
RA-ST-2003 | CPK03-R11-IFC | 2022-03-04 | 7
RA-ST-2004 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2005 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2006 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-2007 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-2008 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-2009 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2010 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2011 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2012 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-2013 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-2014 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-2015 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-2016 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-2017 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2018 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2019 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2020 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2021 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2022 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2023 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2024 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-2025 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2026 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2027 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2028 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-2029 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2030 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2031 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2032 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-2033 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2034 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2035 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2036 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2037 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-203 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2039 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2040 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2041 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2042 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-2043 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2044 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-2045 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2046 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2047 | CPK03-R11-IFC | 2022-03-04 | 7
RA-ST-2048 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2049 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2050 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2051 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2052 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2053 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2054 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2055 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2056 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2057 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2058 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2059 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2060 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2061 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2062 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2063 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2064 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2065 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2066 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2067 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2068 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2069 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2070 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2071 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2072 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2073 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2074 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2075 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2076 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2077 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2078 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2079 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2080 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2081 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2082 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2083 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2084 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2085 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2086 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2087 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2088 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2089 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2090 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2091 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2092 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2093 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2094 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2095 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2096 | CPK03-R11-IFC | 2022-03-04 | 7
RA-ST-2097 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2098 | CPK03-R11-IFC | 2022-03-04 | 7
RA-ST-2099 | CPK03-R11-IFC | 2022-03-04 | 7
RA-ST-2100 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2101 | CPK03-R11-IFC | 2022-03-04 | 7
RA-ST-2102 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2103 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-2104 | CPK03-R11-IFC | 2022-03-04 | 7
RA-ST-2105 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2106 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2107 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2108 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2109 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2110 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2111 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2112 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2113 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2114 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2115 | CPK03-R11-IFC | 2022-03-04 | 7
RA-ST-2116 | CPK03-R11-IFC | 2022-03-04 | 7
RA-ST-2117 | CPK03-R11-IFC | 2022-03-04 | 7
RA-ST-2118 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2119 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2120 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2121 | CPK03-R11-IFC | 2022-03-04 | 7
RA-ST-2122 | CPK03-R11-IFC | 2022-03-04 | 7
RA-ST-2123 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2124 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2125 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2126 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2127 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2128 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2129 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2130 | CPK03-R11-IFC | 2022-03-04 | 7
RA-ST-2131 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2133 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2134 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2135 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2136 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2137 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2138 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2139 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2140 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2141 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2142 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2143 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2144 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2145 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2146 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2147 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2148 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2149 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2150 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2151 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2152 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2153 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2157 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2158 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2160 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2161 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2163 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2164 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2165 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2166 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2167 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-2168 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2169 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2170 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2171 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2172 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2173 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2174 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2175 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2176 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-2177 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2178 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2179 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2180 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2181 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-2182 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2183 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-2184 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2185 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST-2186 | CPK03-R11-IFC | 2022-03-04 | 4
RA-ST-2187 | CPK03-R11-IFC | 2022-03-04 | 4
RA-ST-2188 | CPK03-R11-IFC | 2022-03-04 | 4
RA-ST-2189 | CPK03-R11-IFC | 2022-03-04 | 4
RA-ST-2190 | CPK03-R11-IFC | 2022-03-04 | 4
RA-ST-2191 | CPK03-R11-IFC | 2022-03-04 | 4
RA-ST-2192 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-2193 | CPK03-R11-IFC | 2022-03-04 | 4
RA-ST-2194 | CPK03-R11-IFC | 2022-03-04 | 4
RA-ST-2195 | CPK03-R11-IFC | 2022-03-04 | 4
RA-ST-2196 | CPK03-R11-IFC | 2022-03-04 | 4
RA-ST-2197 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-2198 | CPK03-R11-IFC | 2022-03-04 | 4
RA-ST-2199 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-2200 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-2201 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-2202 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2203 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2204 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-2205 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-2206 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-2207 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-2208 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-2209 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-2210 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-2211 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2212 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2213 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2214 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2215 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2216 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2217 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2218 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-2219 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-2220 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-2221 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2222 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-2223 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-2224 | CPK03-R11-IFC | 2022-03-04 | 3
RA-ST-2225 | CPK03-R11-IFC | 2022-03-04 | 4
RA-ST-2226 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2227 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2228 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2229 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2230 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-2231 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2232 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2233 | CPK03-R11-IFC | 2022-03-04 | 4
RA-ST-2234 | CPK03-R11-IFC | 2022-03-04 | 4
RA-ST-2235 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2237 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2238 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2239 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-2240 | CPK03-R11-IFC | 2022-03-04 | 4
RA-ST-2241 | CPK03-R11-IFC | 2022-03-04 | 4
RA-ST-2242 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-2243 | CPK03-R11-IFC | 2022-03-04 | 6
RA-ST-2245 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2246 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2247 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2248 | CPK03-R11-IFC | 2022-03-04 | 4
RA-ST-2249 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2250 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2251 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2252 | CPK03-R11-IFC | 2022-03-04 | 4
RA-ST-2253 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2254 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2255 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2256 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2257 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2258 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2260 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2261 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2262 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2263 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2264 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2265 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2266 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2267 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2268 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2269 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2270 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2271 | CPK03-R11-IFC | 2022-03-04 | 3
RA-ST-2272 | CPK03-R11-IFC | 2022-03-04 | 3
RA-ST-2277 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2278 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2279 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2280 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2281 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2282 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2283 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2284 | CPK03-R11-IFC | 2022-03-04 | 4
RA-ST-2285 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2286 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2287 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2288 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2289 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2290 | CPK03-R11-IFC | 2022-03-04 | 1
RA-ST-2291 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2292 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2293 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2294 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2295 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2296 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2297 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2298 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2299 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-2300 | CPK03-R11-IFC | 2022-03-04 | 3
RA-ST-2301 | CPK03-R11-IFC | 2022-03-04 | 3
RA-ST-2303 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2304 | CPK03-R11-IFC | 2022-03-04 | 3
RA-ST-2305 | CPK03-R11-IFC | 2022-03-04 | 3
RA-ST-2308 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2309 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2310 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2311 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2312 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2313 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2314 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2315 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2316 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2317 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2318 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2319 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2320 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2321 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2322 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2323 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2325 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2326 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2327 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2328 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2329 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2330 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2331 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2332 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2333 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-2334 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-3000 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-3001 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-3002 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-3005 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-3006 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-3008 | CPK03-R11-IFC | 2022-03-04 | 8
RA-ST--3009 | CPK03-R11-IFC | 2022-03-04 | 1
RA-ST-3010 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-3011 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-3012 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-3013 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-3014 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-3015 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-3016 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-3017 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-3019 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-3020 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-4000 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-4001 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-4002 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-4003 | CPK03-R11-IFC | 2022-03-04 | 9
RA-ST-4004 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-4005 | CPK03-R11-IFC | 2022-03-04 | 4
RA-ST-4006 | CPK03-R11-IFC | 2022-03-04 | 4
RA-ST-4007 | CPK03-R11-IFC | 2022-03-04 | 4
RA-ST-4008 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-4009 | CPK03-R11-IFC | 2022-03-04 | 4
RA-ST-4010 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-4011 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-4012 | CPK03-R11-IFC | 2022-03-04 | 5
RA-ST-4013 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-4014 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-4015 | CPK03-R11-IFC | 2022-03-04 | 2
RA-ST-4016 | CPK03-R11-IFC | 2022-03-04 | 2
RA-AR-D1617 | CPK03-R11-IFC | 2022-03-04 | 3
RA-AR-D2506 | CPK03-R11-IFC | 2022-03-04 | 3
RA-AR-D2427 | CPK03-R11-IFC | 2022-03-04 | 1
RA-AR-D2426 | CPK03-R11-IFC | 2022-03-04 | 1
RA-AR-D2428 | CPK03-R11-IFC | 2022-03-04 | 1
RA-AR-D2504 | CPK03-R11-IFC | 2022-03-04 | 3
CMXR1Q56B-911 | CPK03-R11-IFC | 2022-03-04 | 1
MXD2H57B-L7-OHV-1 | CPK03-R11-IFC | 2022-03-04 | 1
SCC-RB318 | CPK03-R11-IFC | 2022-03-04 | 1
SCR-RB311 | CPK03-R11-IFC | 2022-03-04 | 1
SCR-RB313 | CPK03-R11-IFC | 2022-03-04 | 1
D-H-1840-LSS-MDP-H33 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1840-LSS-MDP-H34 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1840-LSS-MDP-H35 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-001-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-100-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-101-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-105-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-110-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-115-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-200-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-201-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-202-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-204-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-206-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-207-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-210-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-211-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-215-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-250-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-255-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-256-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-260-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-261-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-270-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-271-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-275-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-276-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-300-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-301-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-302-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-303-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-304-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-305-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-306-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-310-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-311-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-312-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-350-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-360-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-365-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-366-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-FIRE-375-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-LSS-MDP-F01 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-LSS-MDP-F02 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-LSS-MDP-F03 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-LSS-MDP-F04 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-LSS-MDP-F05 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1841-LSS-MDP-F06 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1842-TAS-203-MDP | CPK03-R11-IFC | 2022-03-04 | 2
D-H-1842-LSS-MDP-H09 | CPK03-R11-IFC | 2022-03-04 | 2
D-H-1842-LSS-MDP-H52 | CPK03-R11-IFC | 2022-03-04 | 2
D-H-1842-LSS-MDP-H52A | CPK03-R11-IFC | 2022-03-04 | 2
D-H-1842-LSS-MDP-H70 | CPK03-R11-IFC | 2022-03-04 | 2
D-H-1842-LSS-MDP-H70A | CPK03-R11-IFC | 2022-03-04 | 2
D-H-1842-LSS-MDP-H71 | CPK03-R11-IFC | 2022-03-04 | 2
D-H-1842-LSS-MDP-H72 | CPK03-R11-IFC | 2022-03-04 | 2
D-H-1842-LSS-MDP-H72A | CPK03-R11-IFC | 2022-03-04 | 2
D-H-1842-TAS-100-MDP | CPK03-R11-IFC | 2022-03-04 | 2
D-H-1842-TAS-200-MDP | CPK03-R11-IFC | 2022-03-04 | 2
D-H-1842-TAS-201-MDP | CPK03-R11-IFC | 2022-03-04 | 2
D-H-1842-TAS-202-MDP | CPK03-R11-IFC | 2022-03-04 | 2
D-H-1844-HPM-001-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-HPM-320-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-HPM-322-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-HPM-323-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-HPM-325-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-HPM-326-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-HPM-327-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-HPM-328-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-HPM-329-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-HPM-330-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-HPM-538-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-HPM-539-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-HPM-540-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-HPM-585-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-HPM-703-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-HPM-704-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-HPM-705-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-HPM-707-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-HPM-708-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-HPM-711-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-HPM-713-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-HPM-714-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-HPM-715-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-HPM-716-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-HPM-717-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-HPM-718-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-HPM-719-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H01 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H02 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H03 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H05 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H06 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H07 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H08 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H15 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H16 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H20 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H21 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H22 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H23 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H24 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H25 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H26 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H27 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H30 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H31 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H32 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H33 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H34 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H35 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H50 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H50A | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H55 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H55A | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H55B | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H56 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H56A | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H56B | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H57 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H58 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H58A | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H58B | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H59 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H59A | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H60 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H60A | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H61 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H61A | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H61B | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H61C | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H62 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H62A | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H62B | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H63 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H63A | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H63B | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H64 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H64A | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H64B | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H80 | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-LSS-MDP-H80A | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1845-HPM-402-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1845-HPM-403-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1845-HPM-404-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1845-HPM-405-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1845-HPM-406-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1845-HPM-410-MDP | CPK03-R11-IFC | 2022-03-04 | 4
D-H-1845-HPM-411-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1846-EWS-100-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1846-EWS-201-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1846-EWS-202-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1846-EWS-204-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1846-EWS-205-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1846-EWS-301-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1846-FIRE-150-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1846-FIRE-151-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1846-FIRE-152-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1846-FIRE-155-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1846-FIRE-156-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1846-FIRE-157-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1846-FIRE-158-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1846-FIRE-160-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1846-FIRE-161-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1846-FIRE-162-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1846-FIRE-163-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1846-FIRE-164-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1846-FIRE-165-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1846-FIRE-166-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1846-FIRE-167-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1846-FIRE-168-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1846-FIRE-170-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1846-FIRE-171-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1846-FIRE-172-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1846-FIRE-173-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1846-FIRE-174-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-HPM-725-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1844-HPM-726-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-126-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-128-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-130-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-146-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-160-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-161-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-162-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-163-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-164E-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-164-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-164M-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-165E-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-165-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-165M-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-166-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-167-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-168-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-169-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-170-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-171-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-172-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-173-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-174-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-203-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-252E-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-252-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-252M-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-253-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-254-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-255-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-261-MDP | CPK03-R11-IFC | 2022-03-04 | 3
D-H-1848-HPM-270-MDP | CPK03-R11-IFC | 2022-03-04 | 3
MSB1-PCZ132-0-04H | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-PCZ132-0-04J | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-PCZ132-0-04K | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-PCZ138-0-04G | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-PCZ138-0-04H | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-TCV104-1-00A | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-TCV104-2-00A | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-TCV104-3-00A | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-TCV104-4-00A | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-TCV104-5-00A | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-TCV104-5-20A | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-TCV104-6-00A | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-TCV104-6-20A | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-TCV104-7-00A | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-TCV104-7-20A | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-TCV104-8-00A | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-TCV104-8-20A | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-TCV104-9-00A | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-TCV104-9-20A | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-TCV104-10-00A | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-TCV104-11-00A | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-TCV104-12-00A | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-TCV104-13-00A | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-TCV104-14-00A | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-TCV104-15-00A | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-PDIT132-0-00AA | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-PDIT132-0-00AB | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-PDIT132-0-00AC | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-PDIT132-0-00AD | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-PDIT132-0-00AE | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-PDIT132-0-00AF | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-PDIT132-0-00AG | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-PDIT132-0-00AH | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-PDIT132-0-00AJ | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-PDIT132-0-00AK | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-PDIT132-0-00AL | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-PDIT132-0-00AM | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-PDIT132-0-00AN | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-PDIT132-0-00AP | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-PDIT132-0-00W | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-PDIT132-0-00X | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-PDIT138-0-00T | CPK03-R11-IFC | 2022-03-04 | 1
MSB1-PDIT138-0-00U | CPK03-R11-IFC | 2022-03-04 | 1
MS1-AC-2FH-B0000 | CPK03-R11-ADD01-IFC | 2022-03-16 | 5
MS1-AC-2FH-B0000-S | CPK03-R11-ADD01-IFC | 2022-03-16 | 5
RA4-S0-6285 | CPK03-R12-IFC | 2022-03-21 | 1
RA4-SS-2FA-E0100 | CPK03-R12-IFC | 2022-03-21 | 1
MS1-S0-0010 | CPK03-R12-IFC | 2022-03-21 | 8
MS1-SS-1SF-4001 | CPK03-R12-IFC | 2022-03-21 | 2
MS1-SS-1SJ-4000 | CPK03-R12-IFC | 2022-03-21 | 2
MS1-SS-1SD-4000 | CPK03-R12-IFC | 2022-03-21 | 1
MS1-SS-2FG-C02B0 | CPK03-R12-IFC | 2022-03-21 | 2
MS1-SS-2FK-C02B0 | CPK03-R12-IFC | 2022-03-21 | 2
MS1-S0-6218 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-0001 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-0002 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-0003 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-0004 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-0005 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-0006 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-0007 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-0008 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-0009 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-0010 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-0011 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-0012 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-0013 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-0014 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-0015 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-0016 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-0017 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-0018 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-0019 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-0020 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-0021 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-0022 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-0500 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-0501 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-0502 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-0503 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-0504 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-0505 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-0506 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-1000 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-1001 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-1002 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-1003 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-1004 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-1005 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-1006 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-1008 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-1009 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-1010 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-1011 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-1012 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-1013 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-1014 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-1015 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-1016 | CPK03-R12-IFC | 2022-03-21 | 4
RA-ST-1017 | CPK03-R12-IFC | 2022-03-21 | 4
RA-ST-1018 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-1022 | CPK03-R12-IFC | 2022-03-21 | 4
RA-ST-1023 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-1024 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-1025 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-1026 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-1027 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-1028 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-1029 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-1030 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-1031 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-1032 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-1033 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2000 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-2001 | CPK03-R12-IFC | 2022-03-21 | 7
RA-ST-2002 | CPK03-R12-IFC | 2022-03-21 | 7
RA-ST-2003 | CPK03-R12-IFC | 2022-03-21 | 7
RA-ST-2004 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2005 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2006 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-2007 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-2008 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-2009 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2010 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2011 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2012 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-2013 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-2014 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-2015 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-2016 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-2017 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2018 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2019 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2020 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2021 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2022 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2023 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2024 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-2025 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2026 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2027 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2028 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-2029 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2030 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2031 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2032 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-2033 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2034 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2035 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2036 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2037 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2038 | CPK03-R12-IFC | 2022-03-21 | 3
RA-ST-2039 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2040 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2041 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2042 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-2043 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2044 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-2045 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2046 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2047 | CPK03-R12-IFC | 2022-03-21 | 7
RA-ST-2048 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2049 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2050 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2051 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2052 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2053 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2054 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2055 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2056 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2057 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2058 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2059 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2060 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2061 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2062 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2063 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2064 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2065 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2066 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2067 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2068 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2069 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2070 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2071 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2072 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2073 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2074 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2075 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2076 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2077 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2078 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2079 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2080 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2081 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2082 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2083 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2084 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2085 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2086 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2087 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2088 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2089 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2090 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2091 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2092 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2093 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2094 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2095 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2096 | CPK03-R12-IFC | 2022-03-21 | 7
RA-ST-2097 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2098 | CPK03-R12-IFC | 2022-03-21 | 7
RA-ST-2099 | CPK03-R12-IFC | 2022-03-21 | 7
RA-ST-2100 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2101 | CPK03-R12-IFC | 2022-03-21 | 7
RA-ST-2102 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2103 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-2104 | CPK03-R12-IFC | 2022-03-21 | 7
RA-ST-2105 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2106 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2107 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2108 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2109 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2110 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2111 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2112 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2113 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2114 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2115 | CPK03-R12-IFC | 2022-03-21 | 7
RA-ST-2116 | CPK03-R12-IFC | 2022-03-21 | 7
RA-ST-2117 | CPK03-R12-IFC | 2022-03-21 | 7
RA-ST-2118 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2119 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2120 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2121 | CPK03-R12-IFC | 2022-03-21 | 7
RA-ST-2122 | CPK03-R12-IFC | 2022-03-21 | 7
RA-ST-2123 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2124 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2125 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2126 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2127 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2128 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2129 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2130 | CPK03-R12-IFC | 2022-03-21 | 7
RA-ST-2131 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2133 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2134 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2135 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2136 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2137 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2138 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2139 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2140 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2141 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2142 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2143 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2144 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2145 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2146 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2147 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2148 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2149 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2150 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2151 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2152 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2153 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2157 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2158 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2160 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2161 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2163 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2164 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2165 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2166 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2167 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-2168 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2169 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2170 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2171 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2172 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2173 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2174 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2175 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2176 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-2177 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2178 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2179 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2180 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2181 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-2182 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2183 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-2184 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2185 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-2186 | CPK03-R12-IFC | 2022-03-21 | 4
RA-ST-2187 | CPK03-R12-IFC | 2022-03-21 | 4
RA-ST-2188 | CPK03-R12-IFC | 2022-03-21 | 4
RA-ST-2189 | CPK03-R12-IFC | 2022-03-21 | 4
RA-ST-2190 | CPK03-R12-IFC | 2022-03-21 | 4
RA-ST-2191 | CPK03-R12-IFC | 2022-03-21 | 4
RA-ST-2192 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-2193 | CPK03-R12-IFC | 2022-03-21 | 4
RA-ST-2194 | CPK03-R12-IFC | 2022-03-21 | 4
RA-ST-2195 | CPK03-R12-IFC | 2022-03-21 | 4
RA-ST-2196 | CPK03-R12-IFC | 2022-03-21 | 4
RA-ST-2197 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-2198 | CPK03-R12-IFC | 2022-03-21 | 4
RA-ST-2199 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-2200 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-2201 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-2202 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2203 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2204 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-2205 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-2206 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-2207 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-2208 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-2209 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-2210 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-2211 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2212 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2213 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2214 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2215 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2216 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2217 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2218 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-2219 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-2220 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-2221 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2222 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-2223 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-2224 | CPK03-R12-IFC | 2022-03-21 | 3
RA-ST-2225 | CPK03-R12-IFC | 2022-03-21 | 4
RA-ST-2226 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2227 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2228 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2229 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2230 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-2231 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2232 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2233 | CPK03-R12-IFC | 2022-03-21 | 4
RA-ST-2234 | CPK03-R12-IFC | 2022-03-21 | 4
RA-ST-2235 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2237 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2238 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2239 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-2240 | CPK03-R12-IFC | 2022-03-21 | 4
RA-ST-2241 | CPK03-R12-IFC | 2022-03-21 | 4
RA-ST-2242 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-2243 | CPK03-R12-IFC | 2022-03-21 | 6
RA-ST-2245 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2246 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2247 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2248 | CPK03-R12-IFC | 2022-03-21 | 4
RA-ST-2249 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2250 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2251 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2252 | CPK03-R12-IFC | 2022-03-21 | 4
RA-ST-2253 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2254 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2255 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2256 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2257 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2258 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2260 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2261 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2262 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2263 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2264 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2265 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2266 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2267 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2268 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2269 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2270 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2271 | CPK03-R12-IFC | 2022-03-21 | 3
RA-ST-2272 | CPK03-R12-IFC | 2022-03-21 | 3
RA-ST-2277 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2278 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2279 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2280 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2281 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2282 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2283 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2284 | CPK03-R12-IFC | 2022-03-21 | 4
RA-ST-2285 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2286 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2287 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2288 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2289 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2291 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2292 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2293 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2294 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2295 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2296 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2297 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2298 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2299 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-2300 | CPK03-R12-IFC | 2022-03-21 | 3
RA-ST-2301 | CPK03-R12-IFC | 2022-03-21 | 3
RA-ST-2303 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2304 | CPK03-R12-IFC | 2022-03-21 | 3
RA-ST-2305 | CPK03-R12-IFC | 2022-03-21 | 3
RA-ST-2308 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2309 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2310 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2311 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2312 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2313 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2314 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2315 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2316 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2317 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2318 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2319 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2320 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2321 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2322 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2323 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2325 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2326 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2327 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2328 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2329 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2330 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2331 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2332 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2333 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2334 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-2335 | CPK03-R12-IFC | 2022-03-21 | 1
RA-ST-2336 | CPK03-R12-IFC | 2022-03-21 | 1
RA-ST-2344 | CPK03-R12-IFC | 2022-03-21 | 1
RA-ST-3000 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-3001 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-3002 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-3005 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-3006 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-3008 | CPK03-R12-IFC | 2022-03-21 | 8
RA-ST-3009 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-3010 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-3011 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-3012 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-3013 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-3014 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-3015 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-3016 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-3017 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-3019 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-3020 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-4000 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-4001 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-4002 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-4003 | CPK03-R12-IFC | 2022-03-21 | 9
RA-ST-4004 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-4005 | CPK03-R12-IFC | 2022-03-21 | 4
RA-ST-4006 | CPK03-R12-IFC | 2022-03-21 | 4
RA-ST-4007 | CPK03-R12-IFC | 2022-03-21 | 4
RA-ST-4008 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-4009 | CPK03-R12-IFC | 2022-03-21 | 4
RA-ST-4010 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-4011 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-4012 | CPK03-R12-IFC | 2022-03-21 | 5
RA-ST-4013 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-4014 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-4015 | CPK03-R12-IFC | 2022-03-21 | 2
RA-ST-4016 | CPK03-R12-IFC | 2022-03-21 | 2
Formulas:
Date Issued = XLOOKUP([PKG-CODE], '1 PACKAGE OWNERS'!R:R,'1 PACKAGE OWNERS'!D:D,"ERR",0,1)
Filter for "RA4-"
Filter for "MS1-"

## 3 RFI Log
RFI No. | Subject | Date Created | Date Required | Date Answered | Status | From Contact | Posted By? | Date Posted | Notes | PACKAGES | Incorrect (Push To PE) | Slip Sheet Required | Manual Override | In Cold Storage | CMiC Export Date: | 2022-03-03
21029900-0001 | CSA - MSB_RA4 - Post-Installed Anchors at Waffle Slabs | 2021-07-22 | 2021-08-02 | 2021-07-27 | CLOSED | Adam Weisberg | Taylor Patterson | No, see notes | Not tied to a specific package, general information | N/A |  |  |  | TRUE
21029900-0002 | Mech_Arch - MSB_RA4 - CPK01 - JE Dunn Scope Acceptance | 2021-07-27 | 2021-08-05 | 2021-08-02 | ANSWRCOMP | Jenna Stein | Taylor Patterson | 2021-10-21 | RFI-0002 - pyth pend, flag placed | CPK01 |  |  |  | TRUE
21029900-0003 | CSA - RA4 - MS01 - L20A Revised Beams | 2021-07-28 | 2021-08-06 | 2021-08-06 | ANSWRCOMP | Adam Weisberg | Taylor Patterson | 2021-10-21 | RFI-0003 - pyth pend, flag placed | MS01, MS01-R1 |  |  |  | TRUE
21029900-0004 | Process - MSB - LLE01_MS01 - Dome Topped Tanks | 2021-08-06 | 2021-08-10 | 2021-08-10 | ANSWRCOMP | Andrew Stengel | Taylor Patterson | 2021-10-21 | RFI-0004 - pyth pend, flag placed | LLE01 |  |  |  | TRUE
21029900-0005 | Electrical - LLe01 - Acid Scrubber Exhaust Fan VFD | 2021-08-06 | 2021-08-10 | 2021-08-10 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-10-21 | RFI-0005 - pyth pend, flag placed | LLE01 |  |  |  | TRUE
21029900-0006 | RA4 - LLE01 - Sort North RAH | 2021-08-06 | 2021-08-10 | 2021-08-24 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-29 | [5 empty] | TRUE
21029900-0007 | Process - LLE01 - RA4 - BCS Tank Dimension | 2021-08-06 | 2021-08-10 | 2021-08-10 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-10-22 | [5 empty] | TRUE
21029900-0008 | I and C - LLE01 - PMP275 Data Sheets and Package | 2021-08-06 | 2021-08-10 | 2021-08-10 | ANSWRCOMP | Andrew Stengel | Taylor Patterson | 2021-10-22 | [5 empty] | TRUE
21029900-0008R1 | I and C - LLE01 - PMP275 Data Sheets and Package R1 | 2021-10-22 | 2021-11-02 | 2021-10-25 | CLOSED | Taylor Patterson | Taylor Patterson | No, see notes | Superseded by SWN 243 | No, see notes |  |  |  | TRUE
21029900-0009 | Structural - LLE01 - RA4 - Catwalk Design Criteria | 2021-08-06 | 2021-08-17 | 2021-08-10 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-10-22 | [5 empty] | TRUE
21029900-0010 | Process - LLE01 -RA4 - CMS299 LLE01 Mixers | 2021-08-06 | 2021-08-10 | 2021-08-11 | ANSWRCOMP | Andrew Stengel | Taylor Patterson | 2021-10-22 | [5 empty] | TRUE
21029900-0012 | Process - RA4 - PMP299 Material Confirmation | 2021-08-06 | 2021-08-10 | 2021-08-10 | ANSWRCOMP | Andrew Stengel | Taylor Patterson | 2021-10-22 | [5 empty] | TRUE
21029900-0013 | I and C - LLE01 - Port Device Coupler Conformation | 2021-08-06 | 2021-08-10 | 2021-08-12 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-03 | [5 empty] | TRUE
21029900-0014 | Process - LLE01 Mech MSB01 - PCV Positioner Input | 2021-08-06 | 2021-08-10 | 2021-08-11 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-03 | [5 empty] | TRUE
21029900-0015 | Wet - Mech - LLE01 Filter Pressure Ratings | 2021-08-06 | 2021-08-10 | 2021-08-12 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-03 | [5 empty] | TRUE
21029900-0016 | B0001-CPK01-R1 IFC | 2021-08-09 | 2021-08-18 | 2021-08-16 | ANSWRCOMP | Jenna Stein | Taylor Patterson | 2021-11-04 | [5 empty] | TRUE
21029900-0017 | Structural - RA4 Steel Angle Clip Detail | 2021-08-18 | 2021-08-25 | 2021-08-23 | CLOSED | Mitchell Casio | Taylor Patterson | 2021-10-22 | [5 empty] | TRUE
21029900-0018 | LLE- OMI-HB-IMO - LLE01 - C4 Descope QB Items | 2021-08-18 | 2021-08-25 | 2021-08-24 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-03 | [5 empty] | TRUE
21029900-0019 | Mechanical - OMI-HB-IMO - LLE01- Grease Spec Conformation | 2021-08-24 | 2021-08-31 | 2021-11-19 | CLOSED | Andrew Stengel | Taylor Patterson | Superseded by R1 | Superseded by R1 | Superseded by R1 |  |  |  | TRUE
21029900-0019R1 | Mechanical - OMI-HB-IMO - LLE01 - Grease Spec Conformation | 2021-12-14 | 2021-12-16 | - | VOID | Carlos Acosta |  |  | NEED RENAMING IN SHAREPOINT |  |  |  |  | FALSE
21029900-0020 | Mechanical - OMI-HB-IMO - LLE01 - RA4 - Sort North RAH End Switch Conformation | 2021-08-24 | 2021-08-31 | 2021-08-31 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-09 | [5 empty] | TRUE
21029900-0021 | Mechanical - OMI-HB-IMO - LLE01 - RA4 - Sort North RAH Control Panel Conformation | 2021-08-24 | 2021-08-31 | 2021-09-07 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-09 | [5 empty] | TRUE
21029900-0022 | Mechanical - OMI-HB-IMO - LLE01 - RA4 - Sort North RAH VFD for Fan Walls | 2021-08-24 | 2021-08-31 | 2021-08-31 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-09 | [5 empty] | TRUE
21029900-0023 | Mechanical_LLE01_RA4_Sort North_RAH_Piping_Stubbed_Connections. | 2021-08-24 | 2021-08-31 | 2021-08-31 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-09 | [5 empty] | TRUE
21029900-0024 | Mechanical - LLE01 RA4 - Sort North RAH Condensate Drain Line Conformation | 2021-08-24 | 2021-08-31 | 2021-08-31 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-09 | [5 empty] | TRUE
21029900-0025 | Process - OMI-HB-IMO - LLE01- MSB- Tank Vacuum Rating | 2021-08-25 | 2021-09-01 | 2021-08-30 | ANSWRCOMP | Andrew Stengel | Taylor Patterson | 2021-11-03 | [5 empty] | TRUE
21029900-0026 | Process -LLP02 - RA4 Split Case Pump Conformation | 2021-08-26 | 2021-09-02 | 2021-09-14 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-09 | [5 empty] | TRUE
21029900-0027 | Process - LLP02 - Pump Capacity and Differential Head Requirements | 2021-08-26 | 2021-09-02 | 2021-09-08 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-16 | [5 empty] | TRUE
21029900-0028R1 | Mechanical - LLP02- Dry Cooling Coils Approved Manufacturers R1 | 2021-08-27 | 2021-09-17 | 2021-09-08 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-10 | [5 empty] | TRUE
21029900-0029 | Mechanical - LLP02 - ATTD Coil Temperatures | 2021-08-31 | 2021-09-07 | 2021-09-02 | CLOSED | Andrew Stengel | Taylor Patterson | Superseded by RFI 0069 | Superseded by RFI 0069 | Superseded by RFI 0069 |  |  |  | TRUE
21029900-0030 | Mechanical - LLP02 - IMO Cooling Coil Latent Load Confirmation | 2021-08-31 | 2021-09-07 | 2021-09-02 | CLOSED | Andrew Stengel | Taylor Patterson | Superseded by RFI 0069 | Superseded by RFI 0069 | Superseded by RFI 0069 |  |  |  | TRUE
21029900-0031 | Process - LLE01 - RA4- TK252-1-00 Outlet Nozzle Size | 2021-09-01 | 2021-09-08 | 2021-09-10 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-03 | [5 empty] | TRUE
21029900-0032R1 | Mechanical - LLP02 - Carbonator System Procurement R1 | 2021-09-02 | 2021-09-23 | 2021-09-14 | ANSWRCOMP | Andrew Stengel | Taylor Patterson | 2021-11-29 | [5 empty] | TRUE
21029900-0033 | Electrical - LLE01 - Acid Scrubber Exhaust Fan VFD | 2021-09-02 | 2021-09-10 | 2021-09-07 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-03 | [5 empty] | TRUE
21029900-0034 | Process - LLP02 - High Vacuum Process Vacuum Receiver Tank MSB1-TK221-1-60 | 2021-09-02 | 2021-09-10 | 2021-09-13 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-10 | [5 empty] | TRUE
21029900-0035 | Mechanical - LLP02 - Phase 2 RAH Procurement | 2021-09-07 | 2021-09-16 | 2021-09-14 | ANSWRCOMP | Andrew Stengel | Taylor Patterson | 2021-11-29 | [5 empty] | TRUE
21029900-0036 | I and C - LLP02 - Panel Procurement Confirmation | 2021-09-07 | 2021-09-14 | 2021-09-10 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-10 | [5 empty] | TRUE
21029900-0037 R1 | Electrical - LLP02 – Siemens Tool Annunciation SystemR1 | 2021-09-08 | 2021-09-17 | 2021-09-10 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-16 | [5 empty] | TRUE
21029900-0038 | Electrical - LLP02 - Honeywell Gas Detection Panels with Internal Component Parts | 2021-09-08 | 2021-09-15 | 2021-09-10 | CLOSED | Andrew Stengel | Taylor Patterson | Superseded by R1 | Superseded by R1 | Superseded by R1 |  |  |  | TRUE
21029900-0038R1 | Electrical - LLP02 - Honeywell Gas Detection Panels with Internal Component Parts R1 | 2021-09-29 | 2021-10-06 | 2021-09-29 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-16 | [5 empty] | TRUE
21029900-0039 | Mechanical - LLP02 - Manufacturer specification change | 2021-09-10 | 2021-09-17 | 2021-09-21 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-16 | [5 empty] | TRUE
21029900-0040 | Mech, InC, Electric-LLE01-Critical Process Cooling Water Circulation Pumps 202-1-10, 202-2-10, 202-3-10 | 2021-09-10 | 2021-09-17 | 2021-09-15 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-03 | [5 empty] | TRUE
21029900-0041 | Mechanical - InC - LLE01 - Silicon Water Treatment Lift Pumps | 2021-09-13 | 2021-09-20 | 2021-09-17 | ANSWRCOMP | Andrew Stengel | Taylor Patterson | 2021-11-03 | [5 empty] | TRUE
21029900-0042 | Mechanical - Eletrical - LLP02 – RA4 and MSB PMP113 Tagging | 2021-09-20 | 2021-09-29 | 2021-09-23 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-16 | [5 empty] | TRUE
21029900-0043 | Structural - CPK01-R2 - MSB Shared Rack Strut Elevation- VOID | 2021-09-22 | 2021-10-01 | 2021-11-18 | CLOSED | Mitchell Casio | Taylor Patterson | VOID | VOID | VOID |  |  |  | TRUE
21029900-0044 | CSA - CPK02-R2-AT30 - Layout for Exyte Ceiling Grid Anchor Rods | 2021-09-23 | 2021-09-28 | 2021-09-27 | CLOSED | Colin Ratliff | Taylor Patterson | 2021-12-07 | [5 empty] | TRUE
21029900-0045 | Duplicate | 2021-09-23 | 2021-09-28 | 2021-09-28 | CLOSED | Colin Ratliff | Taylor Patterson | Duplicate | Duplicate | Duplicate |  |  |  | FALSE
21029900-0046 | Process - CPK01 R2 - HP02 Line Size Valve | 2021-09-23 | 2021-09-30 | 2021-09-28 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-05 | [5 empty] | TRUE
21029900-0047 | Process - CPK01 R2 - HP02 Tie Point Conformation | 2021-09-23 | 2021-09-30 | 2021-09-24 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-05 | [5 empty] | TRUE
21029900-0048 | Process - FIT and Pipe Size Conformation | 2021-09-23 | 2021-09-30 | 2021-09-24 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-05 | [5 empty] | TRUE
21029900-0049 | CSA - CPK02-R2-AT30 - Steel Support Questions for Exyte Ceiling Grid Coordination (Part 2) | 2021-09-24 | 2021-09-29 | 2021-09-28 | CLOSED | David Phillips | Taylor Patterson | 2021-11-04 | [5 empty] | TRUE
21029900-0050 | MSB West Door Logistics Modifications -Proposed Stud Alternate | 2021-09-29 | 2021-10-06 | 2021-11-15 | ANSWRCOMP | Taylor Bothmann | Taylor Patterson | No, see notes | Logistics, not tied to a specific package, response resulted in no changes to plans | N/A |  |  |  | TRUE
21029900-0051 | Process - LLE01 - RA4 - BCS Tank Dimension diameter and height conformation | 2021-10-01 | 2021-10-08 | 2021-10-04 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-03 | [5 empty] | TRUE
21029900-0052 | Electrical - LLE01 R1 VFD111-17-00 Horsepower Conformation | 2021-10-06 | 2021-10-13 | 2021-10-08 | VOID | Andrew Stengel | Taylor Patterson | VOID | VOID | VOID |  |  |  | FALSE
21029900-0053 | Mechanical – LLP02 – TCHW Pumps MSB and RA4 | 2021-10-11 | 2021-10-18 | 2021-10-15 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-16 | [5 empty] | TRUE
21029900-0054 | Mechanical – LLP02 – GAH104-28-00 Heating Coil Replacement Selection | 2021-10-11 | 2021-10-18 | 2021-10-22 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-29 | [5 empty] | FALSE
21029900-0055 | CSA - CPK02-R2-AT30 - Eyxte Threaded Steel Rod Confirmation | 2021-10-11 | 2021-10-18 | 2021-10-13 | ANSWRCOMP | Callie Johns | Taylor Patterson | Superseded by R1 | Superseded by R1 | Superseded by R1 |  |  |  | FALSE
21029900-0055R1 | CSA - CPK02-R2-AT30 - Eyxte Threaded Steel Rod Confirmation R1 | 2021-10-22 | 2021-11-02 | 2021-10-25 | ANSWRCOMP | Callie Johns | Taylor Patterson | 2021-11-04 | [5 empty] | TRUE
21029900-0056 | Process - LLP02 - LLP02R1 - Valve Matrix | 2021-10-13 | 2021-10-22 | 2021-10-14 | CLOSED | Andrew Stengel | Taylor Patterson | Superseded by R1 | Superseded by R1 | Superseded by R1 |  |  |  | TRUE
21029900-0056R1 | Process - LLP02 - LLP02R1 - Valve Matrix-R1 | 2021-10-14 | 2021-10-21 | 2021-11-11 | CLOSED | Andrew Stengel | Taylor Patterson | Superseded by R2 | Superseded by R2 | Superseded by R2 |  |  |  | TRUE
21029900-0056R2 | Process - LLP02 - LLP02R1 - Valve Matrix | 2021-11-08 | 2021-11-15 | 2021-11-29 | CLOSED | Mitch Kovalev | Taylor Patterson | Superseded by R3 | Superseded by R3 | Superseded by R3 |  |  |  | TRUE
21029900-0056R3 | Process - LLP02 - LLP02R1 - Valve Matrix - REV 3 | 2021-11-29 | 2021-12-06 | 2022-02-17 | CLOSED | Mitch Kovalev | Taylor Patterson | 2022-02-17 | RFI-56R3 - pyth pend, flag placed | LLP02, LLP02-R1 |  |  |  | TRUE
21029900-0057 | Process - LLP02R1 - Valve Spec Change | 2021-10-13 | 2021-10-20 | 2021-10-14 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-03 | [5 empty] | TRUE
21029900-0058 | Process - LLE01 - CPCW Heat Exchanger Dimensions | 2021-10-15 | 2021-10-22 | 2021-10-28 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-04 | [5 empty] | TRUE
21029900-0059 | Structural - MSB - CPK03 - Beam to Beam Moment Connection - Roof Level 5RF | 2021-10-19 | 2021-10-28 | 2021-10-22 | CLOSED | Steve Mazzoni | Taylor Patterson | 2021-11-04 | [5 empty] | TRUE
21029900-0060 | Process - LLP02 - RA4 BCS Pumps PMP252-1-40 and PMP252-2-40 - Duty Point | 2022-01-13 | 2022-01-18 | 2022-01-14 | ANSWRCOMP | Mitch Kovalev | Taylor Patterson | Superseded by R1 | Superseded by R1 | Superseded by R1 |  |  |  | TRUE
21029900-0060R1 | Process - LLP02 - RA4 BCS Pumps PMP252-1-40 and PMP252-2-40 - Duty Point - R1 | 2022-01-25 | 2022-02-03 | 2022-02-01 | ANSWRCOMP | Mitch Kovalev | Taylor Patterson | 2022-02-17 | RFI-60R1 - pyth pend, flag placed | CPK02-R2, CPK02-R4, LLP02, LLP02-R1 |  |  |  | TRUE
21029900-0061 | Process - LLP02 BCS Day Tank Nozzles | 2021-10-27 | 2021-11-03 | 2021-11-03 | CLOSED | Andrew Stengel | Taylor Patterson | 2021-11-04 | [5 empty] | FALSE
21029900-0062 | Process - MSB - CPK01R1 - FPN2 Valve Clarification | 2021-10-27 | 2021-11-03 | 2021-10-29 | CLOSED | Alen Troyer | Taylor Patterson | 2021-11-08 | [5 empty] | TRUE
21029900-0063 | Electrical - LLP02 - RA4/MSB - TCHW Pumps | 2021-10-29 | 2021-11-09 | 2021-11-05 | CLOSED | Taylor Patterson | Taylor Patterson | 2021-11-05 | [5 empty] | TRUE
21029900-0064 | Mechanical - CPK03-R2 - MSB - HXRA Unit Scope Inclusion | 2021-11-01 | 2021-11-10 | 2021-11-01 | CLOSED | Taylor Patterson | Taylor Patterson | 2021-11-08 | [5 empty] | TRUE
21029900-0065 | LLP03 – PSSS – MSB - Analyzer Panel Name Confirmation | 2021-11-03 | 2021-11-12 | 2021-11-04 | CLOSED | Taylor Patterson | Taylor Patterson | 2021-11-08 | [5 empty] | TRUE
21029900-0066 | Structural - CPK01-R2 - MSB Beam Layout Level 1 GRID AE_56-57 | 2021-11-03 | 2021-11-12 | 2021-11-04 | CLOSED | Steve Mazzoni | [7 empty] | TRUE
21029900-0067 | CSA - MSB - CPK01R1 - Fire Rating Wall Patch Confirmation | 2021-11-03 | 2021-11-10 | 2021-11-10 | CLOSED | Alen Troyer | Ernesto | 2022-02-16 |  | CPK01-R1 |  |  |  | TRUE
21029900-0068 | Process - LLP02-R1 - MSB - Carbonator Performance Spec Alignment | 2021-11-05 | 2021-11-12 | 2022-01-28 | CLOSED | Taylor Patterson | Taylor Patterson | 2022-02-18 | RFI-0068 - pyth pend, flag placed | LLP02-R1 |  |  |  | TRUE
21029900-0069 | Mechanical - LLP02 - MSB - ATTD and IMO Dry Cooling Coil Quantity | 2021-11-05 | 2021-11-12 | 2021-11-10 | ANSWRCOMP | Alen Troyer | Taylor Patterson | 2022-02-18 | Action Needed: where's a non-drafted issuance? What's happening with the TCV's TNP BB alerted Ellie & Colin 2/18 TNP emailed Ellie & Colin 2/25 | CPK03-R3, CPK03-R8, LLP02, LLP02-R1 |  |  |  | TRUE
21029900-0070 | Process - LLP02 - LLP02R1 - Valve Matrix | 2021-11-05 | 2021-11-12 | 2022-02-17 | CLOSED | Mitch Kovalev | Taylor Patterson | VOID | VOID | VOID |  |  |  | TRUE
21029900-0071 | CSA - MSB - CPK03R2 - All Thread Rod Lengths (M10 &M16) | 2021-11-08 | 2021-11-17 | 2021-11-12 | CLOSED | Ellie Runte | Connor | [6 empty] | TRUE
21029900-0072 | CSA - CPK02-R2 - RA4 - Adjustability of HSS10x6 Cups Confirmation | 2021-11-09 | 2021-11-18 | 2021-11-12 | ANSWRCOMP | Callie Johns | Ernesto | 2022-02-18 | RFI-0072 - pyth pend, flag placed | CPK02-R2, CPK02-R3, CPK02-R5 |  |  |  | TRUE
21029900-0073 | CSA - CPK02-R2 - RA4 - Slotted Holes in HSS Beams Confirmation | 2021-11-09 | 2021-11-18 | 2021-11-12 | CLOSED | Callie Johns | Ernesto | 2022-02-18 | RFI-0073 - pyth pend, flag placed | CPK02-R2, CPK02-R3, CPK02-R4, CPK02-R5, CPK07 (yet to be posted) |  |  |  | TRUE
21029900-0074 | Mechanical - CPK03-R2 - MSB - HXRA unit VFDs | 2021-11-09 | 2021-12-03 | 2021-11-29 | ANSWRCOMP | Taylor Patterson | Max's Bot | 2022-03-02 | RFI-0074 - pyth pend, flag placed | CPK03-R2, CPK03-R3, CPK03-R9 |  |  |  | TRUE
21029900-0075 | Structural - MSB - CPK01-R2 Subfab Steel - Grid Alignment Vs Survey Points | 2021-11-10 | 2021-11-19 | 2021-11-11 | CLOSED | Steve Mazzoni | [7 empty] | TRUE
21029900-0076 | I and C - LLE01 - RA4-MSB Stratix Ethernet Switch EOL Replacement | 2021-11-10 | 2021-11-19 | 2021-11-15 | ANSWRCOMP | Ismael Hernandez | [7 empty] | TRUE
21029900-0077 | Structural-Mechanical - RA4 -CPK02-R1 Additional Framing Support for MAH Duct | 2021-11-11 | 2021-11-17 | 2021-11-18 | CLOSED | Carlos Acosta | Taylor Patterson | 2022-02-16 | RFI-0077 - pyth pend, flag placed | CPK02, CPK02-R1 |  |  |  | TRUE
21029900-0078 | LLP02 CPK02 R2/CPK03 R2 Rotork Actuators from Fabtech - Quantity and Size Verification | 2021-11-11 | 2021-11-18 | 2021-11-12 | VOID | Taylor Bothmann | Taylor Patterson | Superseded by RFI-0079 | Superseded by RFI-0079 | Superseded by RFI-0079 |  |  |  | TRUE
21029900-0079 | LLP02 CPK02 R2/CPK03 R2 Rotork Actuators from EPC - Quantity and Size Verification | 2021-11-11 | 2021-11-18 | 2021-11-16 | ANSWRCOMP | Taylor Bothmann | Taylor Patterson | 2022-02-18 | RFI-0079 - pyth pend, flag placed | LLP02, CPK02-R2, CPK02-R4, CPK03-R2 |  |  |  | TRUE
21029900-0080 | Mechanical-CPK01-R1-MSB Demo Enabling Spot Cooling Confirmation | 2021-11-15 | 2021-11-22 | 2022-01-03 | CLOSED | Mitchell Casio | Ernesto | 2022-02-18 | RFI-0080 - pyth pend, flag placed Jacobs did not confirm | CPK01-R1 |  |  |  | TRUE
21029900-0081 | Electrical - CPK02 RA4 - Sizing for Feeder K3 from XR4D2E32C to XR4T4J12C | 2021-11-16 | 2021-11-29 | 2021-11-24 | CLOSED | Ismael Hernandez | Ernesto | 2022-02-18 | RFI-0081 - pyth pend, flag placed; need to slipsheet ECR XR4D2E32C into CPK02-R1, slipsheet new electrical sheets | CPK02-R1, CPK02-R2 |  |  |  | TRUE
21029900-0082 | CSA - CPK02-R2-AT90 - CRC Type Confirmation | 2021-11-16 | 2021-11-29 | 2021-11-24 | VOID | Callie Johns | Ernesto | VOID | [5 empty] | TRUE
21029900-0083 | Mechanical - CPK03 - MSB - HVAC Enabling Demo Content | 2021-11-17 | 2021-11-24 | 2021-12-20 | OPEN | Alen Troyer | Max's Bot | [6 empty] | FALSE
21029900-0084 | Mechanical - CPK03 - MSB - Level 2 AB South Duct Change | 2021-11-17 | 2021-11-24 | 2021-11-24 | CLOSED | Alen Troyer | Connor | [6 empty] | TRUE
21029900-0085 | Process - CPK01-R2 - MSB - UN2 and HPO2 Purge Port Valve Assemblies | 2021-11-17 | 2021-11-24 | 2021-11-22 | CLOSED | Rees Bixler | [7 empty] | TRUE
21029900-0086 | Process - CPK03-R1 - MSB - HRW Pipe Support Clarifications | 2021-11-22 | 2021-11-29 | 2021-11-30 | CLOSED | Rees Bixler | Connor | [6 empty] | TRUE
21029900-0087 | CSA - MSB - CPK03R2 - 2FA Full Height GWB Wall at GL J.3 | 2021-11-23 | 2021-11-29 | 2021-12-03 | CLOSED | Ellie Runte | Connor | [6 empty] | TRUE
21029900-0088 | Electrical - LLE01-RA4-ETAP252-1-00 Panel Name Change | 2021-11-24 | 2021-12-07 | 2022-01-03 | CLOSED | Taylor Bothmann | [7 empty] | FALSE
21029900-0089 | Mechanical - LLP02 - RA4 - RAH Submittal Approval | 2021-11-24 | 2021-11-30 | 2021-11-29 | CLOSED | Carlos Acosta | Taylor Patterson | 2022-02-21 | RFI-0089 - pyth pend, flag placed | LLP02, CPK02-R2 |  |  |  | TRUE
21029900-0090 | Electrical LLE01 RA4 Panel-JB650-22-90 name confirmation | 2021-11-24 | 2021-12-07 | 2021-12-13 | CLOSED | Taylor Bothmann | [7 empty] | FALSE
21029900-0091 | Electrical-LLE01 RA4 Field ETAP Panels Count Confirmation | 2021-11-24 | 2021-12-07 | 2021-11-29 | ANSWRCOMP | Taylor Bothmann | [7 empty] | TRUE
21029900-0092 | CSA - MSB - CPK03 IFC- MSB Base Build - Architectural Detail Reference | 2021-11-24 | 2021-12-07 | 2021-12-01 | CLOSED | Steve Mazzoni | [7 empty] | TRUE
21029900-0093 | Mechanical-CPK02-RA4 Make Up Air Flex Confirmation | 2021-11-29 | 2021-12-03 | 2022-01-31 | CLOSED | Carlos Acosta | Ernesto | 2022-02-21 | RFI-0093 - pyth pend, flag placed | CPK02, CPK02-R4 |  |  |  | TRUE
21029900-0094 | Process - B0001-CPK01-R2 - MSB - Strut Rack Elevation and P1067 Clarification | 2021-11-30 | 2021-12-09 | 2021-12-06 | CLOSED | Rees Bixler | [7 empty] | FALSE
21029900-0095 | CSA - MSB - CPK03-IFC - Existing Pedestal Connections | 2021-12-01 | 2021-12-10 | 2021-12-08 | CLOSED | Steve Mazzoni | [7 empty] | TRUE
21029900-0096 | Mechanical-CPK02-R2 RA4 MAU Penetrations Clashes and Relocation | 2021-12-02 | 2021-12-13 | 2021-12-09 | CLOSED | Carlos Acosta | Ernesto | 2022-02-21 | RFI-0096 - pyth pend, flag placed | CPK02-R2, CPK02-R4, CPK07 |  |  |  | TRUE
21029900-0096R1 | Mech-Process-Elec-CSA-CPK02/CPK02-R2-RA4 NW-MAU Penetrations Clashes and Relocations | 2022-01-20 | 2022-01-24 |  | OPEN | Carlos Acosta | Ernesto | [6 empty] | TRUE
21029900-0096R2 | Mech-Process-Elec-CSA-CPK02/CPK02-R2-RA4-South-MAU Penetrations Clashes and Relocations | 2022-01-27 | 2022-01-28 |  | OPEN | Carlos Acosta | Ernesto | [6 empty] | TRUE
21029900-0097 | Process - MSB and RA4 - OFA Laterals | 2021-12-03 | 2021-12-10 | 2021-12-08 | CLOSED | Mitch Kovalev | [7 empty] | TRUE
21029900-0098 | CSA - CPK02-R2 - Dots on HSS Cups and Beams Clarification | 2021-12-06 | 2021-12-15 | 2021-12-09 | CLOSED | Callie Johns | Ernesto | 2022-02-21 | RFI-0098 - pyth pend, flag placed | CPK02-R2, CPK02-R3, CPK02-R5, CPK07 |  |  |  | TRUE
21029900-0099 | Electrical CPK03-R2 MSB PDIT Equipment Order/Not Order | 2021-12-06 | 2021-12-15 | 2021-12-08 | ANSWRCOMP | Taylor Bothmann | Max's Bot | 2022-03-02 | RFI-0099 - pyth pend, flag placed | CPK03-R2, LLP04 |  |  |  | TRUE
21029900-0100 | Electrical-OHIEX-R-B0001-CPK03-RIO 650_1B_01 | 2021-12-07 | 2021-12-16 | 2021-12-08 | ANSWRCOMP | Taylor Bothmann | Connor | 2022-02-18 | RFI-0100 - pyth and flag pending | CPK03-R9 |  |  |  | TRUE
21029900-0101 | CSA - CPK02-01 - Columns on RA4-SS-4RB-K0000 Confirmation | 2021-12-07 | 2021-12-16 | 2021-12-09 | ANSWRCOMP | Callie Johns | [7 empty] | TRUE
21029900-0102 | Mech- CSA - CPK02 RA4 Handrail Modification | 2021-12-07 | 2021-12-14 | 2021-12-09 | ANSWRCOMP | Carlos Acosta | Ernesto | 2022-02-21 | RFI-0102 - pyth pend, flag placed | CPK02, CPK02-R2, CPK02-R4 |  |  |  | TRUE
21029900-0103 | Electrical- B0001-CPK03 MAH Install Circuit Breakers | 2021-12-07 | 2021-12-16 | 2021-12-08 | ANSWRCOMP | Taylor Bothmann | Connor |  | Unsure what is happening within this RFI, CPK03 MAHs add breaker |  | Not in cold storage |  |  | FALSE
21029900-0104 | Mechanical - CPK03-R2 - PMP111-17-00 10% Head Increase Spec Deviation | 2021-12-07 | 2021-12-14 | 2021-12-08 | CLOSED | Alen Troyer | Max's Bot | 2022-03-02 | RFI-0104 - pyth pend, flag placed | CPK03-R2 |  |  |  | TRUE
21029900-0105 | Electrical - CPK02-R2 - RA4 - INSTALL PMD | 2021-12-07 | 2021-12-14 | 2021-12-08 | ANSWRCOMP | Max Parker | Ernesto | 2022-02-21 | RFI-0105 - pyth pend, flag placed | CPK02-R2 |  |  |  | FALSE
21029900-0106 | CSA - MSB - CPK01R2 - BCD Line Conflict with Steel | 2021-12-09 | 2021-12-16 | 2021-12-17 | CLOSED | Alen Troyer | [7 empty] | FALSE
21029900-0107 | CSA - CPK01R2 - MSB - BCD Line Conflict with Cable Tray | 2021-12-09 | 2021-12-16 | 2021-12-20 | ANSWRINCOM | Alen Troyer | [7 empty] | FALSE
21029900-0108 | CSA - MSB - CPK03-R2 IFC - High Bay Clarification | 2021-12-09 | 2021-12-14 | 2021-12-17 | ANSWRCOMP | Ellie Runte | Max's Bot | 2022-03-02 | RFI-0108 - pyth pend, flag placed | CPK03-R2, CPK03-R3, CPK03-R8, CPK03-R9 |  |  |  | TRUE
21029900-0109 | Mechanical - CPK03 - MSB - GMAH103-0-00 Piping Connection Sizes | 2021-12-10 | 2022-01-06 | 2022-01-11 | ANSWRCOMP | Alen Troyer | Connor | 2022-02-18 | RFI-0109 - pyth and flag pending | CPK03-R2 |  |  |  | TRUE
21029900-0110 | CSA-MSB – CPK01-R2 Shop Welded Strut Type | 2021-12-13 | 2021-12-22 | 2021-12-16 | CLOSED | Steve Mazzoni | [7 empty] | TRUE
21029900-0111 | Mechanical - CPK03 - MSB - Level 2 Control Dampers Model vs P&ID | 2021-12-13 | 2021-12-17 |  | VOID | Alen Troyer | Connor |  | Checked |  |  |  |  | FALSE
21029900-0112 | Electrical- CPK03- MSB- AHU Alternate Feeder Route | 2021-12-13 | 2021-12-22 | 2021-12-13 | ANSWRCOMP | Michael Brown | Connor |  | waiting on answer |  |  |  |  | TRUE
21029900-0113 | CSA - MSB - CPK03-R2 IFC - Existing Wall Clarification | 2022-01-10 | 2022-01-14 | 2022-01-26 | ANSWRCOMP | Ellie Runte | Max's Bot | 2022-03-02 | RFI-0113 - pyth pend, flag placed | CPK03-R2, CPK03-R3 CPK03-R8 |  |  |  | TRUE
21029900-0114 | Electrical MSB-CPK03-MAH Evaporator circuits LCP101-7-50A EVAP & LCP101-8-50A EVAP | 2021-12-14 | 2021-12-23 | 2021-12-15 | ANSWRCOMP | Michael Brown | Connor | 2022-02-18 | RFI-0114 - pyth and flag pending | CPK03, CPK03-R9 | Not in cold storage |  |  | TRUE
21029900-0115 | Mechanical - CPK03R2 - MSB - Streimer Clarifications | 2021-12-16 | 2021-12-20 | 2021-12-20 | CLOSED | Alen Troyer | Connor | 2022-03-07 |  |  | Not in cold storage |  |  | FALSE
21029900-0116 | Electrical - MSB- CPK03- Subfab Light Mounting | 2021-12-16 | 2021-12-28 | 2021-12-21 | ANSWRCOMP | Michael Brown | Connor | 2022-02-18 | RFI-0116 - pyth and flag pending | CPK03-R2 | Not in cold storage |  |  | FALSE
21029900-0117 | HVAC--LLP02-MSB- TCHW TCV | 2021-12-16 | 2021-12-28 | 2021-12-17 | ANSWRCOMP | Taylor Bothmann | Taylor Patterson | 2022-02-21 | RFI-0117 - pyth pend, flag placed | LLP02, LLP02-R1, CPK02-R2, CPK03-R2 |  |  |  | TRUE
21029900-0118 | Mechanical - CPK03-R2 - GMAH and GAH Riser | 2021-12-20 | 2022-02-02 | 2022-02-08 | ANSWRCOMP | Alen Troyer | Max's Bot | 2022-03-02 | RFI-0118 - pyth pend, flag placed | CPK03-R2 |  |  |  | TRUE
21029900-0119 | Process - MSB - CPK03-R2 - Charter P&ID vs Model Clarification | 2021-12-20 | 2021-12-22 | 2021-12-20 | CLOSED | Alen Troyer | Max's Bot | 2022-03-02 | RFI-0119 - pyth pend, flag placed | CPK03-R2, CPK03-R9 |  |  |  | TRUE
21029900-0120 | Process - CUB4 - CPK03-R2 - CHW - PMP111-17-00 Motor Enclosure | 2021-12-20 | 2021-12-23 | 2021-12-23 | CLOSED | Alen Troyer | Max's Bot | 2022-03-02 | RFI-0120 - pyth pend, flag placed | CPK03-R2, CPK03-R3 |  |  |  | FALSE
21029900-0121 | Electrical MSB - CPK03-R2 General Purpose Receptacles ECR | 2021-12-21 | 2022-01-03 | 2021-12-27 | CLOSED | Michael Brown | Max's Bot | 2022-03-02 | RFI-0121 - pyth pend, flag placed | CPK03-R2, CPK03-R9 |  |  |  | FALSE
21029900-0122 | Structural - MSB - CPK03-R5 IFC- Revised Drawings | 2021-12-22 | 2022-01-04 | 2022-01-04 | ANSWRCOMP | Steve Mazzoni | Connor | 2022-02-21 | No tags, superseded in CPK03-R9 tags | CPK03-R9 |  |  |  | TRUE
21029900-0123 | Structural - RA4 - CPK02-R2 - Seismic Cable Sizing | 2021-12-22 | 2021-12-28 | 2021-12-23 | CLOSED | Mitchell Casio | Ernesto | 2022-02-21 | RFI-0123 - pyth pend, flag placed | CPK02-R2, CPK02-R3, CPK07 |  |  |  | TRUE
21029900-0124 | Structural - RA4 - CPK02-R2 - Sheet Metal Sheathing Install | 2021-12-22 | 2021-12-28 | 2022-01-05 | CLOSED | Mitchell Casio | Ernesto | 2022-02-21 | RFI-0124 - pyth pend, flag placed | CPK02-R2 |  |  |  | TRUE
21029900-0124-R1 | CSA-CPK02-R2-Sheet Metal Sheathing Type Confirmation | 2022-01-10 | 2022-01-20 | 2022-01-20 | ANSWRCOMP | Carlos Acosta | Ernesto | 2022-02-21 | RFI-0124-R1 - pyth pend, flag placed | CPK02-R2 |  |  |  | TRUE
21029900-0125 | Structural - RA4 - CPK02-R2 - Inside Wall Sheet Metal | 2021-12-22 | 2021-12-28 | 2021-12-29 | CLOSED | Mitchell Casio | Ernesto | 2022-02-21 | RFI-0125 - pyth pend, flag placed | CPK02-R2 |  |  |  | FALSE
21029900-0126 | Structural - RA4 - CPK02-R2 - General Notes Reference | 2021-12-22 | 2021-12-28 | 2021-12-28 | CLOSED | Mitchell Casio | Ernesto | 2022-02-21 | RFI-0126 - pyth pend, flag placed | CPK02-R2, CPK03-R2 |  |  |  | TRUE
21029900-0127 | Structural - RA4 - CPK02-R2 - Gyp Board Thickness | 2021-12-22 | 2021-12-28 | 2021-12-27 | CLOSED | Mitchell Casio | Ernesto | 2022-02-21 | RFI-0127 - pyth pend, flag placed | CPK02-R2, CPK03-R2 |  |  |  | TRUE
21029900-0128 | Process - RA4 - CPK02-R2 - BMWC RFI's | 2021-12-22 | 2021-12-28 | 2021-12-23 | ANSWRCOMP | Mitch Kovalev | Ernesto | 2022-02-22 | RFI-0128 - pyth pend, flag placed | CPK02-R2, CPK02-R6, LLE01 (RA4-248-D0-A01 superseded by CPK02-R2) |  |  |  | TRUE
21029900-0128R1 | Process - RA4 - CPK02-R2 - BMWC RFI's | 2021-12-22 | 2022-01-25 | 2022-01-26 | ANSWRCOMP | Mason Ray | Ernesto | 2022-02-22 | RFI-0128R1 - pyth pend, flag placed | CPK02-R2, CPK02-R6, LLE01 (RA4-248-D0-A01 superseded by CPK02-R2) |  |  |  | TRUE
21029900-0129 | Telecom/Mechanical CPK02-R2 RA4 - Level 1 Telecom and Ductwork Conflicts | 2021-12-22 | 2022-01-04 | 2021-12-29 | CLOSED | Ismael Hernandez | Ernesto | VOID | RFI Rejected |  |  |  |  | TRUE
21029900-0130 | Wet Mechanical - RA4 - CPK02-R2 - BMWC RFI's | 2021-12-22 | 2021-12-28 | 2022-01-08 | ANSWRCOMP | Mitch Kovalev | Ernesto | 2022-02-22 | RFI-0130 - pyth pend, flag placed | CPK02-R2, CPK02-R4, CPK07 |  |  |  | TRUE
21029900-0131 | Electrical MSB - CPK03 R2- RIO650-101-04 Relocation | 2021-12-22 | 2022-01-04 | 2021-12-23 | ANSWRCOMP | Michael Brown | Connor | 2022-02-18 | RFI-0131 - pyth and flag pending | CPK03-R3 |  |  |  | TRUE
21029900-0132 | I and C - CPK02-R2 RA4 - PDIT and TET Instruments on Column Discrepancy | 2021-12-22 | 2022-01-04 | 2022-01-05 | ANSWRCOMP | Ismael Hernandez | Ernesto | 2022-02-23 | RFI-0132 - pyth pend, flag placed | CPK02-R2, CPK02-R4, CPK07 |  |  |  | TRUE
21029900-0133 | Electrical MSB - CPK03 R2- MSB1-RIO650-102-04 Relocation | 2021-12-23 | 2022-01-05 | 2021-12-23 | ANSWRCOMP | Michael Brown | Connor | 2022-02-18 | RFI-0133 - pyth and flag pending | CPK03-R3 |  |  |  | TRUE
21029900-0134 | Mech - MSB - CPK03-R2 - P&IDs Needed for Reference | 2021-12-29 | 2022-01-05 | 2021-12-29 | CLOSED | Rees Bixler | Max's Bot | 2022-03-02 | RFI-0134 - pyth pend, flag placed | CPK03-R2 |  |  |  | FALSE
21029900-0135 | Mech - MSB - CPK03-R2 - P&IDs Needed for Model Clarification | 2021-12-29 | 2022-01-05 | 2021-12-29 | ANSWRCOMP | Rees Bixler | Max's Bot | 2022-03-02 | RFI-0135 - pyth pend, flag placed | CPK03-R2 |  |  |  | FALSE
21029900-0136 | Mech - MSB - CPK03-R2 - NaOH P&ID Needed for Reference | 2021-12-29 | 2022-01-05 | 2021-12-29 | CLOSED | Rees Bixler | Max's Bot | 2022-03-02 | RFI-0136 - pyth pend, flag placed | CPK03-R2 |  |  |  | FALSE
21029900-0137 | Mech - MSB - CPK03-R2 - UPW Valve Clarifications | 2021-12-29 | 2022-01-05 | 2021-12-29 | CLOSED | Rees Bixler | Max's Bot | 2022-03-02 | RFI-0137 - pyth pend, flag placed | CPK03-R2, CPK03-R3 |  |  |  | FALSE
21029900-0138 | Mech - MSB - CPK03-R2 - SHPOFA Tie-In | 2021-12-29 | 2022-01-05 | 2021-12-30 | CLOSED | Rees Bixler | Max's Bot | 2022-03-02 | RFI-0138 - pyth pend, flag placed | CPK03-R2 |  |  |  | FALSE
21029900-0139 | I&C - CPK02-R2 - CPK07 - RA4 - RIO650-1B-07 Package Verification | 2021-12-30 | 2022-01-11 | 2021-12-30 | ANSWRCOMP | Taylor Patterson | Ernesto | 2022-02-28 | RFI-0139 - pyth pend, flag placed | CPK02-R2, CPK07 |  |  |  | TRUE
21029900-0139R1 | I and C - CPK02-R2 - CPK07 - RA4 - RIO650-1B-07 Package Verification - R1 | 2022-01-04 | 2022-01-13 | 2022-01-04 | ANSWRCOMP | Ernesto ZuritaRuiz | Ernesto | 2022-02-28 | RFI-39R1 - pyth pend, flag placed | CPK02-R2, CPK07 |  |  |  | TRUE
21029900-0140 | Process - MSB - B0001-CPK01-R1 - UPW Demo Conflicts | 2021-12-30 | 2022-01-06 | 2022-01-08 | CLOSED | Rees Bixler | Ernesto | 2022-03-01 | RFI-0140 - pyth pend, flag placed | CPK01-R1 |  |  |  | FALSE
21029900-0141 | Electrical- CPK03-R2 EC Cable Tray Location | 2022-01-03 | 2022-01-12 | 2022-01-04 | CLOSED | Michael Brown | Max's Bot | 2022-03-02 | RFI-0141 - pyth pend, flag placed | CPK03-R2, CPK01-R2, CPK03-R3, CPK03-R7, CPK03-R9, CPK04 |  |  |  | FALSE
21029900-0142 | Electrical- CPK03- MSB- MXD Housekeeping Pad 90% | 2022-01-03 | 2022-01-12 | 2022-01-04 | CLOSED | Michael Brown | Connor |  |  |  | Not in cold storage |  |  | FALSE
21029900-0143 | Electrical- MSB - Luminaire Screw Clamp Detail RAC-EL-D034 | 2022-01-03 | 2022-01-12 | 2022-01-11 | CLOSED | Michael Brown | [7 empty] | TRUE
21029900-0144 | Dry Mech-CPK02-R2-RA4 Air Coils Fluid Temp Change Confirmation | 2022-01-03 | 2022-01-12 | 2022-01-06 | CLOSED | Carlos Acosta | Ernesto | 2022-03-01 | RFI-0144 - pyth pend, flag placed | CPK02-R2, CPK02-R4, CPK07 |  |  |  | TRUE
21029900-0145 | I and C- MSB1-CPK03-R2- Outdated transmitters | 2022-01-04 | 2022-01-13 | 2022-01-05 | ANSWRCOMP | Michael Brown | Max's Bot | 2022-03-02 | RFI-0145 - pyth pend, flag placed | CPK03-R2 |  |  |  | TRUE
21029900-0146 | I and C- MSB1-CPK03-R2- MSB1-FIT245-0-40A and MSB1-FIT245-0-40B | 2022-01-04 | 2022-01-13 | 2022-01-12 | ANSWRCOMP | Michael Brown | Max's Bot | 2022-03-02 | RFI-0146 - pyth pend, flag placed | CPK03-R2 |  |  |  | FALSE
21029900-0147 | I and C- MSB1-CPK03-R2- MSB1-TET103-1-02 | 2022-01-04 | 2022-01-13 | 2022-01-06 | ANSWRCOMP | Michael Brown | Max's Bot | 2022-03-02 | RFI-0147 - pyth pend, flag placed | CPK03-R2 |  |  |  | FALSE
21029900-0148 | I and C- MSB1-CPK03-R2- Missing Data Sheets | 2022-01-04 | 2022-01-13 | 2022-01-05 | ANSWRCOMP | Michael Brown | Max's Bot | 2022-03-02 | RFI-0148 - pyth pend, flag placed | CPK03-R2 |  |  |  | FALSE
21029900-0149 | Mechanical - CPK03/02-R2 - Commercial Air-Handling Units (Non-Cleanroom) Manufacturers | 2022-01-05 | 2022-01-07 | 2022-02-18 | CLOSED | Alen Troyer | Connor |  |  |  | Not in cold storage |  |  | FALSE
21029900-0150 | Fire - MSB - CPK03 - Conflicts with Fire Risers | 2022-01-05 | 2022-01-12 | 2022-01-18 | CLOSED | Rees Bixler | Connor |  |  |  | Not in cold storage |  |  | FALSE
21029900-0151 | Structural - RA4 - CPK02-R2 - Washer Dimensions | 2022-01-05 | 2022-01-10 | 2022-01-10 | CLOSED | Mitchell Casio | Ernesto | 2022-03-01 | RFI-0151 - pyth pend, flag placed | CPK02-R2, CPK02-R3, CPK03-R2, CPK03-R5, CPK07 |  |  |  | TRUE
21029900-0152 | Process - MSB - CPK01-R2 - Harder AW Clarifications | 2022-01-06 | 2022-01-10 | 2022-01-12 | CLOSED | Alen Troyer | [7 empty] | FALSE
21029900-0153 | Structural - MSB - CPK03-R5 Below Roof Upgrade Conflicts | 2022-01-06 | 2022-01-18 | 2022-01-10 | CLOSED | Steve Mazzoni | Connor | 2022-02-16 | Atached to RFI122 |  |  |  |  | TRUE
21029900-0154 | TEST RFI | 2022-01-06 | 2022-01-18 | 2022-01-24 | ANSWRCOMP | Jenna Stein | [7 empty] | TRUE
21029900-0155 | Dry Mech- CPK02-R2-RA4-Spring Isolation on RAH Recirculation Air Design | 2022-01-05 | 2022-01-07 | 2022-01-10 | CLOSED | Carlos Acosta | Ernesto | 2022-03-03 | RFI-0155 - pyth pend, flag placed | CPK02-R2, CPK02-R8, CPK07 |  |  |  | TRUE
21029900-0156 | Mech - MSB - LLE01 - CPCW Surge Tank (ET) Changes | 2022-01-07 | 2022-01-14 | 2022-01-11 | ANSWRCOMP | Rees Bixler | [7 empty] | FALSE
21029900-0157 | Dry Mech-CPK02-R2-RA4 Table for Spring Isolators Confirmation | 2022-01-07 | 2022-01-19 | 2022-01-10 | CLOSED | Carlos Acosta | Ernesto | 2022-03-03 | RFI-0157 - pyth pend, flag placed | CPK02-R2, CPK02-R8, CPK07 |  |  |  | TRUE
21029900-0158 | Control Valves-MSB-LLP02/CPK03 R2-Damper Size Change Confirmation | 2022-01-07 | 2022-01-19 | 2022-01-11 | ANSWRCOMP | Taylor Bothmann | Taylor Patterson | 2022-02-23 | RFI-0158 - pyth pend, flag placed | LLP02, CPK03-R2 |  |  |  | TRUE
21029900-0159 | I and C - MSB1-CPK03R2-TE218-0-08A - Threaded to Welded | 2022-01-10 | 2022-01-20 | 2022-01-11 | ANSWRCOMP | Michael Brown | Connor | 2022-02-18 | RFI-0159 - pyth and flag pending | CPK03-R2 |  |  |  | TRUE
21029900-0160 | I and C- MSB1-CPK03-R2-MSB1-PLC133-1-00- fiber type to copper | 2022-01-10 | 2022-01-20 | 2022-01-11 | ANSWRCOMP | Michael Brown | Max's Bot | 2022-03-02 | RFI-0160 - pyth pend, flag placed | CPK03-R2 |  |  |  | FALSE
21029900-0161 | Dry Mech-CPK02-R2-RA4-Duct Supports From New HSS Steel Confirmation. | 2022-01-11 | 2022-01-13 | 2022-01-14 | CLOSED | Carlos Acosta | Ernesto | 2022-03-01 | RFI-0161 - pyth pend, flag placed | CPK02-R2, CPK02-R3, CPK02-R5, CPK07 |  |  |  | TRUE
21029900-0162 | I and C- MSB1-CPK03-R2-Revit & Navis Files | 2022-01-11 | 2022-01-21 | 2022-01-27 | CLOSED | Michael Brown | Max's Bot | 2022-03-02 | RFI-0162 - pyth pend, flag placed | CPK03-R2 |  |  |  | FALSE
21029900-0163 | Wet Mech - MSB - CPK03-R2 - Missing Drawing MS1-650-MH-A01 | 2022-01-12 | 2022-01-14 | 2022-01-13 | ANSWRCOMP | Mason Ray | Max's Bot | 2022-03-02 | RFI-0163 - pyth pend, flag placed | CPK03-R2 |  |  |  | FALSE
21029900-0164 | Structural - RA4 - CPK02 - Field Condition Stanchion Conflict | 2022-01-12 | 2022-01-24 | 2022-01-20 | CLOSED | Steve Mazzoni | Ernesto | 2022-03-01 | RFI-0164 - pyth pend, flag placed | CPK02, CPK02-R1, CPK02-R6 |  |  |  | TRUE
21029900-0165 | Structural - MSB- CPK03-R5 RA-ST-2043 Alt Welded Connection | 2022-01-12 | 2022-01-24 | 2022-01-13 | CLOSED | Steve Mazzoni | Connor | 2022-02-16 | RFI-0165 - pyth and flag pending | CPK03-R9, CPK02-R6 |  |  |  | TRUE
21029900-0166 | Structural - MSB - CPK03-R2- MS1-SS-2FM-B0300 TOS Elevations | 2022-01-12 | 2022-01-24 | 2022-01-14 | CLOSED | Steve Mazzoni | Max's Bot | 2022-03-02 | RFI-0166 - pyth pend, flag placed | CPK03-R2, CPK03-R3, CPK03-R9 |  |  |  | TRUE
21029900-0167 | Mech.Electrical.LSS.Telecom.IandC - CPK02-R2 RA4 - RAH 9-13 Conflicts | 2022-01-12 | 2022-01-24 | 2022-01-20 | ANSWRCOMP | Ismael Hernandez | Ernesto | 2022-03-02 | RFI-0167 - pyth pend, flag placed | CPK02-R2, CPK02-R3 |  |  |  | TRUE
21029900-0168 | Process - MSB - CPK03-R2 - C02 Line Change From KEX to KET | 2022-01-13 | 2022-01-17 | 2022-01-13 | CLOSED | Alen Troyer | Max's Bot | 2022-03-02 | RFI-0168 - pyth pend, flag placed | CPK03-R2, CPK03-R7, LLP02-R1 |  |  |  | FALSE
21029900-0169 | Process - MSB - CPK03-R2 - Charter RFI 31- HVPV and PV Clarifications | 2022-01-13 | 2022-01-17 | 2022-01-14 | ANSWRCOMP | Alen Troyer | Max's Bot |  | RFI-0169 - pyth and flag pending | CPK02-R2 | Y |  |  | FALSE
21029900-0170R1 | CSA - MSB - CPK03-R3 - Detail Pages | 2022-01-13 | 2022-01-25 |  | CLOSED | Ellie Runte | Add | [6 empty] | FALSE
21029900-0171 | Process - MSB - CPK03-R2 - Charter RFI#2 - SCHW Missing EOL Components | 2022-01-13 | 2022-01-17 | 2022-01-18 | ANSWRCOMP | Alen Troyer | Max's Bot | 2022-03-02 | RFI-0171 - pyth pend, flag placed | CPK03-R2 |  |  |  | FALSE
21029900-0172 | Mechanical - MSB - CPK03-R2 - Streimer Misc RFIs 8-12 | 2022-01-13 | 2022-01-17 | 2022-01-24 | CLOSED | Alen Troyer | Max's Bot | 2022-03-02 | RFI-0172 - pyth pend, flag placed | CPK03-R2 |  |  |  | FALSE
21029900-0173 | Dry Mech-CPK02-R2-RA4-VFD Schematic for the RAH Units Keynotes Confirmation | 2022-01-13 | 2022-01-17 | 2022-01-14 | CLOSED | Carlos Acosta | Ernesto | 2022-03-03 | RFI-0173 - pyth pend, flag placed | CPK02-R2, CPK07 |  |  |  | FALSE
21029900-0174 | Mechanical - CPK03-R1 - MSB - Harder RFIs 5-6 - GA-11 Valve and Clarifications | 2022-01-13 | 2022-01-17 | 2022-01-14 | CLOSED | Alen Troyer | Connor | 2022-02-16 | RFI-0174 - pyth and flag pending | CPK03, CPK03-R4 |  |  |  | TRUE
21029900-0175 | Process - MSB - CPK03-R2 - Charter RFIs 23-30 | 2022-01-13 | 2022-01-17 | 2022-01-19 | ANSWRCOMP | Alen Troyer | Max's Bot | 2022-03-02 | RFI-0175 - pyth pend, flag placed | CPK03-R2, CPK03-R3, CPK03-R7 |  |  |  | FALSE
21029900-0176 | CSA - MSB - CPK03R2 - Wall Type Clarification | 2022-01-13 | 2022-01-25 | 2022-01-21 | ANSWRCOMP | Ellie Runte | Connor | 2022-02-21 | RFI-0176 - pyth and flag pending | CPK03-R2, CPK03-R8 |  |  |  | TRUE
21029900-0177 | CSA - Structural - CPK02-R1 - Bolted Column Splice Alternative | 2022-01-13 | 2022-01-25 | 2022-01-14 | ANSWRCOMP | Callie Johns | Taylor Patterson | 2022-02-16 | RFI-0177 - pyth pend, flag placed | CPK02-R1 |  |  |  | TRUE
21029900-0178 | CSA - Structural - CPK02-R2 - HSS Infill B&10 | 2022-01-13 | 2022-01-25 | 2022-01-20 | ANSWRCOMP | Callie Johns | Ernesto | 2022-03-07 | RFI-0173 - pyth pend, flag placed | CPK02-R2, CPK02-R3 |  |  |  | FALSE
21029900-0179 | CSA - Structural - CPK02 - Alternate Anchors at Pedestals Anchored to Concrete | 2022-01-13 | 2022-01-25 | 2022-01-20 | ANSWRCOMP | Callie Johns | Ernesto |  | Cannot view RFI documents w/ attachments |  |  |  |  | FALSE
21029900-0180 | CSA - Structural - CPK02-R2 TC Bolts | 2022-01-13 | 2022-01-25 | 2022-01-20 | ANSWRCOMP | Callie Johns | Taylor Patterson | 2022-03-07 | RFI-0180 - pyth pend, flag placed | CPK02-R2, CPK02-R3, CPK02-R4, CPK02-R5, CPK02-R6, CPK02-R8 |  |  |  | FALSE
21029900-0181 | CSA - Structural - CPK02-R2 - Conduit Conflicts | 2022-01-13 | 2022-01-25 | 2022-01-14 | ANSWRCOMP | Callie Johns | Ernesto |  | Cannot view RFI documents w/ attachments |  |  |  |  | FALSE
21029900-0182 | Wet Mech - MSB - CPK03-R2 - CUB4 CHW Pump Suction Diffuser Specification | 2022-01-14 | 2022-01-18 | 2022-01-14 | ANSWRCOMP | Mason Ray | Max's Bot | 2022-03-02 | RFI-0182 - pyth pend, flag placed | CPK03-R2 |  |  |  | TRUE
21029900-0183 | Wet Mech - MSB - CPK03-R2 - Missing Detail RA-PL-D105 | 2022-01-14 | 2022-01-18 | 2022-01-24 | ANSWRCOMP | Mason Ray | Max's Bot | 2022-03-02 | RFI-0183 - pyth pend, flag placed | CPK03-R2, CPK04 |  |  |  | TRUE
21029900-0184 | Wet Mech - MSB - CPK03-R2 - Cooling Coil Mounting Details | 2022-01-14 | 2022-01-18 | 2022-01-27 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0184 - pyth pend, flag placed | CPK03-R2, CPK03-R3, CPK03-R8 |  | Y |  | TRUE
21029900-0185 | Process - RA4 - CPK02-R2 - TCHW Coil Isolation for Future Scope | 2022-01-14 | 2022-01-19 | 2022-01-19 | ANSWRCOMP | Mitch Kovalev | Ernesto | 2022-03-07 | RFI-0185 - pyth pend, flag placed | CPK02-R2, CPK02-R4 |  |  |  | TRUE
21029900-0186 | LSS - RA4 - CPK02-R3 - Missing VESDA Drawings | 2022-01-14 | 2022-01-19 | 2022-01-20 | CLOSED | Mitch Kovalev | Taylor Patterson | 2022-02-16 | RFI-0186 - pyth pend, flag placed | CPK02-R3, CPK02-R4 |  |  |  | TRUE
21029900-0187 | Structural - RA4 - CPK02-R3 - Pipe Support Model Discrepancy | 2022-01-14 | 2022-01-19 | 2022-01-24 | ANSWRCOMP | Mitch Kovalev | Taylor Patterson | No, see notes | Related to model content, not relevant to drawings | Related to model content, not relevant to drawings |  |  |  | TRUE
21029900-0188 | Wet Mech - MSB - CPK03-R2 - BA-5 vs BF-3 on 3" ADA CHWS/R Laterals | 2022-01-14 | 2022-01-26 | 2022-01-24 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0188 - pyth pend, flag placed | CPK03-R2, CPK03-R3 |  | Y |  | TRUE
21029900-0189 | Process - MSB - CPK03-R2 - Charter RFIs 32-41 | 2022-01-19 | 2022-01-21 | 2022-01-25 | ANSWRCOMP | Alen Troyer | Max's Bot | 2022-03-02 | RFI-0189 - pyth pend, flag placed | CPK03-R2, LLP02-R2 |  |  |  | FALSE
21029900-0190 | Electrical CPK03 R2/CPK03 R3 MSB - Panelboard MXD2R50A Confirmation | 2022-01-20 | 2022-01-31 | 2022-01-21 | ANSWRCOMP | Taylor Bothmann | Connor | 2022-02-21 | RFI-0190 - pyth and flag pending | CPK03-R2, CPK03-R3 |  |  |  | TRUE
21029900-0191 | I&C- MSB1-CPK03-R2- Missing Data Sheet PMP272-(16-17-18)-40 | 2022-01-20 | 2022-01-31 | 2022-01-20 | ANSWRCOMP | Michael Brown | Max's Bot |  | RFI-0191 - pyth and flag pending | CPK03-R2 |  | Y |  | TRUE
21029900-0192 | Wet Mech - MSB - CPK03-R2 - CHWS Drawing Continuation Clarification | 2022-01-20 | 2022-01-24 | 2022-01-21 | CLOSED | Mason Ray | Max's Bot |  | RFI-0192 - pyth and flag pending | CPK03-R2, CPK03-R3 |  | Y |  | TRUE
21029900-0193 | Wet Mech - MSB - CPK03-R2 - CHW Pump SSP-3 versus SPP-3 | 2022-01-20 | 2022-01-24 | 2022-01-21 | CLOSED | Mason Ray | Max's Bot | 2022-03-04 | RFI-0193 - pyth and flag placed | CPK03-R2 |  |  |  | TRUE
21029900-0194 | Wet Mech - MSB - CPK03-R2 - MS1-113-D0-Z05 Line Numbering | 2022-01-20 | 2022-01-24 | 2022-01-25 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0194 - pyth and flag placed | CPK03-R2, CPK03-R3 |  | Y |  | TRUE
21029900-0195 | Wet Mech - MSB - CPK03-R2 - CUB-4 CHW Pump FNPT Cap vs. H-1 | 2022-01-20 | 2022-01-24 | 2022-01-24 | ANSWRCOMP | Mason Ray | Max's Bot | 2022-03-04 | RFI-0195 - pyth and flag pending | CPK03-R2 |  |  |  | TRUE
21029900-0196 | Wet Mech - MSB - CPK03-R2 - Branch Order Discrepancy Between P&ID and BIM Model | 2022-01-20 | 2022-01-24 | 2022-01-31 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0196 - pyth and flag pending | CPK03-R2, CPK03-R3 |  | Y |  | TRUE
21029900-0197 | Electrical CPK03 R3 MSB - Equipment Tag Confirmation | 2022-01-20 | 2022-01-31 | 2022-01-26 | ANSWRCOMP | Taylor Bothmann | Connor | 2022-02-21 | RFI-0197 - pyth and flag pending | CPK03-R9 |  |  |  | TRUE
21029900-0198 | Wet Mech - MSB - CPK03-R2 - BA-73 in Lieu of BA-6 on Propress IDC Piping Line Class | 2022-01-20 | 2022-01-24 | 2022-01-21 | ANSWRCOMP | Mason Ray | Max's Bot | 2022-03-04 | RFI-0198 - pyth and flag pending | CPK03-R2, CPK03-R3 |  |  |  | TRUE
21029900-0199 | Electrical B0001-CPK03 R2 MSB ECR Clarifications | 2022-01-20 | 2022-01-31 | 2022-02-18 | CLOSED | Taylor Bothmann | Connor |  | RFI-0199 - pyth and flag pending |  | Not in cold storage |  |  | FALSE
21029900-0200 | Electrical - CPK03 R2 MSB L2 Cleanroom Wall Ground Clarifications | 2022-01-20 | 2022-01-31 | 2022-01-25 | ANSWRCOMP | Taylor Bothmann |  |  | In model |  |  |  |  | TRUE
21029900-0201 | DRY-MECH-CPK02-R2-RAH Units Return Air Damper Removal Confirmation | 2022-01-20 | 2022-01-24 | 2022-01-26 | CLOSED | Carlos Acosta | Taylor Patterson | 2022-03-07 | RFI-0201 - pyth pend, flag placed | CPK02-R2, CPK02-R8, CPK07 |  |  |  | TRUE
21029900-0202 | Process - RA4 - LLP02-R1 - Vibration Isolation for IMO Carbonator pumps | 2022-01-20 | 2022-01-25 | 2022-01-31 | ANSWRCOMP | Rees Bixler | Taylor Patterson | 2022-02-24 | RFI-0202 - pyth and flag pending | LLP02-R1, CPK02-R4 |  |  |  | TRUE
21029900-0203 | Process - MSB - LLP02-R1 - Confirmation of CO2 gas pressure to the IMO Carbonator skid | 2022-01-20 | 2022-01-25 | 2022-01-24 | ANSWRCOMP | Rees Bixler | Taylor Patterson | 2022-02-24 | RFI-0203 - pyth and flag pending | LLP02-R1 |  |  |  | TRUE
21029900-0204 | Process - RA4 - LLP02-R1 - Confirmation of space available around the RA4 CO2DI skid | 2022-01-20 | 2022-01-25 | 2022-01-28 | ANSWRCOMP | Rees Bixler | Taylor Patterson | 2022-02-24 | RFI-0204 - pyth and flag pending | LLP02-R1, CPK02-R4 |  |  |  | TRUE
21029900-0205 | Process - MSB - LLP02-R1 - Confirmation of Chilled Water Supply Conditions to the CHCO2DI Heat Exchanger | 2022-01-20 | 2022-01-25 | 2022-01-24 | ANSWRCOMP | Rees Bixler | Taylor Patterson | 2022-02-25 | RFI-0205 - pyth and flag pending | LLP02-R1 |  |  |  | TRUE
21029900-0206 | I&C- MSB1-CPK03-R2- FE Datasheet Revise | 2022-01-21 | 2022-02-01 | 2022-01-27 | ANSWRCOMP | Michael Brown | Max's Bot |  | RFI-0206 - pyth and flag pending | MOVED TO ANSWERED RFIS |  | Y |  | TRUE
21029900-0207 | Wet Mech - MSB - CPK03-R2 - PI-12 Pressure Gauge Range | 2022-01-21 | 2022-01-25 | 2022-01-25 | ANSWRCOMP | Mason Ray | Max's Bot | 2022-03-04 | RFI-0207 - pyth and flag Placed | CPK03-R2 |  |  |  | TRUE
21029900-0208 | I&C- MSB1-CPK03-R2- Panel Anchoring | 2022-01-21 | 2022-02-01 | 2022-01-25 | ANSWRCOMP | Michael Brown | Max's Bot |  | RFI-0208 - pyth and flag pending | CPK03-R2 |  | Y |  | TRUE
21029900-0209 | Process - MSB - CPK03-R2 - Charter RFIs 42-61 | 2022-01-21 | 2022-01-25 | 2022-01-31 | CLOSED | Alen Troyer | Max's Bot |  | RFI-0209 - pyth and flag pending | LOTS OF RFIS |  | Y |  | TRUE
21029900-0210 | Process - MSB - CPK03-R2 - Charter RFIs 62-103 | 2022-01-21 | 2022-01-25 | 2022-01-31 | CLOSED | Alen Troyer | Max's Bot |  | RFI-0210 - pyth and flag pending |  |  | Y | FALSE | FALSE
21029900-0211 | Mechanical - CPK03-R3 - Streimer RFI 14 - Mising HXRA tap in Bay K | 2022-01-21 | 2022-01-25 | 2022-01-26 | CLOSED | Alen Troyer | Add | [6 empty] | FALSE
21029900-0212 | Mechanical - CPK03-R2 - MSB - Streimer RFI #13 - False Load Location | 2022-01-22 | 2022-01-25 | 2022-01-25 | CLOSED | Alen Troyer | Max's Bot |  | RFI-0212 - pyth and flag pending |  |  |  |  | FALSE
21029900-0213 | Mechanical - CPK03-R2 - MSB - BCS Day Tank to EXSC Main PID Missing Damper | 2022-01-22 | 2022-01-25 | 2022-01-31 | ANSWRCOMP | Alen Troyer | Max's Bot |  | RFI-0213 - pyth and flag pending |  |  |  |  | FALSE
21029900-0214 | Mechanical - CPK03-R2 - MSB - Exhaust Submain Damper Actuator Orientation | 2022-01-22 | 2022-01-25 | 2022-02-04 | ANSWRCOMP | Alen Troyer | Max's Bot |  | RFI-0214 - pyth and flag pending |  |  |  |  | TRUE
21029900-0215 | Process - CPK03-R2 - MSB - CPCW Distribution Pumps Discharge Nozzle Size | 2022-01-24 | 2022-01-31 | 2022-01-28 | ANSWRCOMP | Rees Bixler | Max's Bot |  | RFI-0215 - pyth and flag pending |  |  |  |  | FALSE
21029900-0216 | Wet Mech - MSB - CPK03-R2 - Reducers to TCVs | 2022-01-24 | 2022-01-26 | 2022-01-25 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0216 - pyth and flag pending |  |  |  |  | FALSE
21029900-0217 | Process - CPK03-R3 - FFU Layout near AC-52 | 2022-01-24 | 2022-02-02 | 2022-01-26 | ANSWRCOMP | Alen Troyer | Add | [6 empty] | FALSE
21029900-0218 | MECH-CPK-02-R2-RA4-Ceiling Diffusers CD9 and CD10 Type Confirmation | 2022-01-24 | 2022-01-26 | 2022-01-25 | CLOSED | Carlos Acosta | Ernesto | 2022-03-07 | RFI-0218 - pyth pend, flag placed | CPK02-R2, CPK07 |  |  |  | TRUE
21029900-0219 | Mechanical - CPK03-R2 - EXGF and EXSC Design vs IFF Content Missing | 2022-01-24 | 2022-01-26 | 2022-01-27 | OPEN | Alen Troyer | Max's Bot |  | RFI-0219 - pyth and flag pending |  |  |  |  | FALSE
21029900-0220 | Process - MSB - CPK03-R2 - Charter RFI#107 SPP-107 Design Information Missing | 2022-01-24 | 2022-01-26 | 2022-01-28 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0220 - pyth and flag pending |  |  |  |  | FALSE
21029900-0221 | CSA - MSB - CPK03-R3 MS2B05 Wall Clarification | 2022-01-24 | 2022-02-02 | 2022-01-28 | CLOSED | Ellie Runte | Add | [6 empty] | FALSE
21029900-0222 | Process - MSB - CPK03-R2 - Charter RFI#108 FI-3 GPM Part Number Discrepancy from Specification | 2022-01-24 | 2022-01-26 | 2022-02-01 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0222 - pyth and flag pending |  |  |  |  | FALSE
21029900-0223 | Mech - MSB - CPK03-R2 - MSB EXGB Fan Orientation and Reducer Question | 2022-01-24 | 2022-01-31 | 2022-01-25 | CLOSED | Rees Bixler | Max's Bot |  | RFI-0223 - pyth and flag pending |  |  |  |  | FALSE
21029900-0224 | Wet Mech - MSB - CPK03-R2 - MSB TCHWS-R Piping Line Class Spec Change | 2022-01-24 | 2022-01-26 | 2022-01-25 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0224 - pyth and flag pending |  |  |  |  | FALSE
21029900-0224R1 | Wet Mech - MSB - CPK03-R2 - MSB TCHWS-R Piping Line Class Spec Change Rev1 | 2022-01-28 | 2022-01-31 | 2022-02-02 | CLOSED | Mason Ray | Max's Bot |  | RFI-24R1 - pyth and flag pending |  |  |  |  | FALSE
21029900-0225 | Process - MSB - CPK03-R2 - Charter RFI#109 OFA Lateral EOL Valve Clash | 2022-01-25 | 2022-01-27 | 2022-01-31 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0225 - pyth and flag pending |  |  |  |  | FALSE
21029900-0226 | Structural - MSB - CPK03-R5 Conflicts with Continuity Plates | 2022-01-25 | 2022-02-03 | 2022-01-27 | ANSWRCOMP | Steve Mazzoni | Connor | 2022-02-21 | RFI-0226 - pyth and flag pending | CPK03-R5 |  |  |  | TRUE
21029900-0227 | Process - MSB - CPK03-R2 - Charter RFI#111 CPCW FI-25 Flow Range | 2022-01-25 | 2022-01-27 | 2022-01-31 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0227 - pyth and flag pending |  |  |  |  | FALSE
21029900-0228 | Process - MSB - CPK03-R2 - Charter RFI#112 SHPOFA Spec Correction | 2022-01-25 | 2022-01-27 | 2022-01-31 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0228 - pyth and flag pending |  |  |  |  | FALSE
21029900-0229 | Process - MSB - CPK03-R2 - Charter RFI#113 CPCW ET PSV Tag and Size | 2022-01-25 | 2022-01-27 | 2022-02-01 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0229 - pyth and flag pending |  |  |  |  | FALSE
21029900-0230 | Process - MSB - CPK03-R2 - Charter RFI#114 CPCW EOL FI PI and D versus Model Conflict | 2022-01-25 | 2022-01-27 | 2022-02-01 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0230 - pyth and flag pending |  |  |  |  | FALSE
21029900-0231 | Process - MSB - CPK03-R2 - Charter RFI#116 DDA Spec Piping Finishes | 2022-01-25 | 2022-01-27 | 2022-01-31 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0231 - pyth and flag pending |  |  |  |  | FALSE
21029900-0232 | Process - MSB - CPK03-R2 - Charter RFI#117 NaOH Line Size | 2022-01-25 | 2022-01-27 | 2022-01-31 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0232 - pyth and flag pending |  |  |  |  | FALSE
21029900-0233 | Process - MSB - CPK03-R2 - Charter RFI#118 UPS PRV Swap | 2022-01-25 | 2022-01-27 | 2022-01-31 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0233 - pyth and flag pending |  |  |  |  | FALSE
21029900-0234 | Mechanical - CPK03-R2 - MSB - Streimer RFI#015 Structural Clearance with Supports | 2022-01-25 | 2022-01-27 | 2022-01-27 | CLOSED | Mason Ray | Max's Bot |  | RFI-0234 - pyth and flag pending |  |  |  |  | FALSE
21029900-0235 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#039 CHWS/R and SCHWS/R Insulation | 2022-01-25 | 2022-01-27 | 2022-01-26 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0235 - pyth and flag pending |  |  |  |  | FALSE
21029900-0236 | MECH-ELEC-InC-CPK02-R2 RAH Units System Tag in MEL Log | 2022-01-25 | 2022-02-03 | 2022-02-03 | CLOSED | Carlos Acosta | Ernesto | 2022-03-07 | RFI-0236 - pyth pend, flag placed | CPK02-R2 |  |  |  | TRUE
21029900-0237 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#040 Lateral EOL Shunt Detail | 2022-01-25 | 2022-01-27 | 2022-02-01 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0237 - pyth and flag pending |  |  |  |  | FALSE
21029900-0237R1 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#040 Lateral EOL Shunt Detail R1 | 2022-02-18 | 2022-02-22 | 2022-02-21 | ANSWRCOMP | Mason Ray | [7 empty] | TRUE
21029900-0238 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#043 TCHW Suction Diffusers | 2022-01-25 | 2022-01-27 | 2022-01-27 | CLOSED | Mason Ray | Max's Bot |  | RFI-0238 - pyth and flag pending |  |  |  |  | FALSE
21029900-0239 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#044 PSV Datasheet for CHWS | 2022-01-25 | 2022-01-27 | 2022-01-31 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0239 - pyth and flag pending |  |  |  |  | FALSE
21029900-0240 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#046 Safety Shower Location 4121F2 | 2022-01-25 | 2022-01-27 | 2022-02-01 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0240 - pyth and flag pending |  |  |  |  | FALSE
21029900-0241 | Process - RA4 - CPK02-R2 - PDIT Valve Specification | 2022-01-25 | 2022-01-27 | 2022-01-31 | ANSWRCOMP | Mitch Kovalev | Taylor Patterson | 2022-03-07 | RFI-0241 - pyth pend, flag placed, new MEL slipsheeted | CPK02-R2, CPK02-R8, CPK07 |  |  |  | TRUE
21029900-0242 | Process - RA4 - CPK02-R2 - BF-23 Callout Location | 2022-01-25 | 2022-01-27 | 2022-02-01 | ANSWRCOMP | Mitch Kovalev | Ernesto | 2022-03-08 | RFI-0242 - pyth pend, flag placed | LLE01, CPK02-R2 |  |  |  | TRUE
21029900-0243 | Process - RA4 - CPK02-R2 - UN2 1/2" KET Jumper Assembly | 2022-01-25 | 2022-01-27 | 2022-01-28 | ANSWRCOMP | Mitch Kovalev | Ernesto | 2022-03-07 | RFI-0243 - pyth pend, flag placed | CPK02-R2. CPK02-R4, CPK07 |  |  |  | TRUE
21029900-0244 | Process - RA4 - CPK02-R2 - BIO Spec Change From Tank | 2022-01-25 | 2022-01-27 | 2022-02-01 | ANSWRCOMP | Mitch Kovalev | Ernesto | 2022-03-07 | RFI-0244 - pyth pend, flag placed | CPK02-R2 |  |  |  | TRUE
21029900-0245 | Process - RA4 - CPK02-R2 - PV Reducer Clarification | 2022-01-25 | 2022-01-27 | 2022-02-01 | ANSWRCOMP | Mitch Kovalev | Ernesto | 2022-03-07 | RFI-0245 - pyth pend, flag placed | CPK02-R2, CPK02-R4 |  |  |  | TRUE
21029900-0246 | Process - RA4 - CPK02-R2 - Safety Shower Relocation Clarification | 2022-01-25 | 2022-01-27 | 2022-02-01 | ANSWRCOMP | Mitch Kovalev | Ernesto | 2022-03-07 | RFI-0246 - pyth pend, flag placed | CPK02-R2, CPK02-R4 |  |  |  | TRUE
21029900-0247 | MSB - CSA - CPK03-R2&CPK03-R3 M16 Rod Drops at Embed Strut Alternate Details | 2022-01-26 | 2022-02-04 | 2022-01-27 | ANSWRCOMP | Ellie Runte | Max's Bot |  | RFI-0247 - pyth and flag pending |  |  |  |  | TRUE
21029900-0248 | Mechanical - CPK03-R2 - Streimer RFI 16 - Scrubber Expansion Joint Length of Flex | 2022-01-26 | 2022-01-28 | 2022-01-27 | CLOSED | Alen Troyer | Max's Bot |  | RFI-0248 - pyth and flag pending |  |  |  |  | FALSE
21029900-0249 | Process - MSB - CPK03-R2 - Charter RFI#121 HFW and SCB DrainTransition | 2022-01-26 | 2022-01-28 | 2022-01-27 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0249 - pyth and flag pending |  |  |  |  | FALSE
21029900-0250 | Process - MSB - CPK03-R2 - Charter RFI#122 HFW and SCB Line Centralizer | 2022-01-26 | 2022-01-28 | 2022-01-27 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0250 - pyth and flag pending |  |  |  |  | FALSE
21029900-0251 | Process - MSB - CPK03-R2 - Charter RFI#123 Clamshell Clarification | 2022-01-26 | 2022-01-28 | 2022-02-03 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0251 - pyth and flag pending |  |  |  |  | FALSE
21029900-0252 | Process - MSB - CPK03-R2 - Charter RFI#124 PI-221-1 Specification Needed | 2022-01-26 | 2022-01-28 | 2022-02-01 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0252 - pyth and flag pending |  |  |  |  | FALSE
21029900-0253 | Process - MSB - CPK03-R2 - Charter RFI#119 GL-66H Procurement/Design Questions | 2022-01-26 | 2022-01-28 | 2022-02-02 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0253 - pyth and flag pending |  |  |  |  | FALSE
21029900-0254 | M10 Rod Drops at Embed Strut Alternate Details | 2022-01-26 | 2022-02-04 | 2022-01-27 | ANSWRCOMP | Ellie Runte | [7 empty] | FALSE
21029900-0255 | CSA - MSB - CPK03-R2 & CPK03-R3 - Cleanroom Slider Door Clarification | 2022-01-27 | 2022-02-02 | 2022-02-16 | ANSWRCOMP | Ellie Runte | Max's Bot |  | RFI-0255 - pyth and flag pending |  |  |  |  | TRUE
21029900-0256 | Mechanical - CPK01 - Harder RFI 7 - AW Vent, UN2, and HPO2 Model Clash Resolutions | 2022-01-27 | 2022-01-31 | 2022-02-04 | CLOSED | Alen Troyer | [7 empty] | FALSE
21029900-0257 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#057 TCHW Conflict with Brace BT-17 | 2022-01-27 | 2022-01-31 | 2022-02-02 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0257 - pyth and flag pending |  |  |  |  | FALSE
21029900-0258 | Wet Mech - MSB - CPK03-R2 - TCHW Conflict with Brace at BT/14 and BT/46 | 2022-01-27 | 2022-01-31 | 2022-02-02 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0258 - pyth and flag pending |  |  |  |  | FALSE
21029900-0259 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#062 Safety Shower Locations | 2022-01-27 | 2022-02-07 | 2022-02-04 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0259 - pyth and flag pending |  |  |  |  | TRUE
21029900-0260 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#070 TCHW Conflict with Steel at BT-54 and BT-55 | 2022-01-27 | 2022-01-31 | 2022-02-02 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0260 - pyth and flag pending |  |  |  |  | FALSE
21029900-0261 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#071 TCHW Coil Size Discrepancy | 2022-01-27 | 2022-01-31 | 2022-02-02 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0261 - pyth and flag pending |  |  |  |  | FALSE
21029900-0262 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#072 Missing Model Content UPN 213 Level 2FA | 2022-01-27 | 2022-01-31 | 2022-01-28 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0262 - pyth and flag pending |  |  |  |  | FALSE
21029900-0263 | Process - RA4 - CPK02-R2 - BA-59s on Specification JEA | 2022-01-27 | 2022-01-31 | 2022-02-02 | ANSWRCOMP | Mitch Kovalev | Ernesto | 2022-03-08 | RFI-0263 - pyth pend, flag placed | CPK02-R2 |  |  |  | TRUE
21029900-0264 | Process - RA4 - CPK02-R2 - TCHW Bypass | 2022-01-27 | 2022-01-31 | 2022-02-02 | ANSWRCOMP | Mitch Kovalev | Ernesto | 2022-03-08 | RFI-0264 - pyth pend, flag placed | CPK02-R2, CPK02-R8, CPK07 |  |  |  | TRUE
21029900-0265 | Process - RA4 - CPK02-R2 - SHCWS BA-8 | 2022-01-27 | 2022-01-31 | 2022-02-02 | ANSWRCOMP | Mitch Kovalev | Ernesto | 2022-03-08 | RFI-0265 - pyth pend, flag placed | CPK02-R2, LLE01 |  |  |  | TRUE
21029900-0266 | Mechanical - CPK03-R2 - MSB - Streimer RFI 17 - Level 1/Level 2 Spring Can Hangers | 2022-01-27 | 2022-01-31 | 2022-01-28 | ANSWRCOMP | Alen Troyer | Max's Bot |  | RFI-0266 - pyth and flag pending |  |  |  |  | FALSE
21029900-0267 | Process - RA4 - CPK02-R2 - Design Discrepancy for Piping to TCHW, CHW Equipment | 2022-01-27 | 2022-01-31 | 2022-02-02 | ANSWRCOMP | Mitch Kovalev | Ernesto | 2022-03-08 | RFI-0267 - pyth pend, flag placed | CPK02-R2, CPK02-R4, CPK02-R8, CPK07, CPK03, CPK03-R2, CPK03-R3, CPK04 |  |  |  | TRUE
21029900-0268 | DRY MECH-CPK02-R2-RA4 EXGF Blast Gate Vs Damper Confirmation | 2022-01-27 | 2022-02-07 | 2022-02-01 | CLOSED | Carlos Acosta | Ernesto | 2022-03-08 | RFI-0268 - pyth pend, flag placed | CPK02-R2 |  |  |  | TRUE
21029900-0269 | DRYMECH-ELEC-CPK02-R2-RA4-Conduit Relocation at Grid C,D,10.5, B and F of Subfab Level. | 2022-02-01 | 2022-02-03 | 2022-02-02 | CLOSED | Carlos Acosta | Ernesto | 2022-03-08 | RFI-0269 - pyth pend, flag placed | CPK02-R2, CPK02-R3 |  |  |  | TRUE
21029900-0270 | Process - RA4 - CPK02-R2 - HRWS/R Piping Demo | 2022-01-27 | 2022-01-31 | 2022-02-02 | ANSWRCOMP | Mitch Kovalev | Ernesto |  | Taylor |  |  |  |  | TRUE
21029900-0271 | Structural - CPK02-R2 CUPS Conflicts Sector E | 2022-01-27 | 2022-02-07 | 2022-02-03 | ANSWRCOMP | Ismael Hernandez | Ernesto |  | RFI-0271 - pyth pend, flag placed | CPK02-R2, CPK02-R3, CPK02-R8, CPK07 |  |  |  | TRUE
21029900-0272 | Process - MSB - CPK03-R2 - Charter RFI#126 Spec Gas Routing Zone Clash | 2022-01-28 | 2022-01-31 | 2022-02-02 | CLOSED | Mason Ray | Max's Bot |  | RFI-0272 - pyth and flag pending |  |  |  |  | FALSE
21029900-0273 | Process - MSB - CPK03-R2 - Charter RFI#127 AB1N-S, AC1N-S Wye Spacing | 2022-01-28 | 2022-01-31 | 2022-02-01 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0273 - pyth and flag pending |  |  |  |  | FALSE
21029900-0274 | Process - MSB - CPK03-R2 - Charter RFI#128 PCAr Column Drops | 2022-01-28 | 2022-01-31 | 2022-02-02 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0274 - pyth and flag pending |  |  |  |  | FALSE
21029900-0275 | Process - MSB - CPK03-R2 - Charter RFI#129 Tubing Bends Vs. Fittings | 2022-01-28 | 2022-01-31 | 2022-02-02 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0275 - pyth and flag pending |  |  |  |  | FALSE
21029900-0276 | Process - MSB - CPK03-R2 - Charter RFI#130 Crosby 900 PSV-PRV Clarification | 2022-01-28 | 2022-01-31 | 2022-01-31 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0276 - pyth and flag pending |  |  |  |  | FALSE
21029900-0277 | Process - MSB - CPK03-R2 - Charter RFI#131 CV and EX Mismatch | 2022-01-28 | 2022-01-31 | 2022-02-02 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0277 - pyth and flag pending |  |  |  |  | FALSE
21029900-0278 | Process - MSB - CPK03-R2 - Charter RFI#132 Spec Gas Submain EOL Points | 2022-01-28 | 2022-01-31 | 2022-02-02 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0278 - pyth and flag pending |  |  |  |  | FALSE
21029900-0279 | Process - MSB - CPK03-R2 - Charter RFI#133 QCHA Wye and Valve Not Shown | 2022-01-28 | 2022-01-31 | 2022-02-02 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0279 - pyth and flag pending |  |  |  |  | FALSE
21029900-0280 | Process - MSB - CPK03-R2 - Charter RFI#122 HFW and SCB Line Centralizer | 2022-01-28 | 2022-01-31 |  | VOID | Mason Ray | Max's Bot |  | RFI-0280 - pyth and flag pending |  |  |  |  | FALSE
21029900-0281 | Process - RA4 - CPK02-R4 - Zero Reference Clarification | 2022-01-28 | 2022-02-01 | 2022-02-04 | ANSWRCOMP | Mitch Kovalev | Ernesto |  | Ernesto |  |  |  |  | TRUE
21029900-0282 | Process - RA4 - CPK02-R4 - Bearing Air Valve Clarification | 2022-01-28 | 2022-02-01 | 2022-02-02 | ANSWRCOMP | Mitch Kovalev | Ernesto | [6 empty] | TRUE
21029900-0283 | Process - RA4 - CPK02-R2 - IW Insulation Clarification | 2022-01-28 | 2022-02-01 | 2022-02-03 | ANSWRCOMP | Mitch Kovalev | Ernesto | [6 empty] | TRUE
21029900-0284 | Process - MSB - CPK03-R2 - Charter RFI#136 FRP Reinforced Blind Flange | 2022-02-01 | 2022-02-03 | 2022-02-04 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0284 - pyth and flag pending |  |  |  |  | TRUE
21029900-0285 | Process - MSB - CPK03-R2 - Charter RFI#137 UPN 412 Clash with Lateral Racks | 2022-02-01 | 2022-02-03 | 2022-02-03 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0285 - pyth and flag pending |  |  |  |  | TRUE
21029900-0286 | Structural - MSB - CPK03-R2- South MAH Platform Changes | 2022-02-01 | 2022-02-10 | 2022-02-01 | ANSWRCOMP | Steve Mazzoni | Max's Bot |  | RFI-0286 - pyth and flag pending |  |  |  |  | TRUE
21029900-0287 | Process - MSB - CPK03-R2 - Charter RFI#138 SHCW FI-1 Range Needed | 2022-02-01 | 2022-02-03 | 2022-02-03 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0287 - pyth and flag pending |  |  |  |  | TRUE
21029900-0287R1 | Process - MSB - CPK03-R2 - Charter RFI#138.1 GF Revised Range | 2022-02-15 | 2022-02-17 | 2022-02-15 | OPEN | Mason Ray | Max's Bot |  | RFI-87R1 - pyth and flag pending |  |  |  |  | FALSE
21029900-0288 | Mechanical - CPK03-R2 - Streimer RFI 18 - Damper Rotation Clashes | 2022-02-01 | 2022-02-03 | 2022-02-17 | CLOSED | Alen Troyer | Max's Bot |  | RFI-0288 - pyth and flag pending |  |  |  |  | FALSE
21029900-0289 | Process - MSB - CPK03-R2 - Charter RFI#139 CSW & GSW Low Point Discrepancy | 2022-02-01 | 2022-02-03 | 2022-02-03 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0289 - pyth and flag pending |  |  |  |  | TRUE
21029900-0290 | Process - MSB - CPK03-R2 - Charter RFI#140 CHCO2DI Missing DA-26 | 2022-02-01 | 2022-02-03 | 2022-02-08 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0290 - pyth and flag pending |  |  |  |  | TRUE
21029900-0291 | Process - MSB - CPK03-R2 - Charter RFI#141 CPCW EOL Size Discrepancy | 2022-02-01 | 2022-02-03 | 2022-02-03 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0291 - pyth and flag pending |  |  |  |  | TRUE
21029900-0292 | Structural - MSB - CPK03-R5 - RA-ST-2001 Key Note 4 and 6 Callout | 2022-02-01 | 2022-02-10 | 2022-02-02 | CLOSED | Steve Mazzoni | Connor | 2022-02-16 | RFI-0292 - pyth and flag pending | CPK03-R5 |  |  |  | TRUE
21029900-0293 | DRY MECH-CPK02-RA4- Diffuser and Supply Grille Cans Vs Ceiling Grid Conflicts | 2022-02-01 | 2022-02-03 | 2022-02-04 | CLOSED | Carlos Acosta | Ernesto | [6 empty] | TRUE
21029900-0293R1 | DRY MECH-CPK02-RA4- Diffuser and Supply Grille Cans Vs Ceiling Grid Conflicts | 2022-02-01 | 2022-02-03 |  | CLOSED | Carlos Acosta | [7 empty] | TRUE
21029900-0294 | DRYMECH-CSA-CPK02-R2-RA4-Plenum Wall Extension | 2022-02-01 | 2022-02-10 | 2022-02-04 | CLOSED | Carlos Acosta | Ernesto | [6 empty] | TRUE
21029900-0295 | Process - MSB - CPK03-R2 - Charter RFI#78.1 CPCW Mechanical Area Issues | 2022-02-01 | 2022-02-03 | 2022-02-04 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0295 - pyth and flag pending |  |  |  |  | TRUE
21029900-0296 | Structural - MSB - CPK03-R2 - RA-ST-2031 P2343 Change to P2341 | 2022-02-01 | 2022-02-10 | 2022-02-04 | ANSWRCOMP | Steve Mazzoni | Max's Bot |  | RFI-0296 - pyth and flag pending |  |  |  |  | TRUE
21029900-0297 | Structural - CPK01-R2 - Harder RFI 9 - U57 and AD57 Column Strut Rack Conflict | 2022-02-01 | 2022-02-03 | 2022-02-04 | ANSWRCOMP | Alen Troyer | [7 empty] | TRUE
21029900-0298 | DRYMECH-CPK02-R2-RA4- Duct Sizing Confirmation | 2022-02-01 | 2022-02-10 | 2022-02-02 | CLOSED | Carlos Acosta | Ernesto | [6 empty] | TRUE
21029900-0299 | DRYMECH-CSA-CPK02-R2-RA4-Duct Vs Tube Steel Conflict at Grid F and 10 Confirmation | 2022-02-01 | 2022-02-10 | 2022-02-10 | ANSWRCOMP | Carlos Acosta | Ernesto | [6 empty] | TRUE
21029900-0300 | Electrical - MSB LLE01 VFD202-3-10 CPCW Distribution Pump Confirmation | 2022-02-01 | 2022-02-10 | 2022-02-03 | ANSWRCOMP | Taylor Bothmann | [7 empty] | TRUE
21029900-0301 | DRYMECH-ELEC-CPK02-RA4-Conduit Relocation at Grid E.5 and 13 of Subfab Level | 2022-02-01 | 2022-02-10 | 2022-02-07 | CLOSED | Carlos Acosta | Ernesto | [6 empty] | TRUE
21029900-0302 | CSA - MSB - CPK03-R3 - Scrubber Pad Clarifications | 2022-02-01 | 2022-02-10 | 2022-02-03 | CLOSED | Ellie Runte | Add | [6 empty] | FALSE
21029900-0303 | Structural - MSB - CPK01- R2 - AE-56 Subfab Rack Steel Connection As-Built | 2022-02-01 | 2022-02-10 | 2022-02-07 | ANSWRCOMP | Steve Mazzoni | [7 empty] | TRUE
21029900-0304 | Electrical CPK03 R2 CMXR1M53B Panel Confirmation | 2022-02-01 | 2022-02-10 | 2022-02-04 | ANSWRCOMP | Taylor Bothmann | Connor |  | Updated in CPK03-R9 |  |  |  |  | TRUE
21029900-0305 | Electrical B0001-CPK03-R2 MSB ERC Source Panel MXR1N53B Confirmation | 2022-02-01 | 2022-02-10 | 2022-02-03 | ANSWRCOMP | Taylor Bothmann | Max's Bot |  | RFI-0305 - pyth and flag pending |  |  |  |  | TRUE
21029900-0306 | Electrical B0001-CPK03-R2 MSB Ground Wire Size Confirmation | 2022-02-01 | 2022-02-10 | 2022-02-03 | ANSWRCOMP | Taylor Bothmann | Max's Bot |  | RFI-0306 - pyth and flag pending |  |  |  |  | TRUE
21029900-0307 | Electrical CPK03 R2 ECR Source Panel MXR1R53B Confirmation | 2022-02-02 | 2022-02-11 | 2022-02-04 | ANSWRCOMP | Taylor Bothmann | Connor |  | Updated in CPK03-R9 |  |  |  |  | TRUE
21029900-0308 | CSA - RA4 - CPk02-R4 - Details and Keynote Clarification | 2022-02-02 | 2022-02-04 | 2022-02-04 | ANSWRCOMP | Mitchell Casio | Ernesto | [6 empty] | TRUE
21029900-0309 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#079 TI-2 Gauge Requirement | 2022-02-02 | 2022-02-04 | 2022-02-03 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0309 - pyth and flag pending |  |  |  |  | FALSE
21029900-0310 | Process - MSB - CPK03-R2 - Charter RFI#118 UPS PRV Swap V582 | 2022-02-02 | 2022-02-04 | 2022-02-04 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0310 - pyth and flag pending |  |  |  |  | TRUE
21029900-0311 | Electrical- CPK03-R2 ECR 30A Construction Receptacles MXR2X57B | 2022-02-02 | 2022-02-11 | 2022-02-04 | ANSWRCOMP | Michael Brown | Max's Bot |  | RFI-0311 - pyth and flag pending |  |  |  |  | TRUE
21029900-0312 | Process - MSB - CPK03-R2 - Charter RFI#142 CPCW Valve Handles Clash | 2022-02-02 | 2022-02-04 | 2022-02-04 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0312 - pyth and flag pending |  |  |  |  | TRUE
21029900-0313 | Process - MSB - CPK03-R2 - Charter RFI#143 OFA Lateral in Bay U Ductwork Clash | 2022-02-02 | 2022-02-04 | 2022-02-04 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0313 - pyth and flag pending |  |  |  |  | TRUE
21029900-0314 | Process - MSB - CPK03-R2 - Charter RFI#144 Future Branch Missing | 2022-02-02 | 2022-02-04 | 2022-02-04 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0314 - pyth and flag pending |  |  |  |  | TRUE
21029900-0314R1 | Process - MSB - CPK03-R2 - Charter RFI#144 Future Branch Missing R1 | 2022-02-02 | 2022-02-04 | 2022-02-15 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-14R1 - pyth and flag pending |  |  |  |  | TRUE
21029900-0315 | Process - MSB - CPK03-R2 - Charter RFI#145 Inaccessible Cleanout on CSW Submain | 2022-02-02 | 2022-02-04 | 2022-02-04 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0315 - pyth and flag pending |  |  |  |  | TRUE
21029900-0316 | Electrical - CPK02-R2 RA4 D-Board R4D1C15A Future Tag Discrepancy - Confirming | 2022-02-02 | 2022-02-11 | 2022-02-03 | ANSWRCOMP | Ismael Hernandez | Ernesto | [6 empty] | TRUE
21029900-0317 | Electrical- CPK03-R2 30A Conduit Size Request | 2022-02-02 | 2022-02-11 | 2022-02-04 | ANSWRCOMP | Michael Brown | Max's Bot |  | RFI-0317 - pyth and flag pending |  |  |  |  | TRUE
21029900-0318 | Electrical- CPK03-R2 ECR for MXT2S57E | 2022-02-02 | 2022-02-11 | 2022-02-04 | ANSWRCOMP | Michael Brown | Max's Bot |  | RFI-0318 - pyth and flag pending |  |  |  |  | TRUE
21029900-0319 | Electrical- CPK03-R2 ECR MS1-GMAH103-01-00 | 2022-02-02 | 2022-02-11 | 2022-02-04 | ANSWRCOMP | Michael Brown | Max's Bot |  | RFI-0319 - pyth and flag pending |  |  |  |  | TRUE
21029900-0320 | Electrical- CPK03-R2 ECR Missing for LDP-AB57-02 | 2022-02-02 | 2022-02-11 | 2022-02-04 | ANSWRCOMP | Michael Brown | Max's Bot |  | RFI-0320 - pyth and flag pending |  |  |  |  | FALSE
21029900-0321 | Electrical - CPK02-R2 RA4 Existing Column Mounted Electrical Devices - Confirming | 2022-02-02 | 2022-02-11 | 2022-02-04 | ANSWRCOMP | Ismael Hernandez | Ernesto | [6 empty] | TRUE
21029900-0322 | Telecom - CPK02-R2 RA4 Existing Column Mounted WAP Devices - Confirming | 2022-02-02 | 2022-02-11 | 2022-02-07 | ANSWRCOMP | Ismael Hernandez | Ernesto | [6 empty] | TRUE
21029900-0322R1 | Telecom - CPK02-R2 RA4 Existing Column Mounted WAP Devices New Locations | 2022-02-02 | 2022-02-11 |  | OPEN | Ismael Hernandez | [7 empty] | FALSE
21029900-0323 | LSS - CPK02-R2 RA4 Existing Column Mounted FA and Security Devices - Confirming | 2022-02-02 | 2022-02-11 | 2022-02-07 | ANSWRCOMP | Ismael Hernandez | Ernesto | [6 empty] | FALSE
21029900-0324 | I and C - CPK02-R2 RA4 Existing Column Mounted TET Devices - Confirming | 2022-02-02 | 2022-02-11 | 2022-02-07 | ANSWRCOMP | Ismael Hernandez | Ernesto | [6 empty] | TRUE
21029900-0325 | Mechanical - CPK03-R2 - Streimer RFI 22 - HXRA Return Air Flex Duct | 2022-02-02 | 2022-02-04 | 2022-02-08 | CLOSED | Alen Troyer | Max's Bot |  | RFI-0325 - pyth and flag pending |  |  |  |  | TRUE
21029900-0326 | Electrical - CPK02-R2 RA4 VFD135 Tag - Confirming | 2022-02-02 | 2022-02-11 | 2022-02-04 | ANSWRCOMP | Ismael Hernandez | Ernesto | [6 empty] | FALSE
21029900-0327 | Electrical - CPK02-R2 RA4 Power Cable Tray Height - Confirming | 2022-02-02 | 2022-02-11 | 2022-02-04 | ANSWRCOMP | Ismael Hernandez | Ernesto | [6 empty] | TRUE
21029900-0328 | Process - MSB - CPK03-R2 - Charter RFI 14 - BCD Tray Cut Sheet | 2022-02-03 | 2022-02-07 | 2022-02-07 | CLOSED | Alen Troyer | Max's Bot |  | RFI-0328 - pyth and flag pending |  |  |  |  | TRUE
21029900-0329 | Process - MSB - CPK03-R2 - Charter RFI 15 - KN2 Detail Clarification | 2022-02-03 | 2022-02-07 | 2022-02-04 | CLOSED | Alen Troyer | Max's Bot |  | RFI-0329 - pyth and flag pending |  |  |  |  | TRUE
21029900-0330 | Mechanical - CPK03-R2 - MSB - Streimer - Level 2 HXRA Dampers | 2022-02-03 | 2022-02-07 | 2022-02-09 | CLOSED | Alen Troyer | Max's Bot |  | RFI-0330 - pyth and flag pending |  |  |  |  | TRUE
21029900-0331 | Electrical- CPK03-R2 EC 1200 amp D-Boards Grounding | 2022-02-03 | 2022-02-14 | 2022-02-04 | ANSWRCOMP | Michael Brown | Max's Bot |  | RFI-0331 - pyth and flag pending |  |  |  |  | TRUE
21029900-0332 | Process - MSB - CPK03-R2 - Charter RFI#134 VELAN Glove Valve Clarification | 2022-02-03 | 2022-02-07 | 2022-02-04 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0332 - pyth and flag pending |  |  |  |  | TRUE
21029900-0333 | Mechanical - CPK03-R2 - Streimer RFI 21 - FAB SA Hanger Issue | 2022-02-03 | 2022-02-07 | 2022-02-07 | CLOSED | Alen Troyer | Max's Bot |  | RFI-0333 - pyth and flag pending |  |  |  |  | TRUE
21029900-0334 | Electrical- CPK03-R2 - ECR Tool Cluster | 2022-02-03 | 2022-02-14 | 2022-02-08 | ANSWRCOMP | Michael Brown | Max's Bot |  | RFI-0334 - pyth and flag pending |  |  |  |  | TRUE
21029900-0335 | CSA - MSB - CPK03-R2 Subfab Column Connections | 2022-02-03 | 2022-02-14 | 2022-02-08 | ANSWRCOMP | Ellie Runte | Max's Bot |  | RFI-0335 - pyth and flag pending |  |  |  |  | FALSE
21029900-0336 | Electrical- CPK03-R2 Subfab General Purpose Receptacle Elevation | 2022-02-03 | 2022-02-14 | 2022-02-04 | ANSWRCOMP | Michael Brown | Max's Bot |  | RFI-0336 - pyth and flag pending |  |  |  |  | TRUE
21029900-0337 | CSA - MSB - CPK03-R5 CJP Weld RA-ST-2096 | 2022-02-03 | 2022-02-14 | 2022-02-08 | ANSWRCOMP | Ellie Runte | Connor | 2022-02-16 | RFI-0337 - pyth and flag pending | CPK03-R5 |  |  |  | TRUE
21029900-0338 | Process - MSB - CPK01-R2 - Harder RFI 11 - ZREF Additional MSB Inline Valve | 2022-02-04 | 2022-02-08 | 2022-02-09 | CLOSED | Alen Troyer | [7 empty] | TRUE
21029900-0339 | Process - RA4 - CPK02-R2 - PSV248-1C-16A Type Clarification | 2022-02-04 | 2022-02-08 | 2022-02-07 | ANSWRCOMP | Mitch Kovalev | Ernesto | [6 empty] | TRUE
21029900-0340 | Structural - CPK01-R2 - Harder RFI 12 - AB/57 4" Conduit Clash w New Rack | 2022-02-04 | 2022-02-08 | 2022-02-15 | ANSWRCOMP | Alen Troyer | [7 empty] | TRUE
21029900-0340R1 | Structural - CPK01-R2 - Harder RFI 12 - AB/57 4" Conduit Clash w New Rack | 2022-02-24 | 2022-02-28 | 2022-02-15 | OPEN | Alen Troyer | [7 empty] | TRUE
21029900-0341 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#086 Socket Weld of ADB Piping | 2022-02-04 | 2022-02-08 | 2022-02-07 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0341 - pyth and flag pending |  |  |  |  | TRUE
21029900-0342 | Process - MSB - CPK03-R2 - Charter RFI#146 HPN2 Design Deviation | 2022-02-07 | 2022-02-09 | 2022-02-09 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0342 - pyth and flag pending |  |  |  |  | TRUE
21029900-0343 | Process - MSB - CPK03-R2 - Charter RFI#147 Metering Pump Door Material | 2022-02-07 | 2022-02-09 | 2022-02-10 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0343 - pyth and flag pending |  |  |  |  | TRUE
21029900-0344 | Process - MSB - CPK03-R2 - Charter RFI#59.1 CHCO2DI Future Lateral | 2022-02-07 | 2022-02-09 | 2022-02-15 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0344 - pyth and flag pending |  |  |  |  | TRUE
21029900-0345 | Process - MSB - CPK03-R2 - Charter RFI#149 Adjustable Foot Support | 2022-02-07 | 2022-02-09 | 2022-02-09 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0345 - pyth and flag pending |  |  |  |  | TRUE
21029900-0346 | CSA - MSB - CPK03-R5 - Option of RA-ST-2024 | 2022-02-07 | 2022-02-09 | 2022-02-09 | ANSWRCOMP | Ellie Runte | Connor | 2022-02-16 | RFI-0346 - pyth and flag pending | CPK03-R5 |  |  |  | TRUE
21029900-0347 | Process - MSB - CPK03-R2 - Charter RFI#150 Space Heater Requirement | 2022-02-07 | 2022-02-09 | 2022-02-08 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0347 - pyth and flag pending |  |  |  |  | TRUE
21029900-0348 | CSA - MSB - CPK03-R2 LVL2 Connections to Embedded Strut-f | 2022-02-07 | 2022-02-16 | 2022-02-09 | ANSWRCOMP | Ellie Runte | Max's Bot |  | RFI-0348 - pyth and flag pending |  |  |  |  | TRUE
21029900-0349 | Process - MSB - CPK03-R2 - Charter RFI#154 5% H2-He Line Reduced | 2022-02-07 | 2022-02-09 | 2022-02-09 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0349 - pyth and flag pending |  |  |  |  | TRUE
21029900-0350 | Process - MSB - CPK03-R2 - Charter RFI#153 UN2 and SWS | 2022-02-07 | 2022-02-09 | 2022-02-10 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0350 - pyth and flag pending |  |  |  |  | TRUE
21029900-0351R1 | CSA - MSB - CPK03-R3 - Stair 1 Design Changes | 2022-02-07 | 2022-02-09 | 2022-02-16 | OPEN | Ellie Runte | Connor | 2022-02-16 | RFI-0351R1 - pyth and flag pending | CPK03-R3 | Not in cold storage |  |  | FALSE
21029900-0352R1 | CSA - MSB - CPK03-R3 Door & Sill Clarifications | 2022-02-07 | 2022-02-09 | 2022-02-18 | OPEN | Ellie Runte | Connor | 2022-02-16 | RFI-0352R1 - pyth and flag pending | CPK03-R3 | Not in cold storage |  |  | TRUE
21029900-0353 | Structural - RA4 - CPK02-R2 - Framing Details at GL A-9 | 2022-02-07 | 2022-02-15 | 2022-02-10 | ANSWRCOMP | Mitchell Casio | Ernesto | [6 empty] | TRUE
21029900-0354 | CSA - MSB - CPK03-R3 RA-ST-2200 Substitution | 2022-02-07 | 2022-02-09 | 2022-02-10 | ANSWRCOMP | Ellie Runte | Connor | 2022-02-16 | RFI-0354 - pyth and flag pending | CPK03-R3 |  |  |  | TRUE
21029900-0355 | CSA - MSB - CPK03-R3 Strut Fitting Substitution | 2022-02-07 | 2022-02-09 | 2022-02-10 | ANSWRCOMP | Ellie Runte | Connor | 2022-02-16 | RFI-0355 - pyth and flag pending | CPK03-R3 |  |  |  | TRUE
21029900-0356 | Mech Process - RA4 - CPK02-R2 - TCHW Conflict with RMF at E.5/10 and B/13 | 2022-02-22 | 2022-02-24 |  | OPEN | Mitch Kovalev | Ernesto | [6 empty] | FALSE
21029900-0357 | Electrical- CPK03-R2 ECR Model and Spec Discrepancy | 2022-02-07 | 2022-02-16 | 2022-02-09 | ANSWRCOMP | Michael Brown | Max's Bot |  | RFI-0357 - pyth and flag pending |  |  |  |  | TRUE
21029900-0358 | Process - MSB - CPK03-R2 - Charter RFI#073.1 Dead Legs | 2022-02-07 | 2022-02-09 | 2022-02-10 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0358 - pyth and flag pending |  |  |  |  | TRUE
21029900-0359 | Architectural - RA4 - CPK02-R4 - Mineral Wool Insulation | 2022-02-07 | 2022-02-15 | 2022-02-15 | ANSWRCOMP | Mitchell Casio | Ernesto | [6 empty] | TRUE
21029900-0360 | Mech Process - RA4 - CPK02-R2 - TCHW Conflict with RMF at E.5/10, J.2/7, and E.5/9 | 2022-02-22 | 2022-02-24 |  | ANSWRCOMP | Mitch Kovalev | Ernesto | [6 empty] | TRUE
21029900-0361 | Process - RA4 - CPK02-R2 - BEA Routing Clash with Duct | 2022-02-07 | 2022-02-09 | 2022-02-09 | ANSWRCOMP | Mitch Kovalev | Ernesto | [6 empty] | TRUE
21029900-0362 | Process - RA4 - CPK02-R2 - SSH-5140 Clash with PCW | 2022-02-07 | 2022-02-09 | 2022-02-14 | ANSWRCOMP | Mitch Kovalev | Ernesto | [6 empty] | TRUE
21029900-0363 | CSA - CPK03-R2 Clean Room Stair Landings | 2022-02-07 | 2022-02-09 | 2022-02-17 | ANSWRCOMP | Callie Johns | Max's Bot |  | RFI-0363 - pyth and flag pending |  |  |  |  | TRUE
21029900-0364 | Process - RA4 - CPK02-R4 - 2 inch OFA Lateral FPOC Qty | 2022-02-07 | 2022-02-09 | 2022-02-09 | ANSWRCOMP | Mitch Kovalev | Ernesto | [6 empty] | TRUE
21029900-0365 | CSA - CPK03-R2 MSB LVL2 HSS Cup Conflicts - R1 | 2022-02-07 | 2022-02-23 | 2022-02-10 | ANSWRCOMP | Callie Johns | Max's Bot |  | RFI-0365 - pyth and flag pending |  |  |  |  | TRUE
21029900-0365R1 | CSA - CPK03-R2 MSB LVL2 HSS Cup Conflicts - R1 | 2022-02-25 | 2022-02-23 | 2022-02-10 | ANSWRCOMP | Callie Johns | [7 empty] | TRUE
21029900-0366 | Process - RA4 - CPK02-R4 - 2 inch PA IDC Discrepancy | 2022-02-07 | 2022-02-09 | 2022-02-09 | ANSWRCOMP | Mitch Kovalev | Ernesto | [6 empty] | TRUE
21029900-0367 | CSA - CPK03-R2 MSB LVL2 Connections to Embedded Strut | 2022-02-07 | 2022-02-09 |  | VOID | Callie Johns | Max's Bot |  | RFI-0367 - pyth and flag pending |  |  |  |  | FALSE
21029900-0368 | Process - RA4 - CPK02-R2 - TCHW Discrepancies in DM at RA4-RAH102-09 thru RA4-RAH102-13 | 2022-02-07 | 2022-02-09 | 2022-02-14 | ANSWRCOMP | Mitch Kovalev | Ernesto | [6 empty] | TRUE
21029900-0369 | Process - RA4 - CPK02-R4 - GL-66H Purge Ports | 2022-02-07 | 2022-02-09 | 2022-02-09 | ANSWRCOMP | Mitch Kovalev | Ernesto | [6 empty] | TRUE
21029900-0370 | Process - MSB - CPK03-R2 - D1X UPWR Analytical Cabinet MEL Change | 2022-02-07 | 2022-02-14 | 2022-02-09 | OPEN | Rees Bixler | Max's Bot |  | RFI-0370 - pyth and flag pending |  |  |  |  | FALSE
21029900-0371 | Process - RA4 - CPK02-R4 - AWN Tanks and Pump Vendor | 2022-02-07 | 2022-02-09 | 2022-02-09 | ANSWRCOMP | Mitch Kovalev | Ernesto | [6 empty] | TRUE
21029900-0372 | Process - RA4 - CPK02-R2 - TCHWS Clash with Cable Tray Unistrut | 2022-02-07 | 2022-02-09 | 2022-02-09 | ANSWRCOMP | Mitch Kovalev | Ernesto | [6 empty] | TRUE
21029900-0373 | Process - RA4 - LLP02-R1 - Suez CHCO2DI Skid Redundancy Upgrade Kit | 2022-02-07 | 2022-02-09 | 2022-02-10 | ANSWRCOMP | Mitch Kovalev | Taylor Patterson | 2022-02-25 | Question rejected, nothing to post | N/A |  |  |  | TRUE
21029900-0374 | Wet Mech - MSB - CPK03-R2 -BMWCRFI#087 - CHWSR Reducers vs. Eccentric | 2022-02-08 | 2022-02-10 | 2022-02-10 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0374 - pyth and flag pending |  |  |  |  | TRUE
21029900-0375 | Wet Mech - MSB - CPK03-R2 - BMWCRFI#096 Safety Shower Missing Drawing | 2022-02-08 | 2022-02-10 | 2022-02-22 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0375 - pyth and flag pending |  |  |  |  | TRUE
21029900-0376 | Electrical- CPK03-R2 General Purpose Receptacles Conduit | 2022-02-08 | 2022-02-17 | 2022-02-14 | ANSWRCOMP | Michael Brown | Max's Bot |  | RFI-0376 - pyth and flag pending |  |  |  |  | TRUE
21029900-0377 | Electrical- CPK03-R2- ECR NPS for MSB1-RIO650-104-02 | 2022-02-08 | 2022-02-17 | 2022-02-09 | ANSWRCOMP | Michael Brown | Max's Bot |  | RFI-0377 - pyth and flag pending |  |  |  |  | TRUE
21029900-0378 | Electrical- CPK03-R2 ECR VFD147-2-00 and VFD147-4-00 Clarifications | 2022-02-08 | 2022-02-17 | 2022-02-10 | ANSWRCOMP | Michael Brown | Max's Bot |  | RFI-0378 - pyth and flag pending |  |  |  |  | TRUE
21029900-0379 | Electrical- CPK03-R2 ECR Confirm Circuits | 2022-02-08 | 2022-02-17 | 2022-02-14 | ANSWRCOMP | Michael Brown | Max's Bot |  | RFI-0379 - pyth and flag pending |  |  |  |  | TRUE
21029900-0380R1 | MSB - CPK03-R3 - Door MS1B07A Wall Type | 2022-02-28 | 2022-03-02 |  | OPEN | Ellie Runte | Connor | 2022-02-16 | RFI-0380R1 - pyth and flag pending | CPK03-R3 | Not in cold storage |  |  | TRUE
21029900-0381 | Process - MSB - CPK03-R2 - Charter RFI#050.1 UPW Lateral Follow Up | 2022-02-08 | 2022-02-10 | 2022-02-10 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0381 - pyth and flag pending |  |  |  |  | TRUE
21029900-0382 | Process - MSB - CPK03-R2 - Charter RFI#155 AWN Various Issues | 2022-02-08 | 2022-02-10 | 2022-02-14 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0382 - pyth and flag pending |  |  |  |  | TRUE
21029900-0383 | Process - MSB - CPK03-R2 - Charter RFI#156 CO2 Laterals Not Matching Drawing | 2022-02-08 | 2022-02-10 | 2022-02-11 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0383 - pyth and flag pending |  |  |  |  | TRUE
21029900-0384 | Electrical MSB LLE01 - OIT Equipment Tag Change Confirmation | 2022-02-08 | 2022-02-17 | 2022-02-09 | ANSWRCOMP | Taylor Bothmann | [7 empty] | TRUE
21029900-0385R1 | CSA - MSB - CPK03-R8 - Door Schedule Clarifications | 2022-02-28 | 2022-03-02 | 2022-02-17 | OPEN | Ellie Runte | Connor | 2022-02-16 | RFI-0385R1 - pyth and flag pending | CPK03-R8 | Not in cold storage |  |  | TRUE
21029900-0386 | Wet Mech - MSB - CPK03-R2 - BMWC RFI097 CHWSR In Egress Zone | 2022-02-09 | 2022-02-11 | 2022-02-10 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0386 - pyth and flag pending |  |  |  |  | TRUE
21029900-0387 | CSA - MSB - CPK03-R3 - M16 & M10 Rod Drops @ Strut Embed Alternate #2 | 2022-02-09 | 2022-02-11 | 2022-02-14 | ANSWRCOMP | Ellie Runte | Connor | 2022-02-16 | RFI-0387 - pyth and flag pending | CPK03-R3 |  |  |  | TRUE
21029900-0388 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#098 CHWSR Clash with Door | 2022-02-09 | 2022-02-11 | 2022-02-10 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0388 - pyth and flag pending |  |  |  |  | TRUE
21029900-0389 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#099 Line Numbering Discrepancy | 2022-02-09 | 2022-02-11 | 2022-02-16 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0389 - pyth and flag pending |  |  |  |  | TRUE
21029900-0390 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#101 CHW Conflict with Cable Tray | 2022-02-09 | 2022-02-11 | 2022-02-10 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0390 - pyth and flag pending |  |  |  |  | TRUE
21029900-0391 | Wet Mech - MSB - CPK03-R2 - BMWC RFI088 DPIT Spec Clarification | 2022-02-09 | 2022-02-11 | 2022-02-11 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0391 - pyth and flag pending |  |  |  |  | TRUE
21029900-0392 | Wet Mech - MSB - CPK03-R2 - BMWCRFI#090 Air Exhaust Port Clarification | 2022-02-09 | 2022-02-11 | 2022-02-10 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0392 - pyth and flag pending |  |  |  |  | TRUE
21029900-0393 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#091 Lateral Sample Detail Conflicts KEE Spec | 2022-02-09 | 2022-02-11 | 2022-02-22 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0393 - pyth and flag pending |  |  |  |  | TRUE
21029900-0394 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#092 General Process Exhaust Port Clarification | 2022-02-09 | 2022-02-11 | 2022-02-11 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0394 - pyth and flag pending |  |  |  |  | TRUE
21029900-0395 | Wet Mech - MSB - CPK03-R2 - BMWCRFI#093 KEE Fitting Confirmation | 2022-02-09 | 2022-02-11 | 2022-02-10 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0395 - pyth and flag pending |  |  |  |  | TRUE
21029900-0396 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#095 DPIT Valve Redundancy Clarification | 2022-02-09 | 2022-02-11 | 2022-02-16 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0396 - pyth and flag pending |  |  |  |  | TRUE
21029900-0397 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#089 End of Lateral DPIT | 2022-02-09 | 2022-02-11 | 2022-02-15 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0397 - pyth and flag pending |  |  |  |  | TRUE
21029900-0398 | Process - MSB - CPK03-R2 - Charter RFI#159 OFA Lateral Reduction Missing in DM | 2022-02-09 | 2022-02-11 | 2022-02-11 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0398 - pyth and flag pending |  |  |  |  | TRUE
21029900-0399 | Mechanical - CPK03-R2 - Streimer RFI 23 - EXGB Fan vs GRD CFM | 2022-02-09 | 2022-02-11 | 2022-02-10 | CLOSED | Alen Troyer | Max's Bot |  | RFI-0399 - pyth and flag pending |  |  |  |  | TRUE
21029900-0400 | Mechanical - CPK03-R2/R3 - Streimer RFI 24 - FAB Level Coil Discrepancies | 2022-02-09 | 2022-02-11 | 2022-02-14 | ANSWRCOMP | Alen Troyer | Max's Bot |  | RFI-0400 - pyth and flag pending |  |  |  |  | TRUE
21029900-0401 | Telecom- CPK03-R2-MSB1-CCH-CP24-A9 288 Strand Request | 2022-02-09 | 2022-02-18 | 2022-02-15 | ANSWRCOMP | Michael Brown | Max's Bot |  | RFI-0401 - pyth and flag pending |  |  |  |  | TRUE
21029900-0402 | Process - MSB - CPK03-R2 - Charter RFI#160 SHCW Branches Model and Keynotes | 2022-02-09 | 2022-02-11 | 2022-02-15 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0402 - pyth and flag pending |  |  |  |  | TRUE
21029900-0402R1 | Process - MSB - CPK03-R2 - Charter RFI#160 SHCW Branches Model and Keynotes | 2022-02-09 | 2022-02-11 | 2022-02-15 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0402R1 |  |  |  |  | TRUE
21029900-0403 | Process - MSB - CPK03-R2 - Charter RFI#161 CHCO2DI QSP Valve and Keynote | 2022-02-09 | 2022-02-11 | 2022-02-15 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0403 - pyth and flag pending |  |  |  |  | TRUE
21029900-0404 | Process - MSB - CPK03-R2 - Charter RFI#162 HPN2 Deviations from DM | 2022-02-09 | 2022-02-11 | 2022-02-11 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0404 - pyth and flag pending |  |  |  |  | TRUE
21029900-0405 | Process - MSB - CPK03-R9 - Charter RFI#164 BEA Content Above Ceiling | 2022-02-09 | 2022-02-11 | 2022-02-11 | ANSWRCOMP | Mason Ray | Connor | 2022-02-28 | RFI-0405 - pyth and flag pending | CPK03-R2 |  |  |  | TRUE
21029900-0406 | CSA - CPK02-R2 - Structural Infill Clarification | 2022-02-09 | 2022-02-17 | 2022-02-17 | ANSWRCOMP | Callie Johns | Ernesto | [6 empty] | TRUE
21029900-0407 | Electrical- CPK03-R2 Subfab Light Mounting on North Side of Steel | 2022-02-09 | 2022-02-18 |  | ANSWRCOMP | Michael Brown | Max's Bot |  | RFI-0407 - pyth and flag pending |  |  |  |  | TRUE
21029900-0408 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#111 Missing IA Source for TCVs | 2022-02-10 | 2022-02-14 | 2022-02-14 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0408 - pyth and flag pending |  |  |  |  | TRUE
21029900-0409 | Mechanical - MSB1 - CPK03-R3 - EXSC Ductwork issue at AC line | 2022-02-10 | 2022-02-14 | 2022-02-15 | ANSWRCOMP | Patrick McCarthy | Connor | 2022-02-16 | RFI-0409 - pyth and flag pending | CPK03-R3 |  |  |  | TRUE
21029900-0410 | Process - MSB - CPK03-R2 - Charter - BF-34 Substitution Request | 2022-02-10 | 2022-02-14 | 2022-02-14 | CLOSED | Alen Troyer | Max's Bot |  | RFI-0410 - pyth and flag pending |  |  |  |  | TRUE
21029900-0410R1 | Process - MSB - CPK03-R2 - Charter - BF-34 Substitution Request | 2022-02-22 | 2022-02-24 |  | ANSWRCOMP | Alen Troyer | Connor | 2022-03-01 | RFI-410R1 - pyth and flag pending | CPK03-R2, CPK03-R3 |  |  |  | TRUE
21029900-0411 | Process - MSB - CPK03-R2 - Charter - GL-18 Substitution Request | 2022-02-10 | 2022-02-14 | 2022-02-14 | ANSWRCOMP | Alen Troyer | Max's Bot |  | RFI-0411 - pyth and flag pending |  |  |  |  | TRUE
21029900-0412 | Mechanical - CPK03-R3 - Dry Cooling Coil Data Sheet Corrections | 2022-02-10 | 2022-02-14 | 2022-02-15 | ANSWRCOMP | Alen Troyer | Connor | 2022-02-16 | RFI-0412 - pyth and flag pending | CPK03-R3 |  |  |  | TRUE
21029900-0413 | Mechanical - CPK03-R3 - In Row Cooling Unit Data Sheet Corrections | 2022-02-10 | 2022-02-14 | 2022-02-14 | ANSWRCOMP | Alen Troyer | Connor | 2022-02-16 | RFI-0413 - pyth and flag pending | CPK03-R3 |  |  |  | FALSE
21029900-0414 | Mechanical - CPK03-R2 - Fan Coil Unit Specifications | 2022-02-10 | 2022-02-14 | 2022-02-14 | ANSWRCOMP | Alen Troyer | Max's Bot |  | RFI-0414 - pyth and flag pending |  |  |  |  | TRUE
21029900-0415 | Mechanical - MSB1 - CPK03-R2 - Shift FFU on Level 2 Fab C4 at grid L-11 | 2022-02-14 | 2022-02-16 | 2022-02-17 | ANSWRCOMP | Alen Troyer | Max's Bot |  | RFI-0415 - pyth and flag pending |  |  |  |  | TRUE
21029900-0416 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#019 CHWSR Loop EOL Valve | 2022-02-11 | 2022-02-15 | 2022-02-14 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0416 - pyth and flag pending |  |  |  |  | TRUE
21029900-0417 | Structural - PUB1 - CPK02-R2 - Concrete Pad Details | 2022-02-11 | 2022-02-15 | 2022-02-22 | ANSWRCOMP | Mitchell Casio | Ernesto | [6 empty] | TRUE
21029900-0418 | CSA - MSB - CPK03-R2 - Southeast MSB Pipe Support | 2022-02-11 | 2022-02-22 | 2022-02-15 | ANSWRCOMP | Ellie Runte | Max's Bot |  | RFI-0418 - pyth and flag pending |  |  |  |  | TRUE
21029900-0419 | Structural - RA4 - CPK02-R2 - TCHW Inertia Pad Clarifications | 2022-02-11 | 2022-02-15 | 2022-02-14 | ANSWRCOMP | Mitchell Casio | Ernesto | [6 empty] | TRUE
21029900-0420 | Structural - RA4 - CPK02-R2 - Spliced Rod Drops | 2022-02-11 | 2022-02-15 | 2022-02-15 | ANSWRCOMP | Mitchell Casio | Ernesto | [6 empty] | TRUE
21029900-0421 | Mechanical - CPK03-R2 - Streimer RFI 25 - L1 Missing Fire Damper in 12" SA | 2022-02-14 | 2022-02-16 | 2022-02-17 | CLOSED | Alen Troyer | Max's Bot |  | RFI-0421 - pyth and flag pending |  |  |  |  | TRUE
21029900-0422 | CSA-CPK02-R2- Plenum Wall and Ceiling Details | 2022-02-14 | 2022-02-16 |  | REJECTED | Carlos Acosta | Ernesto | [6 empty] | FALSE
21029900-0422R1 | CSA-CPK02-R2- Plenum Wall and Ceiling Details | 2022-02-14 | 2022-02-16 |  | OPEN | Carlos Acosta | Ernesto | [6 empty] | FALSE
21029900-0423 | Process - MSB - CPK03-R2 - Charter RFI#165 CPCW Valve Not on P and ID | 2022-02-14 | 2022-02-16 | 2022-02-15 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0423 - pyth and flag pending |  |  |  |  | TRUE
21029900-0424 | Process - MSB - CPK03-R2 - Charter RFI#166 AWN Air Gap Height | 2022-02-14 | 2022-02-16 | 2022-02-17 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0424 - pyth and flag pending |  |  |  |  | TRUE
21029900-0425 | Process - MSB - CPK03-R2 - Charter RFI#167 H2N2 GL-78 Size Not Matching | 2022-02-14 | 2022-02-16 | 2022-02-17 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0425 - pyth and flag pending |  |  |  |  | TRUE
21029900-0426 | Process - MSB - CPK03-R2 - Charter RFI#168 Spare Lateral in Bay 52N1S-S | 2022-02-14 | 2022-02-16 | 2022-02-17 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0426 - pyth and flag pending |  |  |  |  | TRUE
21029900-0427 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#114 BA-4s on ADB Spec | 2022-02-14 | 2022-02-16 | 2022-02-15 | ANSWRCOMP | Mason Ray | Max's Bot |  | RFI-0427 - pyth and flag pending |  |  |  |  | TRUE
21029900-0428 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#115 Safety Shower Spec Revision | 2022-02-14 | 2022-02-16 | 2022-02-21 | ANSWRCOMP | Mason Ray | Connor | 2022-02-28 | RFI-0428 - pyth and flag pending | CPK03-R2,CPK04 |  |  |  | TRUE
21029900-0429 | Wet Mech - MSB - CPK03-R9 - Safety Shower Relocation with Scope Deletion | 2022-02-14 | 2022-02-16 | 2022-02-16 | ANSWRCOMP | Mason Ray | Connor | 2022-02-21 | RFI-0429 - pyth and flag pending | CPK03-R9 |  |  |  | TRUE
21029900-0430 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#121 Missing Plumbing Detail | 2022-02-14 | 2022-02-16 | 2022-02-17 | ANSWRCOMP | Mason Ray | Connor | 2022-02-24 | RFI-0430 - pyth and flag pending | CPK03-R3 |  |  |  | TRUE
21029900-0431 | Electrical - RA4 - CPK02-R4 - MEL PID inst tags do not match for 135 VFD | 2022-02-14 | 2022-02-16 | 2022-02-17 | ANSWRCOMP | Ismael Hernandez | Ernesto | [6 empty] | TRUE
21029900-0432 | All Disciplines - MSB/RA4 - POR Submittals Clarifications | 2022-02-14 | 2022-02-21 |  | APPROVED | Mitchell Casio | [7 empty] | FALSE
21029900-0433 | CSA - RA4 - CPK02-R2 - Beam Conflicts with E wall | 2022-02-14 | 2022-02-16 | 2022-02-18 | ANSWRCOMP | Mitchell Casio | Ernesto |  | Need to push to CMiC folder, or do we |  |  |  |  | TRUE
21029900-0434 | Multi - MSB - CPK03-R2 - LIT133 tags | 2022-02-14 | 2022-02-16 | 2022-02-17 | ANSWRCOMP | Alen Troyer | Connor | 2022-02-24 | RFI-0434 - pyth and flag pending | CPK03-R2 |  |  |  | TRUE
21029900-0435 | Structural - RA4 - CPK02-R2 Beam Conflicts with (E) Wall | 2022-02-14 | 2022-02-23 | 2022-02-15 | VOID | Steve Mazzoni | Ernesto | [6 empty] | TRUE
21029900-0436 | Mechanical - CPK03-R2 - Streimer RFI 26 - EXSC Drain Duct Slope vs Steel Clash | 2022-02-15 | 2022-02-17 | 2022-02-21 | CLOSED | Alen Troyer | Connor | 2022-02-24 | RFI-0436 - pyth and flag pending | SLIP SHEETED |  |  |  | TRUE
21029900-0437 | Mechanical - CPK03-R2 - Streimer RFI 20 - HXRA Rectangular Clash | 2022-02-15 | 2022-02-17 | 2022-02-16 | CLOSED | Alen Troyer | Connor | 2022-02-24 | RFI-0437 - pyth and flag pending | CPK03-R7 |  |  |  | TRUE
21029900-0438 | Mechanical - CPK03-R2 - Streimer RFI 19 - 1SA EXVO Route Deviation and Zone Conflict | 2022-02-15 | 2022-02-17 | 2022-02-22 | CLOSED | Alen Troyer | Connor | 2022-02-24 | RFI-0438 - pyth and flag pending | CPK03-R2,CPK03-R7 |  |  |  | TRUE
21029900-0439 | DRYMECH-CSA-CPK02-South Exterior MA Penetration Vs Steel | 2022-02-14 | 2022-02-16 | 2022-02-18 | REJECTED | Carlos Acosta | Ernesto | [6 empty] | FALSE
21029900-0439R1 | DRYMECH-CSA-CPK02-South Exterior MA Penetration Vs Steel | 2022-02-14 | 2022-02-16 |  | OPEN | Carlos Acosta | [7 empty] | TRUE
21029900-0440 | Process - MSB - CPK03-R2 - Charter RFI#169 JEB Spec CPCW Lines | 2022-02-15 | 2022-02-17 | 2022-02-16 | ANSWRCOMP | Mason Ray | Connor |  | RFI-0440 - pyth and flag pending | 40_05_16_36, JEA and JEB share an specification entry with no differentiation between them, making them interchangeable |  |  |  | TRUE
21029900-0441 | Process - MSB - CPK03-R2 - Charter RFI#170 PV Piping Spec Discrepancy | 2022-02-15 | 2022-02-17 | 2022-02-17 | ANSWRCOMP | Mason Ray | Connor | 2022-03-01 | RFI-0441 - pyth and flag pending | CPK03-R2, CPK03-R3 |  |  |  | TRUE
21029900-0442 | Process - MSB - CPK03-R2 - Charter RFI#172 UPWS Offset Clashing Steel | 2022-02-15 | 2022-02-17 | 2022-02-16 | ANSWRCOMP | Mason Ray | Connor | 2022-02-23 | RFI-0442 - pyth and flag pending | CPK03-R2, CPK03-R3 |  |  |  | TRUE
21029900-0443 | Telecom- CPK02-R4-RA4-SCR 422 Termination | 2022-02-15 | 2022-02-17 | 2022-02-17 | ANSWRCOMP | Michael Brown | Ernesto | [6 empty] | TRUE
21029900-0444 | Structural - MSB - CPK03-R10 - Strut Rack Detail Changes | 2022-02-15 | 2022-02-17 | 2022-02-18 | ANSWRCOMP | Steve Mazzoni | Connor | 2022-03-07 | RFI-0444 - pyth and flag pending | Slipsheeted |  |  |  | TRUE
21029900-0445 | Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Protection Piping BT/28, BT/29, BT/30, BT/50 | 2022-02-15 | 2022-02-17 | 2022-02-18 | ANSWRCOMP | Mason Ray | Connor |  | RFI-0445 - pyth and flag pending | BimTrack issues in this RFI can be resolved with piping adjustments |  |  |  | TRUE
21029900-0446 | Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Protection Piping BT/25, BT/26, BT/27 | 2022-02-15 | 2022-02-17 | 2022-02-18 | ANSWRCOMP | Mason Ray | Connor |  | RFI-0446 - pyth and flag pending | BimTrack issues in this RFI can be resolved with piping adjustments |  |  |  | TRUE
21029900-0447 | Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Protection Piping BT/22, BT/23, BT/24 | 2022-02-15 | 2022-02-17 | 2022-02-22 | ANSWRCOMP | Mason Ray | Connor | 2022-03-07 | RFI-0447 - pyth and flag pending | In model, no view in drawings |  |  |  | TRUE
21029900-0448 | Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Protection Piping BT/7, BT/12, BT/18 | 2022-02-15 | 2022-02-17 | 2022-02-26 | ANSWRCOMP | Mason Ray | Connor | 2022-03-07 | RFI-0448 - pyth and flag pending | In model, no view in drawings |  |  |  | TRUE
21029900-0449 | Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Protection Piping BT/19, BT/20, BT/21 | 2022-02-15 | 2022-02-17 | 2022-02-18 | ANSWRCOMP | Mason Ray | Connor |  | CMIC Error problem, need in answered RFI folder | In model, no view in drawings |  |  |  | TRUE
21029900-0450 | Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Protection Piping BT31, BT32, BT33 | 2022-02-15 | 2022-02-17 | 2022-02-18 | ANSWRCOMP | Mason Ray | Connor |  | CMIC Error problem, need in answered RFI folder | In model, no view in drawings |  |  |  | TRUE
21029900-0451 | Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Protection Piping BT/34, BT/35, BT/36 | 2022-02-15 | 2022-02-17 | 2022-02-18 | ANSWRCOMP | Mason Ray | Connor | 2022-03-07 | RFI-0451 - pyth and flag pending | In model, no view in drawings |  |  |  | TRUE
21029900-0452 | Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Protection Piping BT/39, BT/40, BT/41 | 2022-02-15 | 2022-02-17 | 2022-02-18 | ANSWRCOMP | Mason Ray | Connor |  | CMIC Error problem, need in answered RFI folder | In model, no view in drawings |  |  |  | TRUE
21029900-0453 | Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Protection Piping BT/42, BT/43, BT/45 | 2022-02-15 | 2022-02-17 | 2022-02-18 | ANSWRCOMP | Mason Ray | Connor |  | CMIC Error problem, need in answered RFI folder | In model, no view in drawings |  |  |  | TRUE
21029900-0454 | Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Protection Piping BT/47, BT/55, BT/56 | 2022-02-15 | 2022-02-17 | 2022-02-24 | ANSWRCOMP | Mason Ray | Connor | 2022-03-07 | RFI-0454 - pyth and flag pending | In model, no view in drawings |  |  |  | TRUE
21029900-0455 | Wet Mech - MSB - CPK03-R2 - CHW Conflict with Fire Protection at Column M/51 | 2022-02-15 | 2022-02-17 | 2022-02-18 | ANSWRCOMP | Mason Ray | Connor |  | CMIC Error problem, need in answered RFI folder | In model, no view in drawings |  |  |  | TRUE
21029900-0456 | Wet Mech - MSB - CPK03-R2 - TCHW Conflict with Fire Protection Piping at P/56, R/54, R/56 | 2022-02-15 | 2022-02-17 |  | ANSWRCOMP | Mason Ray | Connor |  | In model | Connor up from here |  |  |  | TRUE
21029900-0457 | I and C-CPK03-R2- MSB1-Magnetrol Switch Probe Length | 2022-02-15 | 2022-02-17 | 2022-02-17 | ANSWRCOMP | Michael Brown | Connor | 2022-02-22 | RFI-0457 - pyth and flag pending | CPK03-R2, CPK03-R9 |  |  |  | TRUE
21029900-0458 | All Disciplines - RA4 - Golden Grid VS DM Alignment | 2022-02-23 | 2022-02-18 |  | OPEN | Mitchell Casio | [7 empty] | FALSE
21029900-0459 | I and C-CPK03-R2- MSB1- Missing MSB1-TCV102-31-22A | 2022-02-16 | 2022-02-18 | 2022-02-17 | CLOSED | Michael Brown | Connor | 2022-02-22 | RFI-0459 - pyth and flag pending | CPK03-R2, CPK03-R3 |  |  |  | TRUE
21029900-0460 | CSA - RA4 - CPK02 - Compression Post Clarification | 2022-02-16 | 2022-02-18 | 2022-02-18 | ANSWRCOMP | Mitchell Casio | Ernesto | [6 empty] | TRUE
21029900-0461 | Structural - CPK02 - RA4 - RR Washer Clarification | 2022-02-16 | 2022-02-18 | 2022-02-18 | ANSWRCOMP | Mitchell Casio | [7 empty] | TRUE
21029900-0462 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#127 POC Count Discrepancy | 2022-02-16 | 2022-02-18 | 2022-02-18 | ANSWRCOMP | Mason Ray | Connor | 2022-02-28 | RFI-0462 - pyth and flag pending | CPK03-R2, CPK03-R3, CPK04 |  |  |  | TRUE
21029900-0463 | Process - MSB - CPK03-R2 - Charter RFI#174 CPCW Supports | 2022-02-16 | 2022-02-18 | 2022-02-22 | ANSWRCOMP | Mason Ray | Connor | 2022-03-01 | RFI-0463 - pyth and flag pending | CPK04-R2, CPK03-R10 |  |  |  | TRUE
21029900-0464 | Process - RA4 - CPK02-R4 - RODI RTD Flush Style Eccentric Reducers | 2022-02-16 | 2022-02-18 | 2022-02-22 | ANSWRCOMP | Mitch Kovalev | [7 empty] | TRUE
21029900-0465 | Structural - RA4 - CPK02-R2 - Framing Details at GL K-13.5 | 2022-02-16 | 2022-02-21 | 2022-02-22 | ANSWRCOMP | Mitchell Casio | [7 empty] | TRUE
21029900-0466 | I&C - CPK02-R2 - RA4 Instrumentation Tag Discrepancies | 2022-02-16 | 2022-02-18 | 2022-02-22 | OPEN | Ismael Hernandez | [7 empty] | TRUE
21029900-0467 | MECH-CPK02-RA4-CLEANROOM MAKEUP AIR-AIR HANDLER PRESSURIZATION SYSTEM P&ID Notes Updates | 2022-02-17 | 2022-02-21 | 2022-02-18 | CLOSED | Carlos Acosta | [7 empty] | TRUE
21029900-0468 | Mechanical - CPK03 - MSB - Streimer RFI 27 - Level 5 Roof Mark Up Air Duct UPN | 2022-02-17 | 2022-02-21 | 2022-02-18 | CLOSED | Alen Troyer | Connor | 2022-03-01 | RFI-0468 - pyth and flag pending | CPK03-R2 |  |  |  | FALSE
21029900-0469 | Process - RA4 - CPK02-R4 - CHCO2DIS-R Size Discrepancy (Lines 249009-00, 249008-00) | 2022-02-17 | 2022-02-21 |  | ANSWRCOMP | Mitch Kovalev | [7 empty] | TRUE
21029900-0470 | Dry Mech-CPK03-R2-MSB - Exhaust Fan Spare Bearings | 2022-02-17 | 2022-02-21 | 2022-02-17 | ANSWRCOMP | Mason Ray | Connor | 2022-03-01 | Not on Drawings | order 3 sets of spare bearings for EXSC fans, and one set of spare bearings for the EXGF fan from |  |  |  | TRUE
21029900-0472 | Process - RA4 - CPK02-R2 - RCRA Matrix for MSW-GSW Relabel Scope | 2022-02-17 | 2022-02-21 |  | ANSWRCOMP | Mitch Kovalev |  |  | Aerovent/DPWilson |  |  |  |  | TRUE
21029900-0473 | Mechanical - CPK03 - MSB - Southland RFI 5 - L2 Duct and Immovable Waste Drain Clash | 2022-02-17 | 2022-02-21 | 2022-02-22 | ANSWRCOMP | Alen Troyer | Connor | 2022-03-01 | RFI-0473 - pyth and flag pending | CPK03-R3, CPK03-R9 |  |  |  | TRUE
21029900-0474 | I&C- MSB1/RA4-CPK03-R2- Profibus Couplers | 2022-02-17 | 2022-02-21 | 2022-02-18 | ANSWRCOMP | Michael Brown | Connor | 2022-03-01 | RFI-0474 - pyth and flag pending | CPK03-R2, LLE01, LLP04 |  |  |  | TRUE
21029900-0475 | Process - RA4 - CPK02-R4 - TCHW to RA4-CC102-05_06_07_08-20 Design Model Issues_BT151 | 2022-02-17 | 2022-02-21 | 2022-02-22 | ANSWRCOMP | Mitch Kovalev | [7 empty] | TRUE
21029900-0476 | Process - RA4 - CPK02-R2 - TCHW to RA4-RAH102-14_15_16-10 Design Model Issues | 2022-02-17 | 2022-02-21 |  | ANSWRCOMP | Mitch Kovalev | [7 empty] | TRUE
21029900-0477 | Process - RA4 - CPK02-R2 - TCHW to RA4-RAH102-05_06_07_08-10 Design Model Issues | 2022-02-17 | 2022-02-21 | 2022-02-22 | ANSWRCOMP | Mitch Kovalev | [7 empty] | TRUE
21029900-0478 | Process - RA4 - CPK02-R2 - TCHW to RA4-CC102-01_02_03_04-20 Design Model Issues_BT154_B158 | 2022-02-17 | 2022-02-21 | 2022-02-22 | ANSWRCOMP | Mitch Kovalev | [7 empty] | TRUE
21029900-0479 | Mechanical - CPK03-R3 - Streimer RFI 28 - Level 2FA Missing Detail Ref Orb | 2022-02-17 | 2022-02-21 |  | ANSWRCOMP | Alen Troyer | Connor | 2022-03-01 | RFI-0479 - pyth and flag pending | In model, no view in drawings |  |  |  | TRUE
21029900-0480 | Process - RA4 - CPK02-R4 - UN2 DM Branch Question - 409001-00 | 2022-02-17 | 2022-02-21 | 2022-02-23 | ANSWRCOMP | Mitch Kovalev | [7 empty] | TRUE
21029900-0481 | Process - RA4 - CPK02-R4 - CHCO2DI End of Lateral DM Discrepancy | 2022-02-17 | 2022-02-21 |  | ANSWRCOMP | Mitch Kovalev | [7 empty] | TRUE
21029900-0482 | Process - PUB1 - CPK02-R2 - OFA Dryer Skid Clarification | 2022-02-17 | 2022-02-21 | 2022-02-22 | ANSWRCOMP | Mitch Kovalev | [7 empty] | TRUE
21029900-0483 | Process - RA4 - CPK02-R4 - SHCWS/R High Point Vent Clarification | 2022-02-17 | 2022-02-21 | 2022-02-18 | ANSWRCOMP | Mitch Kovalev | [7 empty] | TRUE
21029900-0484 | Process - RA4 - CPK02-R4 - DM Clash with Process vs Existing (BT58) | 2022-02-17 | 2022-02-21 | 2022-02-22 | ANSWRCOMP | Mitch Kovalev | [7 empty] | TRUE
21029900-0485 | Wet Mech - MSB - CPK03-R8- Upsize of HSS for CUB4 Pipe Supports | 2022-02-17 | 2022-02-21 |  | OPEN | Mason Ray | Connor | 2022-03-02 | RFI-0485 - pyth and flag pending | No answer |  |  |  | TRUE
21029900-0486 | Wet Mech - MSB - CPK03-R2 - Extra BA at TCWH Pump Header Vents | 2022-02-17 | 2022-02-21 | 2022-02-17 | OPEN | Mason Ray | Connor | 2022-03-02 | RFI-0486 - pyth and flag pending | No answer |  |  |  | FALSE
21029900-0487 | Process - RA4 - CPK02-R4 - RODI End of Line Issues BT176 | 2022-02-17 | 2022-02-21 |  | ANSWRCOMP | Mitch Kovalev | [7 empty] | TRUE
21029900-0488 | Wet Mech - MSB - CPK03-R2 - Straight Length Requirements | 2022-02-17 | 2022-02-21 | 2022-02-21 | ANSWRCOMP | Mason Ray | Connor | 2022-03-02 | RFI-0488 - pyth and flag pending | CPK03-R2 |  |  |  | TRUE
21029900-0489 | Wet Mech - MSB - CPK03-R2 - TCHWSR Clash with Existing Anti-Foam Lines | 2022-02-17 | 2022-02-21 | 2022-02-21 | ANSWRCOMP | Mason Ray | Connor | 2022-03-02 | RFI-0489 - pyth and flag pending | CPK03-R2 |  |  |  | TRUE
21029900-0490 | Process - RA4 - CPK02-R4 - EOL Lateral Loops Not Shown | 2022-02-17 | 2022-02-21 | 2022-02-18 | ANSWRCOMP | Mitch Kovalev | [7 empty] | TRUE
21029900-0491 | Process - RA4 - CPK02-R4 - KN-19 on RA4-252-D0-A01 Clarification | 2022-02-17 | 2022-02-21 | 2022-02-22 | ANSWRCOMP | Mitch Kovalev | [7 empty] | TRUE
21029900-0492 | MECH-CPK02-R4-Link8 Equipment ID Tags Inconsistency SOO and MEL for PDIT131-0-10 A, B, C | 2022-02-17 | 2022-02-21 | 2022-02-18 | CLOSED | Carlos Acosta | [7 empty] | TRUE
21029900-0493 | Process - RA4 - CPK02-R4 - PA Clash with Wall and Ped Legs_BT112 | 2022-02-17 | 2022-02-21 |  | ANSWRCOMP | Mitch Kovalev | [7 empty] | TRUE
21029900-0494 | Process - RA4 - CPK02-R4 - OFA-PCWS Clash with DM Ped Braces_BT113 | 2022-02-17 | 2022-02-21 |  | OPEN | Mitch Kovalev | [7 empty] | FALSE
21029900-0495 | Structural - RA4 - CPK02-R2 - Missing (e) WF beams-f | 2022-02-18 | 2022-02-22 | 2022-02-18 | ANSWRCOMP | Mitchell Casio | [7 empty] | TRUE
21029900-0496 | Process - RA4 - CPK02-R4 - HPO2 Valve-Branch Discrepancy 412002-00 _ BT118 | 2022-02-17 | 2022-02-21 | 2022-02-21 | ANSWRCOMP | Mitch Kovalev | [7 empty] | TRUE
21029900-0497 | Process - RA4 - CPK02-R4 - PA Valve-Branch Discrepancy - 211002-00 _ BT122 | 2022-02-17 | 2022-02-21 | 2022-02-18 | ANSWRCOMP | Mitch Kovalev | [7 empty] | TRUE
21029900-0498 | DRYMECH-CPK02-RA4-MAH NET-TET Devices Qty Confirmation | 2022-02-18 | 2022-02-22 | 2022-02-22 | CLOSED | Carlos Acosta | [7 empty] | TRUE
21029900-0499 | Structural - CPK03 - Level 2 South Strut Rack Seismic Strut Move | 2022-02-18 | 2022-02-22 | 2022-02-22 | ANSWRCOMP | Alen Troyer | Connor | 2022-03-02 | RFI-0499 - pyth and flag pending | CPK03-R2 |  |  |  | TRUE
21029900-0500 | CSA - RA4 - CPK02-R4 - Containment Area CRC Clarification | 2022-02-18 | 2022-02-22 |  | ANSWRCOMP | Mitchell Casio | [7 empty] | TRUE
21029900-0501 | Telecom- CPK03-R2-MSB1- Fiber Backbone Routing(175,176,177,178) | 2022-02-18 | 2022-02-22 | 2022-02-22 | ANSWRCOMP | Michael Brown | Connor | 2022-03-07 | RFI-0501 - pyth and flag pending | CPK03-R2 |  |  |  | TRUE
21029900-0502 | Structural - RA4 - CPK02 - Column-Pedestal Offset-f | 2022-02-18 | 2022-02-22 | 2022-02-18 | ANSWRCOMP | Mitchell Casio | [7 empty] | FALSE
21029900-0503 | Electrical- CPK03-Ground Size Per Code-Confirmation | 2022-02-18 | 2022-02-22 |  | ANSWRCOMP | Michael Brown | Connor | 2022-03-02 | Cant find in the drawings | The ground has been upsized for a few circuits to align with NEC 250.122(B) |  |  |  | TRUE
21029900-0504 | Electrical- CPK02-RA4-Ground Size Per Code-Confirmation | 2022-02-18 | 2022-02-22 |  | ANSWRCOMP | Michael Brown | [7 empty] | TRUE
21029900-0505 | Wet Mechanical - CPK03-R2 - HRWS-R Valve Conflict with New Steel | 2022-02-18 | 2022-02-22 |  | ANSWRCOMP | Alen Troyer | Connor | 2022-03-07 | RFI-0505 - pyth and flag pending |  |  |  |  | TRUE
21029900-0505R1 | Wet Mechanical - CPK03-R2 - HRWS-R Valve Conflict with New Steel | 2022-02-18 | 2022-02-22 |  | VOID | Alen Troyer | [7 empty] | FALSE
21029900-0506 | CSA - RA4 - CPK02-R2 - Bigger Steel Columns Conflict | 2022-02-18 | 2022-02-22 |  | PENDING | Mitchell Casio | [7 empty] | FALSE
21029900-0507 | CSA - RA4 - CPK02-R2 - Existing Column Unistrut Constraint | 2022-02-18 | 2022-02-22 | 2022-02-23 | ANSWRCOMP | Mitchell Casio | [7 empty] | TRUE
21029900-0508 | Process - RA4 - CPK02 - HRWS GA-10 Clash with TIT | 2022-02-18 | 2022-02-22 | 2022-02-22 | ANSWRCOMP | Mitch Kovalev | [7 empty] | TRUE
21029900-0509 | Process - MSB - CPK01-R2 - Harder RFI 14 - K57 AW Clash with South Rack | 2022-02-21 | 2022-02-23 |  | ANSWRCOMP | Alen Troyer | [7 empty] | TRUE
21029900-0510 | Mechanical - CPK01-R2 - MSB - Harder RFI 15 - EXH Duct Clash with South Rack | 2022-02-21 | 2022-02-23 | 2022-02-22 | ANSWRCOMP | Alen Troyer | [7 empty] | TRUE
21029900-0511 | Process - MSB - CPK01-R2 - Harder RFI 16 - HPAR HPHe Lines Clash with South Rack | 2022-02-21 | 2022-02-23 |  | ANSWRCOMP | Alen Troyer | [7 empty] | TRUE
21029900-0512 | Mechanical - CPK03-R3 - MSB - Streimer RFI 29 - Level 5 EXSC and Relocation | 2022-02-21 | 2022-02-23 |  | ANSWRCOMP | Alen Troyer | Connor | 2022-03-02 | RFI-0512 - pyth and flag pending | SLIP SHEETED |  |  |  | TRUE
21029900-0513 | I&C- MSB1-CPK03-R2- MSB1-LCP106-1-00 | 2022-02-21 | 2022-02-23 | 2022-02-22 | ANSWRCOMP | Michael Brown | Connor | 2022-03-02 | RFI-0513 - pyth and flag pending | CPK03-R2, CPK03-R3 | Not in cold storage |  |  | FALSE
21029900-0514 | MSB - CSA - Plascore Wall Height Modifications and Bracing Details at AMHS travel paths | 2022-02-21 | 2022-02-23 |  | OPEN | Ellie Runte | [7 empty] | FALSE
21029900-0515 | Process - MSB - CPK03-R2 - Charter RFI 179 - CK-24 Substitution Request | 2022-02-21 | 2022-02-23 |  | OPEN | Alen Troyer | [7 empty] | FALSE
21029900-0516 | Electrical-CPK03 R2-MSB-MSB1-RIO650-103-04 NPS Duplicate | 2022-02-21 | 2022-02-23 |  | ANSWRCOMP | Taylor Bothmann | Connor | 2022-03-03 | RFI-0516 - pyth and flag pending | CPK03-R2, CPK03-R9 |  |  |  | TRUE
21029900-0517 | CSA - RA4 - CPK02-R2 - Column Frame Dimension Change | 2022-02-22 | 2022-02-24 |  | REJECTED | Mitchell Casio | [7 empty] | TRUE
21029900-0517R1 | CSA - RA4 - CPK02-R2 - Column Frame Dimension Change | 2022-02-22 | 2022-02-24 |  | ANSWRCOMP | [8 empty] | TRUE
21029900-0518 | Electrical-CPK03 R2-MSB Construction Receptacle Outlet Devices Confirmation | 2022-02-21 | 2022-02-23 |  | ANSWRCOMP | Taylor Bothmann | Connor | 2022-03-03 | RFI-0518 - pyth and flag pending | CPK03-R2, CPK03-R9 |  |  |  | TRUE
21029900-0519 | Mechanical - CPK03-R2 - MSB - Streimer RFI 30 - HXRA SA/RA Duct Vs Steel Clashes | 2022-02-22 | 2022-02-24 |  | OPEN | Alen Troyer | Connor | 2022-03-03 | RFI-0519 - pyth and flag pending | CPK03-R9 |  |  |  | TRUE
21029900-0520 | Mech Process - RA4 - CPK02-R5 - TCHW Support Dimension Clarification | 2022-02-22 | 2022-02-24 |  | ANSWRCOMP | Mitch Kovalev | [7 empty] | TRUE
21029900-0521 | Process - RA4 - CPK02-R2 - Deferred Submittal Clarification | 2022-02-22 | 2022-02-24 |  | OPEN | Mitch Kovalev | [7 empty] | FALSE
21029900-0522 | LSS - CPK03_R9- MSB1- Demo (P402-06-P57) | 2022-02-22 | 2022-02-24 |  | ANSWRCOMP | Michael Brown | Connor | 2022-03-07 | RFI-0522 - pyth and flag pending | CPK03-R9 |  |  |  | TRUE
21029900-0523 | Process - RA4 - CPK02-R2 - PDIT-EXGF Spec Clarification | 2022-02-22 | 2022-02-24 | 2022-02-22 | ANSWRCOMP | Mitch Kovalev | [7 empty] | TRUE
21029900-0524 | LSS - CPK03_R9- MSB1- PS42-04-128 and ST09-01-05 Demo Request | 2022-02-22 | 2022-02-24 |  | ANSWRCOMP | Michael Brown | [7 empty] | TRUE
21029900-0525 | Process - MSB - CPK03-R2 - Biocide Pumps Additional Information | 2022-02-22 | 2022-02-24 | 2022-02-22 | ANSWRCOMP | Mason Ray | Connor | 2022-03-04 | RFI-0525 - pyth and flag pending | CPK03-R2 |  |  |  | TRUE
21029900-0525R1 | Process - MSB - CPK03-R2 - Biocide Pumps Additional Information | 2022-02-22 | 2022-02-24 |  | OPEN | Mason Ray | [7 empty] | TRUE
21029900-0526 | Process - MSB - CPK03-R2 - AW Lateral Pipe Support Clashes | 2022-02-22 | 2022-02-24 |  | ANSWRCOMP | Mason Ray | Connor | 2022-03-07 | RFI-0526 - pyth and flag pending | Solved in RFI-0444 |  |  |  | TRUE
21029900-0527 | Process - MSB - CPK03-R2 - 4in DDA Wye Dimensional Issue | 2022-02-22 | 2022-02-24 |  | ANSWRCOMP | Mason Ray | Connor |  | RFI-0527 - pyth and flag pending | RFI says there is a view point attached, no view point provided… | Files need fixing |  |  | TRUE
21029900-0528 | Process - MSB - CPK03-R2 - PUB1 ROP Pipe Support Detail | 2022-02-22 | 2022-02-24 |  | ANSWRCOMP | Mason Ray | Connor | 2022-03-08 | RFI-0528 - pyth and flag pending | CPK03-R9 |  |  |  | TRUE
21029900-0529 | LSS - CPK03_R9- MSB1- MS1B05 Lights-Demo Request | 2022-02-22 | 2022-02-24 |  | OPEN | Michael Brown | [7 empty] | TRUE
21029900-0530 | Architectural - RA4 - CPK02-R4 - Paint System Clarification | 2022-02-22 | 2022-02-24 |  | ANSWRCOMP | Mitchell Casio | [7 empty] | TRUE
21029900-0531 | Process - RA4 - LLE01 - Bulk Caustic Tank TK252-1-10 Nozzle B Redesign | 2022-02-22 | 2022-02-24 | 2022-02-22 | ANSWRCOMP | Mitch Kovalev | [7 empty] | TRUE
21029900-0532 | Mechanical - MSB - CPK03 - MAH101-7-8-00 Orientation Submittal Vs Drawing | 2022-02-22 | 2022-02-24 | 2022-02-23 | ANSWRCOMP | Patrick McCarthy | [7 empty] | TRUE
21029900-0533 | CSA - MSB - CPK03-R8 - Updated Door Hardware Schedule and Door Hardware Specification | 2022-02-22 | 2022-02-24 |  | ANSWRCOMP | Ellie Runte | [7 empty] | TRUE
21029900-0534 | Control Valves-RA4-CPK02 R2-PCZ138-0-04A P&ID Confirmation | 2022-02-22 | 2022-02-24 | 2022-02-22 | ANSWRCOMP | Taylor Bothmann | [7 empty] | TRUE
21029900-0535 | CSA - MSB - CPK03-R2 - Wall Type J1 Liner Wall Attachment | 2022-02-22 | 2022-02-24 |  | OPEN | Ellie Runte | Connor | 2022-03-24 | RFI-0535 - pyth and flag pending | CPK03-R3 | Not in cold storage |  |  | FALSE
21029900-0536 | CSA - MSB - HM Door Swing & Egress Clarifications | 2022-02-22 | 2022-02-24 |  | OPEN | Ellie Runte |  |  |  |  | Not in cold storage |  |  | FALSE
21029900-0537 | Electrical-CPK03 R2-MSB-Exit Light Type Confirmation | 2022-02-22 | 2022-02-24 | 2022-02-23 | ANSWRCOMP | Taylor Bothmann | Connor | 2022-03-08 | RFI-0537 - pyth and flag pending | Waiting to hear back from document control |  |  |  | TRUE
21029900-0538 | CSA - MSB - CPK03-R2 - Conflicting Column Details | 2022-02-22 | 2022-02-24 |  | OPEN | Ellie Runte | Connor | 2022-03-24 | RFI-0538 - pyth and flag pending | Slipsheeted: CPK03-R11, CPK03-R8, CPK03-R3 | Not in cold storage |  |  | FALSE
21029900-0539 | CSA - MSB - CPK03-R2 Missed Ceiling Demo Scope | 2022-02-22 | 2022-02-24 |  | ANSWRCOMP | Ellie Runte | Connor | 2022-03-04 | RFI-0539 - pyth and flag pending | CPK03-R2, CPK03-R9 |  |  |  | TRUE
21029900-0540 | LSS - CPK03_R9- MSB1- FME-1-P51-01 | 2022-02-22 | 2022-02-24 |  | ANSWRCOMP | Michael Brown | Connor | 2022-03-04 | RFI-0540 - pyth and flag pending | CPK03-R9, CPK03-R11 |  |  |  | TRUE
21029900-0541 | LSS - CPK03_R9- MSB1- FBP Panel And Circuit (Request) | 2022-02-22 | 2022-02-24 |  | ANSWRCOMP | Michael Brown | Connor | 2022-03-08 | RFI-0541 - pyth and flag pending | CPK03-R11 |  |  |  | TRUE
21029900-0542 | Process - MSB - CPK03-R2 - SP-PVDF Highpoint Lowpoint Clarification | 2022-02-22 | 2022-02-24 |  | ANSWRCOMP | Mason Ray | Connor | 2022-03-08 | RFI-0542 - pyth and flag pending | CPK03-R11 |  |  |  | TRUE
21029900-0543 | LSS - CPK03_R9- MSB1- Request for 42-04 Low loop and HXRA | 2022-02-22 | 2022-02-24 |  | ANSWRCOMP | Michael Brown | Connor | 2022-03-08 | RFI-0543 - pyth and flag pending | CPK03-R9, CPK03-R11 |  |  |  | TRUE
21029900-0544 | LSS - CPK03_R9- MSB1- FCP-1-Q57-42 | 2022-02-22 | 2022-02-24 |  | ANSWRCOMP | Michael Brown | Connor | 2022-03-08 | RFI-0544 - pyth and flag pending | CPK03-R9, CPK03-R11 |  |  |  | TRUE
21029900-0545 | LSS - CPK03_R9- MSB1- Duplicate Address/Swap to Speaker | 2022-02-22 | 2022-02-24 |  | ANSWRCOMP | Michael Brown | Connor | 2022-03-08 | RFI-0545 - pyth and flag pending | CPK03-R9, CPK03-R11 |  |  |  | TRUE
21029900-0546 | CSA - CPK03-IFC - MSB - Architectural details required | 2022-02-22 | 2022-02-24 |  | ANSWRCOMP | Steve Mazzoni | Connor | 2022-03-08 | RFI-0546 - pyth and flag pending | Slipsheet with new pages? |  |  |  | TRUE
21029900-0547 | LSS - CPK03_R9- MSB1- MS1-HF-2FA-C0000 | 2022-02-22 | 2022-02-24 |  | ANSWRCOMP | Michael Brown | Connor | 2022-03-08 | RFI-0547 - pyth and flag pending | CPK03-R9, CPK03-R11 |  |  |  | TRUE
21029900-0548 | LSS - CPK03_R9- MSB1- Horn Strobe (Clarification) | 2022-02-22 | 2022-02-24 |  | ANSWRCOMP | Michael Brown | Connor | 2022-03-08 | RFI-0548 - pyth and flag pending | CPK03-R9, CPK03-R11 |  |  |  | TRUE
21029900-0549 | DRYMECH-CPK02-RA4- SA header and East Duct Sizing Change | 2022-02-22 | 2022-02-24 |  | ANSWRCOMP | Carlos Acosta | [7 empty] | TRUE
21029900-0550 | LSS - CPK03_R9- MSB1- HF2FA(C,D)-0000 | 2022-02-22 | 2022-02-24 |  | ANSWRCOMP | Michael Brown | Connor | 2022-03-28 | RFI-0550 - pyth and flag pending | Same as RFI-0545 |  |  |  | TRUE
21029900-0551 | DRYMECH-CPK02-R2-RA4-EXGF turning vanes to be added | 2022-02-22 | 2022-02-24 |  | OPEN | Carlos Acosta | [7 empty] | FALSE
21029900-0552 | DRYMECH-CPK02-R2-RA4-RA4 MAH Duct Size Change at J/10 | 2022-02-22 | 2022-02-24 |  | OPEN | Carlos Acosta | [7 empty] | TRUE
21029900-0553 | LSS - CPK03_R9- MSB1- QPS-RF0I27 | 2022-02-22 | 2022-02-24 |  | ANSWRCOMP | Michael Brown | Connor | 2022-03-28 | RFI-0553 - pyth and flag pending | See RFI-0555 and In CPK03-R11 |  |  |  | TRUE
21029900-0554 | DRYMECH-CSA-ELEC-CPK02-R2-RA4-Wall Clash near North Stockers | 2022-02-22 | 2022-02-24 |  | OPEN | Carlos Acosta | [7 empty] | TRUE
21029900-0555 | LSS - CPK03_R9- MSB1- QPS028 | 2022-02-23 | 2022-02-25 |  | ANSWRCOMP | Michael Brown | Connor | 2022-03-29 | RFI-0555 - pyth and flag pending | CPK03-R9, CPK03-R11 |  |  |  | TRUE
21029900-0556 | Mechanical - CPK03-R2 - MSB - New SA Duct vs. Existing Access Door | 2022-02-23 | 2022-02-25 |  | CLOSED | Alen Troyer | Connor | [6 empty] | TRUE
21029900-0557 | Wet Mech - MSB - CPK03-R2 - TCHW Clash with Fire Protection at Column N/52 | 2022-02-23 | 2022-02-25 |  | ANSWRCOMP | Mason Ray | Connor |  | RFI-0557 - pyth and flag pending |  |  |  |  | TRUE
21029900-0558 | Wet Mech - MSB - CPK03-R2 - MSB TCHW Submain EOL Detail Clarification | 2022-02-23 | 2022-02-25 |  | OPEN | Mason Ray | Connor |  | RFI-0558 - pyth and flag pending |  |  |  |  | TRUE
21029900-0559 | M10 Hat Fitting Substitution | 2022-02-24 | 2022-02-28 |  | ANSWRCOMP | Ellie Runte | [7 empty] | TRUE
21029900-0560 | Wet Mech - MSB - CPK03-R2 - TCHW Vs Seismic Brace @ Column R/55 | 2022-02-23 | 2022-02-25 |  | ANSWRCOMP | Mason Ray | Connor |  | RFI-0560 - pyth and flag pending |  |  |  |  | TRUE
21029900-0561 | Wall Type A4 Design Change | 2022-02-23 | 2022-02-25 |  | OPEN | Ellie Runte | [7 empty] | FALSE
21029900-0562 | Architectural - RA4 - CPK02-R2 - Wall type and Typical Detail Clarification | 2022-02-23 | 2022-02-25 |  | ANSWRCOMP | Mitchell Casio | [7 empty] | TRUE
21029900-0563 | LSS - CPK03_R9- MSB1-ER(clarification) | 2022-02-23 | 2022-02-25 |  | ANSWRCOMP | Michael Brown | Connor | [6 empty] | TRUE
21029900-0564 | Structural - MSB - CPK03-R2 - Beam Relocation over Exhaust Fans | 2022-02-23 | 2022-02-25 |  | OPEN | Mason Ray | Connor |  |  |  | Not in cold storage |  |  | FALSE
21029900-0565 | Process - MSB - CPK03-R2 - GSW,CSW Clash With Electrical Zone | 2022-02-24 | 2022-02-28 |  | OPEN | Mason Ray | [7 empty] | TRUE
21029900-0566 | Process - MSB - CPK03-R2 - SWS Lateral Extension BA-30 | 2022-02-24 | 2022-02-28 |  | OPEN | Mason Ray | [7 empty] | TRUE
21029900-0567 | Electrical-MSB-CPK03 R2-Panel Relocation - Conduit & Wire | 2022-02-24 | 2022-02-28 |  | OPEN | Taylor Bothmann | [7 empty] | FALSE
21029900-0568 | Process - MSB - CPK03-R2 - 1/2in CK-59 Threaded Lead Time | 2022-02-24 | 2022-02-28 |  | OPEN | Mason Ray | [7 empty] | TRUE
21029900-0569 | LSS - CPK03_R9- MSB1- duplicate addresses | 2022-02-24 | 2022-02-28 | 2022-02-26 | ANSWRCOMP | Michael Brown | Connor | [6 empty] | TRUE
21029900-0570 | LSS - CPK03_R9- MSB1- Combo units L/51 and N57 | 2022-02-24 | 2022-02-28 | 2022-02-26 | ANSWRCOMP | Michael Brown | Connor | [6 empty] | TRUE
21029900-0571 | CSA - MSB -CPK03-R5 IFC Roofing Details Required | 2022-02-24 | 2022-02-28 | 2022-02-28 | ANSWRCOMP | Steve Mazzoni | Connor | [6 empty] | TRUE
21029900-0572 | Telecom- CPK01-R2-RA4-Cable Tray Reroute | 2022-02-24 | 2022-02-28 |  | OPEN | Michael Brown | [7 empty] | FALSE
21029900-0573 | Electrical-MSB-CPK03 R2-Construction Receptacle Panel Clarification | 2022-02-24 | 2022-02-28 |  | OPEN | Taylor Bothmann | [7 empty] | FALSE
21029900-0574 | I&C-MSB/RA4-VFD Temperature Monitoring Alarm within FMS | 2022-02-24 | 2022-02-28 |  | PENDING | Taylor Bothmann | [7 empty] | FALSE
21029900-0575 | Process - MSB - CPK03-R2 - BIO Metering Pumps | 2022-02-24 | 2022-02-28 |  | VOID | Mason Ray | [7 empty] | FALSE
21029900-0576 | Process - MSB - CPK03-R2 - Spec Gas Lateral EOL Valves | 2022-02-24 | 2022-02-28 | 2022-02-26 | ANSWRCOMP | Mason Ray | Connor | 2022-03-08 | RFI-0576 - pyth and flag pending |  |  |  |  | TRUE
21029900-0577 | Process - MSB - CPK03-R2 - EI Williams Silencers for SHPOFA | 2022-02-24 | 2022-02-28 |  | OPEN | Mason Ray | [7 empty] | TRUE
21029900-0578 | I and C- MSB1-CPK03-R2-GTW650-10-90 Panel Location | 2022-02-24 | 2022-02-28 | 2022-02-26 | ANSWRCOMP | Michael Brown | Connor | [6 empty] | TRUE
21029900-0579 | Wet Mechanical - CPK01-R2 - HRWS-R Valve Conflict with New Steel | 2022-02-24 | 2022-02-28 | 2022-02-28 | ANSWRCOMP | Alen Troyer | [7 empty] | TRUE
21029900-0580 | Structural - CPK01-R2 - P1934 Clash with White Steel | 2022-02-24 | 2022-02-28 |  | OPEN | Alen Troyer | [7 empty] | TRUE
21029900-0581 | Structural - MSB - CPK03-R5 Grid J-51 Connection | 2022-02-24 | 2022-02-28 | 2022-03-02 | ANSWRCOMP | Steve Mazzoni | Connor | [6 empty] | TRUE
21029900-0582 | Process - RA4 - CPK02-R2 - SSH-5140 Drain Clarification | 2022-02-24 | 2022-02-28 |  | OPEN | Mitch Kovalev | [7 empty] | FALSE
21029900-0583 | Wet Mech - MSB - CPK03-R2 - CW Distribution Process Flow Diagram | 2022-02-25 | 2022-03-01 | 2022-03-02 | ANSWRCOMP | Mason Ray | Connor | 2022-03-08 | RFI-0583 - pyth and flag pending |  |  |  |  | TRUE
21029900-0584 | Electrical- CPK03-R2 - MSB1- Basic Wall | 2022-02-25 | 2022-03-01 |  | OPEN | Michael Brown | [7 empty] | FALSE
21029900-0585 | I&C- MSB1-CPK03-R2-RFI0133 confirm | 2022-02-25 | 2022-03-01 | 2022-02-28 | ANSWRCOMP | Michael Brown | Connor | [6 empty] | TRUE
21029900-0586 | Structural - RA4 - CPK02-R1 - RA4 South Facade Conflicts | 2022-02-28 | 2022-03-02 |  | OPEN | Mitchell Casio | [7 empty] | FALSE
21029900-0587 | Electrical - CPK02-R6 RA4 ECR R4D1J05B for Elevator Load | 2022-02-28 | 2022-03-02 | 2022-03-02 | OPEN | Ismael Hernandez | [7 empty] | FALSE
21029900-0588 | Architectural - RA4 - CPK02-R5 - IFC Sheet Correction | 2022-02-28 | 2022-03-02 |  | OPEN | Mitchell Casio | [7 empty] | FALSE
21029900-0589 | DRYMECH-CPK02-RA2-EXGF Duct and Damper Size Discrepancy | 2022-02-28 | 2022-03-02 |  | OPEN | Carlos Acosta | [7 empty] | TRUE
21029900-0590 | Electrical CPK02-R2 RA4 - PCW AFD201-1-10 Relocation | 2022-02-28 | 2022-03-02 |  | OPEN | Ismael Hernandez | [7 empty] | FALSE
21029900-0591 | Process - RA4 - CPK02-R2 - Suez RODI Skid RODII8830F Discrepancy | 2022-02-28 | 2022-03-02 | 2022-02-28 | ANSWRCOMP | Mitch Kovalev | [7 empty] | TRUE
21029900-0592 | Process - MSB - LLP02 - IMO Carbonator CO2 Injection Lines | 2022-02-28 | 2022-03-07 |  | OPEN | Rees Bixler | [7 empty] | FALSE
21029900-0593 | Structural - MSB - CPK03-R5 RA-ST-2103 Bolt conflict with 1.75in ATR at Splice | 2022-02-28 | 2022-03-02 | 2022-03-02 | ANSWRCOMP | Steve Mazzoni | Connor | [6 empty] | TRUE
21029900-0594 | Process - RA4 - CPK07 - OFA Lateral Sizing | 2022-02-28 | 2022-03-02 |  | OPEN | Mitch Kovalev | [7 empty] | FALSE
21029900-0595 | Process - RA4 - CPK02-R4 - AW Submain to Lateral Transition | 2022-02-28 | 2022-03-02 |  | OPEN | Mitch Kovalev | [7 empty] | FALSE
21029900-0596 | Process - RA4 - CPK02-R4 - Additional CHCO2DI Submain POCs Unions | 2022-02-28 | 2022-03-02 |  | OPEN | Mitch Kovalev | [7 empty] | FALSE
21029900-0597 | Process - RA4 - CPK02-R2 - SHCW Tie-In Clarification | 2022-02-28 | 2022-03-02 |  | OPEN | Mitch Kovalev | [7 empty] | FALSE
21029900-0598 | Electrical- CPK03-R2 MXD1R51A and MXD1R51B- Relocation | 2022-02-28 | 2022-03-02 | 2022-03-02 | ANSWRCOMP | Michael Brown | Connor | [6 empty] | FALSE
21029900-0599 | Process - RA4 - CPK02-R4 - PCW Lateral EOL Valve | 2022-02-28 | 2022-03-02 |  | OPEN | Mitch Kovalev | [7 empty] | FALSE
21029900-0600 | Process - RA4 - CPK02-R4 - HPO2 Submain Throttling Valve Clarification | 2022-02-28 | 2022-03-02 |  | OPEN | Mitch Kovalev | [7 empty] | FALSE
21029900-0601 | Process - RA4 - CPK02-R4 - SHCW Submain PDIT Spec Clarification | 2022-02-28 | 2022-03-02 |  | OPEN | Mitch Kovalev | [7 empty] | FALSE
21029900-0602 | Process - RA4 - CPK02-R4 - PV Inconsistent ECC Reducers | 2022-02-28 | 2022-03-02 |  | OPEN | Mitch Kovalev | [7 empty] | FALSE
21029900-0603 | Process - RA4 - CPK02-R4 - DCM Main Size | 2022-02-28 | 2022-03-02 |  | OPEN | Mitch Kovalev | [7 empty] | FALSE
21029900-0604 | Mech Process - RA4 - CPK02 - TCHW and IW Passivation Confirmation | 2022-02-28 | 2022-03-02 |  | OPEN | Mitch Kovalev | [7 empty] | FALSE
21029900-0605 | Process - RA4 - CPK02-R4 - EOL View Tile Access Clarification | 2022-02-28 | 2022-03-02 |  | OPEN | Mitch Kovalev | [7 empty] | FALSE
21029900-0606 | CSA - MSB - CPK03-R8 - Trapeze at Uplift Post Locations | 2022-03-01 | 2022-03-03 |  | OPEN | Ellie Runte | [7 empty] | FALSE
21029900-0607 | Process - MSB - CPK03-R2 - SHPOFA Routing Changes | 2022-03-01 | 2022-03-03 |  | OPEN | Mason Ray | [7 empty] | TRUE
21029900-0608 | Process - MSB - CPK03-R2 - CHCO2Di Routing Changes | 2022-03-01 | 2022-03-03 |  | OPEN | Mason Ray | [7 empty] | FALSE
21029900-0609 | Process - MSB - CPK03-R2 - SWS Routing Changes | 2022-03-01 | 2022-03-03 |  | OPEN | Mason Ray | [7 empty] | FALSE
21029900-0610 | Process - MSB - CPK03-R2 - SWS Routing to Scrubbers | 2022-03-01 | 2022-03-03 |  | OPEN | Mason Ray | [7 empty] | FALSE
21029900-0611 | Process - MSB - CPK03-R2 - Adjust PV Strut to Use Existing Rack | 2022-03-01 | 2022-03-03 |  | OPEN | Mason Ray | [7 empty] | FALSE
21029900-0612 | Process - MSB - CPK03-R2 - UPWS/R Routing | 2022-03-01 | 2022-03-03 |  | OPEN | Mason Ray | [7 empty] | FALSE
21029900-0613 | CPK01-R2 - Mech/FP - MSB - L2 IMO Existing Anti Foaming Lines | 2022-03-01 | 2022-03-03 |  | OPEN | Alen Troyer | [7 empty] | TRUE
21029900-0614 | Process - RA4 - CPK02-R4 - Wall Under the RMF | 2022-03-01 | 2022-03-03 |  | OPEN | Mitch Kovalev | [7 empty] | FALSE
21029900-0615 | DRYMECH-TELECOM-PROCESS-CPK02-R2- Exhaust Duct Conflicts at Grid A8-16 | 2022-03-01 | 2022-03-03 |  | OPEN | Carlos Acosta | [7 empty] | FALSE
21029900-0616 | Process - RA4 - CPK02-R4 - Clarification on HPV & LPD | 2022-03-01 | 2022-03-03 |  | OPEN | Mitch Kovalev | [7 empty] | FALSE
21029900-0617 | Process - RA4 - CPK02-R4 - PV Lateral 152N-S SOW Clarification | 2022-03-01 | 2022-03-03 |  | OPEN | Mitch Kovalev | [7 empty] | FALSE
21029900-0618 | I&C- MSB1-CPK03-R2- 6" Cable tray substitution | 2022-03-01 | 2022-03-03 |  | OPEN | Michael Brown | [7 empty] | TRUE
21029900-0619 | DRYMECH-CPK02-R2 Flexible Ductwork Connection for Cleanroom Space | 2022-03-01 | 2022-03-03 |  | OPEN | Carlos Acosta | [7 empty] | FALSE
21029900-0620 | Process - MSB - CPK03-R2 - CPCW Inertia Bases Overlapping | 2022-03-01 | 2022-03-03 |  | OPEN | Mason Ray | [7 empty] | FALSE
21029900-0621 | CSA-CPK02-R2-Pedestal Vs Cable Tray Conflict at Grid A8 | 2022-03-01 | 2022-03-03 |  | OPEN | Carlos Acosta | [7 empty] | FALSE
21029900-0622 | I&C- MSB1-CPK03-R3-PE221 and PIT221 | 2022-03-01 | 2022-03-03 |  | OPEN | Michael Brown | [7 empty] | TRUE
21029900-0623 | Process - RA4 - CPK02-R4 - Suez Redundancy Skid Motor Substitution | 2022-03-01 | 2022-03-03 |  | OPEN | Mitch Kovalev | [7 empty] | FALSE
21029900-0624 | CSA - RA4 - CPK02-R1 - Cleanout Clarification | 2022-03-02 | 2022-03-04 |  | OPEN | Mitchell Casio | [7 empty] | TRUE
21029900-0625 | Architectural - RA4 - CPK07 - Reissue IFC Drawing | 2022-03-02 | 2022-03-04 |  | OPEN | Mitchell Casio | [7 empty] | FALSE
21029900-0626 | CSA - RA4 - CPK02-R2 and R8 - 9-Line Wall Penetrations | 2022-03-02 | 2022-03-04 |  | OPEN | Mitchell Casio | [7 empty] | FALSE
21029900-0627 | Structural - RA4 - CPK02-R2 - Seismic Upper Connection Point | 2022-03-02 | 2022-03-04 |  | OPEN | Mitchell Casio | [7 empty] | FALSE
21029900-0628 | Structural - RA4 - CPK02-R7 - 6x6 HSS Steel Rod Drop Washer | 2022-03-02 | 2022-03-04 |  | PENDING | Mitchell Casio | [7 empty] | FALSE
21029900-0629 | DRYMECH-CSA-CPK02-R2-CPK07-EXYTE Grid Flashing Detail | 2022-03-02 | 2022-03-04 |  | PENDING | Carlos Acosta | [7 empty] | FALSE
21029900-0630 | Process - RA4 - CPK02-R4 - Drip Pan 12.00-CHWS-ADS-113303 | 2022-03-02 | 2022-03-04 |  | OPEN | Jordan Pifer | [7 empty] | FALSE
21029900-0631 | Electrical- MSB1-CPK03-R2- SCC Cabinet and Receptacles | 2022-03-02 | 2022-03-04 |  | OPEN | Michael Brown | [7 empty] | FALSE
21029900-0632 | DRYMECH-CPK02-R2-RA4-EXGF-3 Fan Inlet and Stack Size | 2022-03-02 | 2022-03-04 |  | OPEN | Carlos Acosta | [7 empty] | FALSE
21029900-0633 | Process - MSB - CPK03-R2 - UPW low point size & type clarification | 2022-03-02 | 2022-03-04 |  | OPEN | Mason Ray | [7 empty] | TRUE
21029900-0634 | Process - MSB - CPK03-R2 - SWS & UN2 Confirmation | 2022-03-02 | 2022-03-04 |  | OPEN | Mason Ray | [7 empty] | TRUE
21029900-0635 | Process - MSB - CPK03-R2 - ISAT-MP-BM-XX-G1-U Substitution Clarification | 2022-03-02 | 2022-03-04 |  | OPEN | Mason Ray | [7 empty] | TRUE
21029900-0636 | Process - MSB - CPK03-R2 - ALL AREAS - ISAT PHD Supports Substitutions | 2022-03-02 | 2022-03-04 |  | OPEN | Mason Ray | [7 empty] | TRUE
21029900-0637 | Telecom- CPK03-R2-MSB1- WAP Locations/Elevations | 2022-03-02 | 2022-03-04 |  | OPEN | Michael Brown | [7 empty] | FALSE
21029900-0638 | Process - RA4 - CPK02-R4 - AW-261- PW Lateral Slope Clarification | 2022-03-02 | 2022-03-04 |  | OPEN | Jordan Pifer | [7 empty] | FALSE
21029900-0639 | Process - RA4 - CPK02-R4 - DM Issues - ISAT vs Pedestals | 2022-03-02 | 2022-03-04 |  | OPEN | Jordan Pifer | [7 empty] | FALSE
21029900-0640 | Process - RA4 - CPK02-R2 - NaOH Routing Clarification | 2022-03-02 | 2022-03-04 |  | OPEN | Jordan Pifer | [7 empty] | FALSE
21029900-0641 | Process - MSB - CPK03-R2 - Slide Substitution Request | 2022-03-03 | 2022-03-07 |  | OPEN | Mason Ray | [7 empty] | TRUE
21029900-0642 | Process - MSB - CPK03-R2 - UPWS/R Lateral Substitute with GF Stress-Less Guide | 2022-03-03 | 2022-03-07 |  | OPEN | Mason Ray | [7 empty] | FALSE
21029900-0643 | Process - MSB - CPK03-R2 - NaOH Caustic Box anchorage Detail | 2022-03-03 | 2022-03-07 |  | OPEN | Mason Ray | [7 empty] | FALSE
21029900-0644 | Process - MSB - CPK03-R2 - CK-93 Substitution Request | 2022-03-03 | 2022-03-07 |  | OPEN | Mason Ray | [7 empty] | FALSE
21029900-0645 | Process - MSB - CPK03-R2 - ISAT Stainless Pipe Attachment Hardware | 2022-03-03 | 2022-03-07 | 2022-03-03 | OPEN | Mason Ray | [7 empty] | FALSE
21029900-0646 | Process - RA4 - CPK02-R2 - PVAC Distribution Routing Clarification | 2022-03-03 | 2022-03-07 | 2022-03-03 | OPEN | Jordan Pifer | [7 empty] | FALSE
21029900-0647 | Process - RA4 - CPK02-R2 - Existing PCWS Line Braces Clashing New MUA Duct | 2022-03-03 | 2022-03-07 |  | OPEN | Mitch Kovalev | [7 empty] | FALSE
21029900-0648 | LSS - CPK03_R9- MSB1-Cable Reroute | 2022-03-03 | 2022-03-07 |  | OPEN | Michael Brown | [7 empty] | FALSE
21029900-0649 | I&C- MSB1-CPK03-R2- 120V Rotork Actuators Lockout Tagout Tab | 2022-03-03 | 2022-03-07 |  | OPEN | Michael Brown | [7 empty] | FALSE
21029900-0650 | I&C- MSB1-CPK03-R2- Rotork Actuators (Position Indicators) | 2022-03-03 | 2022-03-07 |  | OPEN | Michael Brown | [7 empty] | FALSE
21029900-0651 | I&C- MSB1-CPK03-R2- PCZ133-0-04X (Ground level Handstation) | 2022-03-03 | 2022-03-07 |  | OPEN | Michael Brown | [7 empty] | FALSE
21029900-0652 | I&C- MSB1-CPK03-R2- PE/PDITS/PCZs (location Updates) | 2022-03-03 | 2022-03-07 |  | OPEN | Michael Brown | [7 empty] | FALSE
21029900-0653 | I and C - CPK02-R2 RA4 - Level Switch Tags | 2022-03-03 | 2022-03-07 |  | OPEN | Ismael Hernandez | [7 empty] | FALSE
21029900-0654 | I and C - CPK02-R2 RA4 - PMD for PCZ from Two Different PLCs | 2022-03-03 | 2022-03-07 |  | OPEN | Ismael Hernandez | [7 empty] | FALSE
21029900-0655 | Telecom- MSB1-CPK03-R3- CPS-MXD (TO identification number) | 2022-03-03 | 2022-03-07 |  | OPEN | Michael Brown | [7 empty] | FALSE
21029900-0656 | Process - RA4 - CPK02-R4 - IW Submain 231001 FI-9 | 2022-03-03 | 2022-03-07 |  | OPEN | Jordan Pifer | [7 empty] | FALSE
21029900-0657 | Telecom- CPK02-R4-RA4- Camera Telecom Box | 2022-03-03 | 2022-03-07 |  | OPEN | Michael Brown | [7 empty] | FALSE
21029900-0658 | Process - RA4 - CPK02-R4 - PU Not enough room for AAV under RMF | 2022-03-03 | 2022-03-07 |  | OPEN | Jordan Pifer | [7 empty] | FALSE
21029900-0659 | Electrical-MSB-CPK03 R2-CMXD1M55A-CKT 3 update on ECR | 2022-03-03 | 2022-03-07 |  | OPEN | Taylor Bothmann | [7 empty] | FALSE
21029900-TEST1 | TEST1 RFI - HOW TO BUNDLE MULTIPLE RFI'S/NEW PCI'S INTO SINGLE OCO | 2022-02-17 | 2022-02-21 |  | REJECTED | Jenna Stein | [7 empty] | FALSE
21029900-TEST2 | TEST2 RFI - HOW TO BUNDLE MULTIPLE RFI'S/NEW PCI'S INTO SINGLE OCO | 2022-02-17 | 2022-02-21 |  | REJECTED | Jenna Stein | [7 empty] | FALSE
21029900-TEST3 | TEST3 RFI - HOW TO BUNDLE MULTIPLE RFI'S/NEW PCI'S INTO SINGLE OCO | 2022-02-17 | 2022-02-21 |  | REJECTED | Jenna Stein | [7 empty] | FALSE

## Cold Store Log
RFI Number | CMiC Subject | Name | Status | To Contact | CoauthorContact | RFI Spec Section | Modified | Item Type | Path | RFI Code
21029900-0641 | Process - MSB - CPK03-R2 - Slide Substitution Request | 21029900-0641 - Process - MSB - CPK03-R2 - Slide Substitution Request.pdf | Open | JACOBS ENGINEERING GROUP INC (Document Control) | CHARTER MECHANICAL CONTRACTORS INC (Mike Tucker) |  | 44623.4137 | Item | sites/1232505342/CMiC RFI Response | 0641
21029900-0636 | Process - MSB - CPK03-R2 - ALL AREAS - ISAT PHD Supports Substitutions | 21029900-0636 - Process - MSB - CPK03-R2 - ALL AREAS - ISAT PHD Supports Substitutions.pdf | Open | JACOBS ENGINEERING GROUP INC (Document Control) | CHARTER MECHANICAL CONTRACTORS INC (Mike Tucker) |  | 44622.7922 | Item | sites/1232505342/CMiC RFI Response | 0636
21029900-0635 | Process - MSB - CPK03-R2 - ISAT-MP-BM-XX-G1-U Substitution Clarification | 21029900-0635 - Process - MSB - CPK03-R2 - ISAT-MP-BM-XX-G1-U Substitution Clarification.pdf | Open | JACOBS ENGINEERING GROUP INC (Document Control) | CHARTER MECHANICAL CONTRACTORS INC (Mike Tucker) |  | 44622.7814 | Item | sites/1232505342/CMiC RFI Response | 0635
21029900-0634 | Process - MSB - CPK03-R2 - SWS & UN2 Confirmation | 21029900-0634 - Process - MSB - CPK03-R2 - SWS UN2 Confirmation.pdf | Open | JACOBS ENGINEERING GROUP INC (Document Control) | CHARTER MECHANICAL CONTRACTORS INC (Kellen Hearn) |  | 44622.7814 | Item | sites/1232505342/CMiC RFI Response | 0634
21029900-0633 | Process - MSB - CPK03-R2 - UPW low point size & type clarification | 21029900-0633 - Process - MSB - CPK03-R2 - UPW low point size type clarification.pdf | Open | JACOBS ENGINEERING GROUP INC (Document Control) | CHARTER MECHANICAL CONTRACTORS INC (David Hartshorn) |  | 44622.7815 | Item | sites/1232505342/CMiC RFI Response | 0633
21029900-0624 | CSA - RA4 - CPK02-R1 - Cleanout Clarification | RFI-0624 CSA - RA4 - CPK02-R1 - Cleanout Clarification.pdf | Open | JACOBS ENGINEERING GROUP INC (Document Control) | COFFMAN EXCAVATION INC (Dustin Mayfield) |  | 44621.8533 | Item | sites/1232505342/CMiC RFI Response | 0624
21029900-0622 | I&C- MSB1-CPK03-R3-PE221 and PIT221 | RFI-0622- I and C- MSB1-CPK03-R3-PE221 and PIT221.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44622.6823 | Item | sites/1232505342/CMiC RFI Response | 0622
21029900-0618 | I&C- MSB1-CPK03-R2- 6" Cable tray substitution | RFI-0618 I and C- MSB1-CPK03-R2- 6inCable tray substitution.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44622.683 | Item | sites/1232505342/CMiC RFI Response | 0618
21029900-0613 | CPK01-R2 - Mech/FP - MSB - L2 IMO Existing Anti Foaming Lines | RFI0613-CPK01-R2 - Mech-FP - MSB - L2 IMO Existing Anti Foam Line-Resp.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | DELTA FIRE INC (Steve McCourtney) |  | 44623.438 | Item | sites/1232505342/CMiC RFI Response | 0613
21029900-0607 | Process - MSB - CPK03-R2 - SHPOFA Routing Changes | 21029900-0607 - Process - MSB - CPK03-R2 - SHPOFA Routing Changes.pdf | Open | JACOBS ENGINEERING GROUP INC (Document Control) | CHARTER MECHANICAL CONTRACTORS INC (Kellen Hearn) |  | 44621.4657 | Item | sites/1232505342/CMiC RFI Response | 0607
21029900-0593 | Structural - MSB - CPK03-R5 RA-ST-2103 Bolt conflict with 1.75in ATR at Splice | RFI-0593-Structural - MSB - CPK03-R5 RA-ST-2103 Bolt conflict with 1.75in ATR at Splice-RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | SOWLES CO DBA SOWLES STEEL ERECTORS (Kyle Wilcox) |  | 44622.4892 | Item | sites/1232505342/CMiC RFI Response | 0593
21029900-0591 | Process - RA4 - CPK02-R2 - Suez RODI Skid RODII8830F Discrepancy | RFI-0591 Process - RA4 - CPK02-R2 - Suez RODI Skid RODII8830F Discrepancy RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Zachary Villarmia) |  | 44620.7869 | Item | sites/1232505342/CMiC RFI Response | 0591
21029900-0589 | DRYMECH-CPK02-RA2-EXGF Duct and Damper Size Discrepancy | RFI-0589 DRYMECH-CPK02-R2-EXGF Duct and Damper Size Discrepancy RESPONSE (1303314204).pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | APOLLO INC (Evan Lehman) |  | 44623.5731 | Item | sites/1232505342/CMiC RFI Response | 0589
21029900-0585 | I&C- MSB1-CPK03-R2-RFI0133 confirm | RFI-0585-I and C- MSB1-CPK03-R2-RFI0133 confirm.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44621.5056 | Item | sites/1232505342/CMiC RFI Response | 0585
21029900-0583 | Wet Mech - MSB - CPK03-R2 - CW Distribution Process Flow Diagram | 21029900-0583 - Wet Mech - MSB - CPK03-R2 - CW Distribution Process Flow Diagram.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Dave Knecht) |  | 44622.4901 | Item | sites/1232505342/CMiC RFI Response | 0583
21029900-0581 | Structural - MSB - CPK03-R5 Grid J-51 Connection | RFI-0581 - Structural - MSB - CPK03-R5 Grid J-51 Connection- RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | SOWLES CO DBA SOWLES STEEL ERECTORS (Kyle Wilcox) |  | 44622.4902 | Item | sites/1232505342/CMiC RFI Response | 0581
21029900-0580 | Structural - CPK01-R2 - P1934 Clash with White Steel | RFI0580 - Struct - CPK01-R2 - P1934 Clash with White Steel - Resp.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | HARDER MECHANICAL CONTRACTORS INC (Kayleigh Arendt) |  | 44623.4361 | Item | sites/1232505342/CMiC RFI Response | 0580
21029900-0579 | Wet Mechanical - CPK01-R2 - HRWS-R Valve Conflict with New Steel | RFI0579-Wet Mech-CPK01-R2-HRWS-R Valve Conflict - Resp.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | HARDER MECHANICAL CONTRACTORS INC (Kayleigh Arendt) |  | 44621.7575 | Item | sites/1232505342/CMiC RFI Response | 0579
21029900-0578 | I and C- MSB1-CPK03-R2-GTW650-10-90 Panel Location | RFI-0578-I and C- MSB1-CPK03-R2-GTW650-10-90 Panel Location.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | EC ELECTRIC INC (Marcus Wikegard) |  | 44620.4957 | Item | sites/1232505342/CMiC RFI Response | 0578
21029900-0577 | Process - MSB - CPK03-R2 - EI Williams Silencers for SHPOFA | 21029900-0577 - Process - MSB - CPK03-R2 - EI Williams Silencers for SHPOFA.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | CHARTER MECHANICAL CONTRACTORS INC (Mike Tucker) |  | 44622.7585 | Item | sites/1232505342/CMiC RFI Response | 0577
21029900-0576 | Process - MSB - CPK03-R2 - Spec Gas Lateral EOL Valves | 21029900-0576 - Process - MSB - CPK03-R2 - Spec Gas Lateral EOL Valves.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | CHARTER MECHANICAL CONTRACTORS INC (Mike Tucker) |  | 44620.4309 | Item | sites/1232505342/CMiC RFI Response | 0576
21029900-0571 | CSA - MSB -CPK03-R5 IFC Roofing Details Required | RFI-0571 CSA - MSB -CPK03-R5 IFC Roofing Details Required -RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44621.3833 | Item | sites/1232505342/CMiC RFI Response | 0571
21029900-0570 | LSS - CPK03_R9- MSB1- Combo units L/51 and N57 | RFI-0570-LSS - CPK03_R9- MSB1- Combo units L51 and N57.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44620.4959 | Item | sites/1232505342/CMiC RFI Response | 0570
21029900-0569 | LSS - CPK03_R9- MSB1- duplicate addresses | RFI-0569-LSS - CPK03_R9- MSB1-duplicateaddresses.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44620.4622 | Item | sites/1232505342/CMiC RFI Response | 0569
21029900-0568 | Process - MSB - CPK03-R2 - 1/2in CK-59 Threaded Lead Time | 21029900-0568 - Process - MSB - CPK03-R2 - CK59 Threaded Lead Time.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | CHARTER MECHANICAL CONTRACTORS INC (Kellen Hearn) |  | 44622.6316 | Item | sites/1232505342/CMiC RFI Response | 0568
21029900-0566 | Process - MSB - CPK03-R2 - SWS Lateral Extension BA-30 | 21029900-0566 - Process - MSB - CPK03-R2 - SWS Lateral Extension BA-30.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | CHARTER MECHANICAL CONTRACTORS INC (Kellen Hearn) |  | 44622.7688 | Item | sites/1232505342/CMiC RFI Response | 0566
21029900-0565 | Process - MSB - CPK03-R2 - GSW,CSW Clash With Electrical Zone | 21029900-0565 - Process - MSB - CPK03-R2 - GSWCSW Clash With Electrical Zone.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | CHARTER MECHANICAL CONTRACTORS INC (Mike Tucker) |  | 44622.7688 | Item | sites/1232505342/CMiC RFI Response | 0565
21029900-0563 | LSS - CPK03_R9- MSB1-ER(clarification) | RFI-0563 LSS - CPK03_R9- MSB1-ER(clarification).pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44620.4307 | Item | sites/1232505342/CMiC RFI Response | 0563
21029900-0562 | Architectural - RA4 - CPK02-R2 - Wall type and Typical Detail Clarification | RFI-0562 Architectural - RA4 - CPK02-R2 - Wall type and Typical Detail Clarification RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | LONG PAINTING COMPANY (Kyle Hockert) |  | 44620.5254 | Item | sites/1232505342/CMiC RFI Response | 0562
21029900-0560 | Wet Mech - MSB - CPK03-R2 - TCHW Vs Seismic Brace @ Column R/55 | 21029900-0560 - Wet Mech - MSB - CPK03-R2 - TCHW Vs Seismic Brace at Column R55.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Dave Knecht) |  | 44621.4294 | Item | sites/1232505342/CMiC RFI Response | 0560
21029900-0559 | M10 Hat Fitting Substitution | RFI-0559 CSA - MSB - CPK03-R2 M10 Hat Fitting Substitution.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | PERFORMANCE CONTRACTING INC (Grayson Sorenson) |  | 44623.4142 | Item | sites/1232505342/CMiC RFI Response | 0559
21029900-0558 | Wet Mech - MSB - CPK03-R2 - MSB TCHW Submain EOL Detail Clarification | 21029900-0558 - Wet Mech - MSB - CPK03-R2 - MSB TCHW Submain EOL Detail Clarification.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Dave Knecht) |  | 44622.7691 | Item | sites/1232505342/CMiC RFI Response | 0558
21029900-0557 | Wet Mech - MSB - CPK03-R2 - TCHW Clash with Fire Protection at Column N/52 | 21029900-0557 - Wet Mech - MSB - CPK03-R2 - TCHW Clash with Fire Pipe at Column N52.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Dave Knecht) |  | 44621.4293 | Item | sites/1232505342/CMiC RFI Response | 0557
21029900-0556 | Mechanical - CPK03-R2 - MSB - New SA Duct vs. Existing Access Door | RFI0556 - Mechanical - CPK03-R2 - MSB - New SA Duct vs Access Door - Response.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | STREIMER SHEET METAL WORKS INC (Guenevere Brown) | 23311302 | 44622.5674 | Item | sites/1232505342/CMiC RFI Response | 0556
21029900-0555 | LSS - CPK03_R9- MSB1- QPS028 | RFI-0555-LSS - CPK03_R9- MSB1- QPS028.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44617.684 | Item | sites/1232505342/CMiC RFI Response | 0555
21029900-0554 | CSA-ELEC-CPK02-R2-RA4-Wall Clash Near North Stockers | RFI-0554 CSA-ELC-CPK02-R2-RA4-Wall Clash Near Stockers RESPONSE (1303332576).pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44623.5729 | Item | sites/1232505342/CMiC RFI Response | 0554
21029900-0553 | LSS - CPK03_R9- MSB1- QPS-RF0I27 | RFI-0553-LSS - CPK03_R9- MSB1- QPS-RF0I27.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44620.4618 | Item | sites/1232505342/CMiC RFI Response | 0553
21029900-0552 | DRYMECH-CPK02-R2-RA4-RA4 MAH Duct Size Change at J/10 | RFI-0552 DRYMECH-CPK02-R2-RA4-RA4 MAH Duct Size Change at J-10 RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44623.4585 | Item | sites/1232505342/CMiC RFI Response | 0552
21029900-0550 | LSS - CPK03_R9- MSB1- HF2FA(C,D)-0000 | RFI-0550 LSS - CPK03_R9- MSB1- HF2FA(CD)-0000.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44616.576 | Item | sites/1232505342/CMiC RFI Response | 0550
21029900-0549 | DRYMECH-CPK02-RA4- SA Header and East Duct Sizing Change | RFI-0549 DRYMECH-CPK02-RA4-SA Header and East Duct Sizing Change RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44623.555 | Item | sites/1232505342/CMiC RFI Response | 0549
21029900-0548 | LSS - CPK03_R9- MSB1- Horn Strobe (Clarification) | RFI-0548-LSS - CPK03_R9- MSB1- Horn Strobe (Clarification).pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44620.4628 | Item | sites/1232505342/CMiC RFI Response | 0548
21029900-0547 | LSS - CPK03_R9- MSB1- MS1-HF-2FA-C0000 | RFI-0547 LSS - CPK03_R9- MSB1- MS1-HF-2FA-C0000.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44616.5788 | Item | sites/1232505342/CMiC RFI Response | 0547
21029900-0546 | CSA - CPK03-IFC - MSB - Architectural details required | RFI-0546 - CSA - CPK03-IFC - MSB - Architectural details required -RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44620.7695 | Item | sites/1232505342/CMiC RFI Response | 0546
21029900-0545 | LSS - CPK03_R9- MSB1- Duplicate Address/Swap to Speaker | RFI-0545-LSS - CPK03_R9- MSB1- Duplicate Address and Swap to Speaker.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44620.4615 | Item | sites/1232505342/CMiC RFI Response | 0545
21029900-0544 | LSS - CPK03_R9- MSB1- FCP-1-Q57-42 | RFI-0544 LSS - CPK03_R9- MSB1- FCP-1-Q57-42.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44616.5757 | Item | sites/1232505342/CMiC RFI Response | 0544
21029900-0543 | LSS - CPK03_R9- MSB1- Request for 42-04 Low loop and HXRA | RFI-0543-LSS - CPK03_R9- MSB1- Request for 42-04 Low loop and HXRA.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44620.4308 | Item | sites/1232505342/CMiC RFI Response | 0543
21029900-0542 | Process - MSB - CPK03-R2 - SP-PVDF Highpoint Lowpoint Clarification | 21029900-0542 - Process - MSB - CPK03-R2 - SP-PVDF Highpoint Lowpoint Clarification.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | CHARTER MECHANICAL CONTRACTORS INC (David Hartshorn) |  | 44617.612 | Item | sites/1232505342/CMiC RFI Response | 0542
21029900-0541 | LSS - CPK03_R9- MSB1- FBP Panel And Circuit (Request) | RFI-0541 LSS - CPK03_R9- MSB1- FBP Panel And Circuit (Request).pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44617.7482 | Item | sites/1232505342/CMiC RFI Response | 0541
21029900-0540 | LSS - CPK03_R9- MSB1- FME-1-P51-01 | RFI-0540- LSS - CPK03_R9- MSB1- FME-1-P51-01.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44620.7695 | Item | sites/1232505342/CMiC RFI Response | 0540
21029900-0539 | CSA - MSB - CPK03-R2 Missed Ceiling Demo Scope | RFI-0539 CSA - MSB - CPK03-R2 Missed Ceiling Demo Scope.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | PERFORMANCE CONTRACTING INC (Grayson Sorenson) |  | 44621.3832 | Item | sites/1232505342/CMiC RFI Response | 0539
21029900-0537 | Electrical-CPK03 R2-MSB-Exit Light Type Confirmation | RFI-0537 Electrical-CPK03 R2-MSB-Exit Light Type Confirmation Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | QUALITY PLUS SERVICES INC (Megan Ives) | 25_50_00_00 | 44616.4981 | Item | sites/1232505342/CMiC RFI Response | 0537
21029900-0534 | Control Valves-RA4-CPK02 R2-PCZ138-0-04A P&ID Confirmation | RFI-0534 Control Valves-RA4-CPK02 R2-PCZ138-0-04A P and ID Confirmation Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40051534 | 44617.4254 | Item | sites/1232505342/CMiC RFI Response | 0534
21029900-0533 | CSA - MSB - CPK03-R8 - Updated Door Hardware Schedule and Door Hardware Specification | RFI-0533 CSA - MSB - CPK03-R8 Door hardware Schedule and Door Hardware Specification.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | PERFORMANCE CONTRACTING INC (Matthew Reinert) |  | 44620.4037 | Item | sites/1232505342/CMiC RFI Response | 0533
21029900-0532 | Mechanical - MSB - CPK03 - MAH101-7-8-00 Orientation Submittal Vs Drawing | RFI0532 - Mechanical - MSB - CPK03 - MAH101-7-8-00 Orientation Submittal Vs Drawing - Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44616.6461 | Item | sites/1232505342/CMiC RFI Response | 0532
21029900-0531 | Process - RA4 - LLE01 - Bulk Caustic Tank TK252-1-10 Nozzle B Redesign | RFI-0531 Process - RA4 - LLE01 - Bulk Caustic Tank TK252-1-10 Nozzle B Redesign RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Zachary Villarmia) |  | 44615.6744 | Item | sites/1232505342/CMiC RFI Response | 0531
21029900-0530 | Architectural - RA4 - CPK02-R4 - Paint System Clarification | RFI-0530 Architectural - RA4 - CPK02-R4 - Paint System Clarification RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | LONG PAINTING COMPANY (Kyle Hockert) |  | 44620.5252 | Item | sites/1232505342/CMiC RFI Response | 0530
21029900-0529 | LSS - CPK03_R9- MSB1- MS1B05 Lights-Demo Request | RFI-0529 LSS - CPK03_R9- MSB1- MS1B05 Lights-Demo Request.pdf | Open | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44617.7481 | Item | sites/1232505342/CMiC RFI Response | 0529
21029900-0528 | Process - MSB - CPK03-R2 - PUB1 ROP Pipe Support Detail | 21029900-0528 - Process - MSB - CPK03-R2 - PUB1 ROP Pipe Support Detail.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | CHARTER MECHANICAL CONTRACTORS INC (David Hartshorn) |  | 44620.462 | Item | sites/1232505342/CMiC RFI Response | 0528
21029900-0527 | Process - MSB - CPK03-R2 - 4in DDA Wye Dimensional Issue | 21029900-0527 - Process - MSB - CPK03-R2 - 4in DDA Wye Dimensional Issue.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | CHARTER MECHANICAL CONTRACTORS INC (Mike Tucker) |  | 44617.4772 | Item | sites/1232505342/CMiC RFI Response | 0527
21029900-0526 | Process - MSB - CPK03-R2 - AW Lateral Pipe Support Clashes | 21029900-0526 - Process - MSB - CPK03-R2 - AW Lateral Pipe Support Clashes.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | CHARTER MECHANICAL CONTRACTORS INC (Mike Tucker) |  | 44620.4614 | Item | sites/1232505342/CMiC RFI Response | 0526
21029900-0525R1 | Process - MSB - CPK03-R2 - Biocide Pumps Additional Information | 21029900-0525R1 - Process - MSB - CPK03-R2 - Biocide Pumps Additional Information.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | CHARTER MECHANICAL CONTRACTORS INC (David Hartshorn) |  | 44622.6317 | Item | sites/1232505342/CMiC RFI Response | 0525R1
21029900-0525 | Process - MSB - CPK03-R2 - Biocide Pumps Additional Information | 21029900-0525 - Process - MSB - CPK03-R2 - Biocide Pumps Additional Information.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | CHARTER MECHANICAL CONTRACTORS INC (David Hartshorn) |  | 44623.4149 | Item | sites/1232505342/CMiC RFI Response | 0525
21029900-0524 | LSS - CPK03_R9- MSB1- PS42-04-128 and ST09-01-05 Demo Request | RFI-0524-LSS - CPK03_R9- MSB1- PS42-04-128 and ST09-01-05 Demo Request.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44617.7097 | Item | sites/1232505342/CMiC RFI Response | 0524
21029900-0523 | Process - RA4 - CPK02-R2 - PDIT-EXGF Spec Clarification | RFI-0523 Process - RA4 - CPK02-R2 - PDIT-EXGF Spec Clarification RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Zachary Villarmia) |  | 44615.6742 | Item | sites/1232505342/CMiC RFI Response | 0523
21029900-0522 | LSS - CPK03_R9- MSB1- Demo (P402-06-P57) | RFI-0522-LSS - CPK03_R9- MSB1- Demo (P402-06-P57).pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | EC COMPANY (sylvia ashley) |  | 44617.708 | Item | sites/1232505342/CMiC RFI Response | 0522
21029900-0520 | Mech Process - RA4 - CPK02-R5 - TCHW Support Dimension Clarification | RFI-0520 Mech Process - RA4 - CPK02-R5 - TCHW Support Dimension Clarification RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Zachary Villarmia) |  | 44621.8301 | Item | sites/1232505342/CMiC RFI Response | 0520
21029900-0519 | Mechanical - CPK03-R2 - MSB - Streimer RFI 30 - HXRA SA/RA Duct Vs Steel Clashes | RFI-0519 - Mechanical - CPK03-R2 - MSB - Streimer RFI 30 - HXRA SARA Duct Vs Steel Clashes.pdf | Open | JACOBS ENGINEERING GROUP INC (Document Control) | STREIMER SHEET METAL WORKS INC (Guenevere Brown) | 23_31_13_02 | 44623.6252 | Item | sites/1232505342/CMiC RFI Response | 0519
21029900-0518 | Electrical-CPK03 R2-MSB Construction Receptacle Outlet Devices Confirmation | RFI-0518 Electrical-CPK03 R2-MSB Construction Receptacle Outlet Devices Confirmation Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | QUALITY PLUS SERVICES INC (Megan Ives) | 26_24_16_43 | 44623.6054 | Item | sites/1232505342/CMiC RFI Response | 0518
21029900-0517R1 | CSA - RA4 - CPK02-R2 - Column Frame Dimension Change R1 | RFI-0517R1 CSA - RA4 - CPK02-R2 - Column Frame Dimension Change RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44622.5157 | Item | sites/1232505342/CMiC RFI Response | 0517R1
21029900-0517 | CSA - RA4 - CPK02-R2 - Column Frame Dimension Change | RFI-0517 CSA - RA4 - CPK02-R2 - Column Frame Dimension Change RESPONSE.pdf | Rejected | JACOBS ENGINEERING GROUP INC (Document Control) | ADVANCED TECHNOLOGY GROUP INC (Matthew Sutherland) |  | 44620.7244 | Item | sites/1232505342/CMiC RFI Response | 0517
21029900-0516 | Electrical-CPK03 R2-MSB-MSB1-RIO650-103-04 NPS Duplicate | RFI-516 Electrical-CPK03 R2-MSB-MSB1-RIO650-103-04 NPS Duplicate Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | QUALITY PLUS SERVICES INC (Megan Ives) | 26_24_16_43 | 44617.4256 | Item | sites/1232505342/CMiC RFI Response | 0516
21029900-0512 | Mechanical - CPK03-R3 - MSB - Streimer RFI 29 - Level 5 EXSC and Relocation | RFI0512 - Mechanical - CPK03-R3 - MSB - Streimer RFI 29 - Level 5 EXSC and Relocation - Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | STREIMER SHEET METAL WORKS INC (Guenevere Brown) | 23311302 | 44622.7286 | Item | sites/1232505342/CMiC RFI Response | 0512
21029900-0511 | Process - MSB - CPK01-R2 - Harder RFI 16 - HPAR HPHe Lines Clash with South Rack | RFI0511-Process-MSB-CPK01-R2 - Harder RFI 16 - HPAR HPHe Lines Clash w Rack - Resp.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | HARDER MECHANICAL CONTRACTORS INC (Kayleigh Arendt) |  | 44621.4915 | Item | sites/1232505342/CMiC RFI Response | 0511
21029900-0510 | Mechanical - CPK01-R2 - MSB - Harder RFI 15 - EXH Duct Clash with South Rack | RFI0510 - Mech - CPK01-R2 - MSB - Harder RFI 15 - EXH Duct Clash - Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | HARDER MECHANICAL CONTRACTORS INC (Kayleigh Arendt) |  | 44622.545 | Item | sites/1232505342/CMiC RFI Response | 0510
21029900-0509 | Process - MSB - CPK01-R2 - Harder RFI 14 - K57 AW Clash with South Rack | RFI0509 - Process - MSB - CPK01-R2 - Harder RFI 14 - K57 AW Clash with South Rack.pdf | Open | JACOBS ENGINEERING GROUP INC (Document Control) | HARDER MECHANICAL CONTRACTORS INC (Kayleigh Arendt) |  | 44617.402 | Item | sites/1232505342/CMiC RFI Response | 0509
21029900-0508 | Process - RA4 - CPK02 - HRWS GA-10 Clash with TIT | RFI-0508 Process - RA4 - CPK02 - HRWS GA-10 Clash with TIT RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | HARDER MECHANICAL CONTRACTORS INC (Kayleigh Arendt) |  | 44615.6484 | Item | sites/1232505342/CMiC RFI Response | 0508
21029900-0507 | CSA - RA4 - CPK02-R2 - Existing Column Unistrut Constraint | RFI-0507 CSA - RA4 - CPK02-R2 - Existing Column Unistrut Constraint RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | ADVANCED TECHNOLOGY GROUP INC (Ned Naffakh) |  | 44616.7734 | Item | sites/1232505342/CMiC RFI Response | 0507
21029900-0505 | Wet Mechanical - CPK03-R2 - HRWS-R Valve Conflict with New Steel | RFI0505 - Wet Mechanical - CPK03-R2 - HRWS-R Valve Conflict with New Steel - Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44622.7064 | Item | sites/1232505342/CMiC RFI Response | 0505
21029900-0504 | Electrical- CPK02-RA4-Ground Size Per Code-Confirmation | RFI-0504- Electrical- CPK02-RA4-Ground Size Per Code-Confirmation.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44617.7491 | Item | sites/1232505342/CMiC RFI Response | 0504
21029900-0503 | Electrical- CPK03-Ground Size Per Code-Confirmation | RFI-0503 Electrical- CPK03-Ground Size Per Code-Confirmation.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44620.7865 | Item | sites/1232505342/CMiC RFI Response | 0503
21029900-0501 | Telecom- CPK03-R2-MSB1- Fiber Backbone Routing(175,176,177,178) | RFI-0501 Telecom- CPK03-R2-MSB1- Fiber Backbone Routing(175176177178).pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | DYNALECTRIC COMPANY (Neil Heckman) |  | 44616.6438 | Item | sites/1232505342/CMiC RFI Response | 0501
21029900-0500 | CSA - RA4 - CPK02-R4 - Containment Area CRC Clarification | RFI-0500 CSA - RA4 - CPK02-R4 - Containment Area CRC Clarification RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | LONG PAINTING COMPANY (Kyle Hockert) | 09_68_71_00 | 44623.4371 | Item | sites/1232505342/CMiC RFI Response | 0500
21029900-0499 | Structural - CPK03 - Level 2 South Strut Rack Seismic Strut Move | RFI0499 - Struc - CPK03 - Level 2 South Rack Seismic - Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44614.7608 | Item | sites/1232505342/CMiC RFI Response | 0499
21029900-0498 | DRYMECH-CPK02-RA4-MAH NET-TET Devices Qty Confirmation | RFI-0498 DRYMECH-CPK02-RA4-MAH NET-TET-Devices Qty RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44620.5568 | Item | sites/1232505342/CMiC RFI Response | 0498
21029900-0497 | Process - RA4 - CPK02-R4 - PA Valve-Branch Discrepancy - 211002-00 _ BT122 | RFI-0497 Process - RA4 - CPK02-R4 - PA Valve-Branch Discrepancy - 211002-00 _ BT122 RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Zachary Villarmia) |  | 44615.6482 | Item | sites/1232505342/CMiC RFI Response | 0497
21029900-0496 | Process - RA4 - CPK02-R4 - HPO2 Valve-Branch Discrepancy 412002-00 _ BT118 | RFI-0496 Process - RA4 - CPK02-R4 - HPO2 Valve-Branch Discrepancy 412002-00 _ BT118 RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Zachary Villarmia) |  | 44615.6487 | Item | sites/1232505342/CMiC RFI Response | 0496
21029900-0495 | Structural - RA4 - CPK02-R2 - Missing (e) WF beams-f | RFI-0495 Structural - RA4 - CPK02-R2 - Missing (e) WF beams-f RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | SOWLES CO DBA SOWLES STEEL ERECTORS (Kyle Wilcox) |  | 44614.4742 | Item | sites/1232505342/CMiC RFI Response | 0495
21029900-0493 | Process - RA4 - CPK02-R4 - PA Clash with Wall and Ped Legs_BT112 | RFI-0493 Process - RA4 - CPK02-R4 - PA Clash with Wall and Ped Legs_BT112 RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Zachary Villarmia) |  | 44617.8174 | Item | sites/1232505342/CMiC RFI Response | 0493
21029900-0492 | MECH-CPK02-R4-Link8 Equipment ID Tags Inconsistency SOO and MEL for PDIT131-0-10 A, B, C | RFI-0492-MECH-CPK02-R4-Link8 Equip.ID Tags Inconsistency SOO and MEL for PDIT131-0-10ABC RESP.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn | 1261 SSO-XX -RA4 | 44615.8149 | Item | sites/1232505342/CMiC RFI Response | 0492
21029900-0491 | Process - RA4 - CPK02-R4 - KN-19 on RA4-252-D0-A01 Clarification | RFI-0491 Process - RA4 - CPK02-R4 - KN-19 on RA4-252-D0-A01 Clarification RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Zachary Villarmia) |  | 44615.6486 | Item | sites/1232505342/CMiC RFI Response | 0491
21029900-0490 | Process - RA4 - CPK02-R4 - EOL Lateral Loops Not Shown | RFI-0490 Process - RA4 - CPK02-R4 - EOL Lateral Loops Not Shown RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Zachary Villarmia) |  | 44615.618 | Item | sites/1232505342/CMiC RFI Response | 0490
21029900-0489 | Wet Mech - MSB - CPK03-R2 - TCHWSR Clash with Existing Anti-Foam Lines | 21029900-0489 - Wet Mech - MSB - CPK03-R2 - TCHWSR Clash with Existing Anti-Foam Lines.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Dave Knecht) |  | 44613.5169 | Item | sites/1232505342/CMiC RFI Response | 0489
21029900-0488 | Wet Mech - MSB - CPK03-R2 - Straight Length Requirements | 21029900-0488 - Wet Mech - MSB - CPK03-R2 - Straight Length Requirements.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Dave Knecht) |  | 44613.728 | Item | sites/1232505342/CMiC RFI Response | 0488
21029900-0487 | Process - RA4 - CPK02-R4 - RODI End of Line Issues BT176 | RFI-0487 Process - RA4 - CPK02-R4 - RODI End of Line Issues BT176 RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Zachary Villarmia) |  | 44616.8484 | Item | sites/1232505342/CMiC RFI Response | 0487
21029900-0485 | Wet Mech - MSB - CPK03-R8- Upsize of HSS for CUB4 Pipe Supports | 21029900-0485 - Wet Mech - MSB - CPK03-R8- Upsize of HSS for CUB4 Pipe Supports.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Dave Knecht) |  | 44622.768 | Item | sites/1232505342/CMiC RFI Response | 0485
21029900-0484 | Process - RA4 - CPK02-R4 - DM Clash with Process vs Existing (BT58) | RFI-0484 Process - RA4 - CPK02-R4 - DM Clash with Process vs Existing (BT58) RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Zachary Villarmia) |  | 44615.5741 | Item | sites/1232505342/CMiC RFI Response | 0484
21029900-0483 | Process - RA4 - CPK02-R4 - SHCWS/R High Point Vent Clarification | RFI-0483 Process - RA4 - CPK02-R4 - SHCWS-R High Point Vent Clarification RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Zachary Villarmia) |  | 44615.6178 | Item | sites/1232505342/CMiC RFI Response | 0483
21029900-0482 | Process - PUB1 - CPK02-R2 - OFA Dryer Skid Clarification | RFI-0482 Process - PUB1 - CPK02-R2 - OFA Dryer Skid Clarification RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Zachary Villarmia) |  | 44615.6176 | Item | sites/1232505342/CMiC RFI Response | 0482
21029900-0481 | Process - RA4 - CPK02-R4 - CHCO2DI End of Lateral DM Discrepancy | RFI-0481 Process - RA4 - CPK02-R4 - CHCO2DI End of Lateral DM Discrepancy RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Zachary Villarmia) |  | 44616.8484 | Item | sites/1232505342/CMiC RFI Response | 0481
21029900-0480 | Process - RA4 - CPK02-R4 - UN2 DM Branch Question - 409001-00 | RFI-0480 Process - RA4 - CPK02-R4 - UN2 DM Branch Question - 409001-00 RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Zachary Villarmia) |  | 44615.5943 | Item | sites/1232505342/CMiC RFI Response | 0480
21029900-0479 | Mechanical - CPK03-R3 - Streimer RFI 28 - Level 2FA Missing Detail Ref Orb | RFI0479-Mech-CPK03-R3-Streimer RFI 28 - L2 FA Missing Det- Resp.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | STREIMER SHEET METAL WORKS INC (Guenevere Brown) | 23821661 | 44621.5208 | Item | sites/1232505342/CMiC RFI Response | 0479
21029900-0478 | Process - RA4 - CPK02-R2 - TCHW to RA4-CC102-01_02_03_04-20 Design Model Issues_BT154_B158 | RFI-0478 Process - RA4 - CPK02-R2 - TCHW Design Model Issues_BT154_B158 RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Zachary Villarmia) |  | 44615.5941 | Item | sites/1232505342/CMiC RFI Response | 0478
21029900-0477 | Process - RA4 - CPK02-R2 - TCHW to RA4-RAH102-05_06_07_08-10 Design Model Issues | RFI-0477 Process - RA4 - CPK02-R2 - TCHW Design Model Issues RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Zachary Villarmia) |  | 44615.594 | Item | sites/1232505342/CMiC RFI Response | 0477
21029900-0476 | Process - RA4 - CPK02-R2 - TCHW to RA4-RAH102-14_15_16-10 Design Model Issues | RFI-0476 Process - RA4 - CPK02-R2 - TCHW Design Model Issues RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Zachary Villarmia) |  | 44616.8215 | Item | sites/1232505342/CMiC RFI Response | 0476
21029900-0475 | Process - RA4 - CPK02-R4 - TCHW to RA4-CC102-05_06_07_08-20 Design Model Issues_BT151 | RFI-0475 Process - RA4 - CPK02-R4 - TCHW Design Model Issues_BT151 RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Zachary Villarmia) |  | 44615.5939 | Item | sites/1232505342/CMiC RFI Response | 0475
21029900-0474 | I&C- MSB1/RA4-CPK03-R2- Profibus Couplers | RFI-0474 -I AND C- MSB1_RA4-CPK03-R2- Profibus Couplers.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44622.7069 | Item | sites/1232505342/CMiC RFI Response | 0474
21029900-0473 | Mechanical - CPK03 - MSB - Southland RFI 5 - L2 Duct and Immovable Waste Drain Clash | RFI0473 - Mech - CPK03 - Southland RFI 5 - L2 Duct and Drain Clash - Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | TEMP-CONTROL MECHANICAL CORPORATION (Tyler Birdsey) |  | 44614.7605 | Item | sites/1232505342/CMiC RFI Response | 0473
21029900-0472 | Process - RA4 - CPK02-R2 - RCRA Matrix for MSW-GSW Relabel Scope | RFI-0472 Process - RA4 - CPK02-R2 - RCRA Matrix for MSW-GSW Relabel Scope RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Zachary Villarmia) |  | 44616.835 | Item | sites/1232505342/CMiC RFI Response | 0472
21029900-0470 | Dry Mech-CPK03-R2-MSB - Exhaust Fan Spare Bearings | 21029900-0470 - Dry Mech-CPK03-R2-MSB - Exhaust Fan Spare Bearings.pdf | Answered - Complete | INTEL NETWORK SYSTEMS INC (Chris Van Zee) | JE Dunn |  | 44609.5151 | Item | sites/1232505342/CMiC RFI Response | 0470
21029900-0469 | Process - RA4 - CPK02-R4 - CHCO2DIS-R Size Discrepancy (Lines 249009-00, 249008-00) | RFI-0469 Process - RA4 - CPK02-R4 - CHCO2DIS-R Size Discrepancy RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Zachary Villarmia) |  | 44616.8349 | Item | sites/1232505342/CMiC RFI Response | 0469
21029900-0467 | MECH-CPK02-RA4-CLEANROOM MAKEUP AIR-AIR HANDLER PRESSURIZATION SYSTEM P&ID Notes Updates | RFI-0467 CPK02-MECH-CLEANROOM MAKEUP AIR-AIR HANDLER PRESSURIZATION SYSTEM PnID NotesRESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44616.7263 | Item | sites/1232505342/CMiC RFI Response | 0467
21029900-0466 | I&C - CPK02-R2 - RA4 Instrumentation Tag Discrepancies | RFI-0466 I and C - CPK02-R2 - RA4 Instrumentation Tag Discrepancies RESPONSE.pdf | Answered - Complete | OEG INC (Ryan Pfeifer) |  |  | 44623.5388 | Item | sites/1232505342/CMiC RFI Response | 0466
21029900-0465 | Structural - RA4 - CPK02-R2 - Framing Details at GL K-13.5 | RFI-0465 Structural - RA4 - CPK02-R2 - Framing Details at GL K-13.5 RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | ADVANCED TECHNOLOGY GROUP INC (Ned Naffakh) |  | 44615.5175 | Item | sites/1232505342/CMiC RFI Response | 0465
21029900-0464 | Process - RA4 - CPK02-R4 - RODI RTD Flush Style Eccentric Reducers | RFI-0464 Process - RA4 - CPK02-R4 - RODI RTD Flush Style Eccentric Reducers RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Zachary Villarmia) |  | 44615.5938 | Item | sites/1232505342/CMiC RFI Response | 0464
21029900-0463 | Process - MSB - CPK03-R2 - Charter RFI#174 CPCW Supports | 21029900-0463 - Process - MSB - CPK03-R2 - Charter RFI174 CPCW Supports.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | CHARTER MECHANICAL CONTRACTORS INC (Mike Tucker) |  | 44614.7098 | Item | sites/1232505342/CMiC RFI Response | 0463
21029900-0462 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#127 POC Count Discrepancy | 21029900-0462 - Wet Mech - MSB - CPK03-R2 - BMWC RFI127 POC Count Discrepancy.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Dave Knecht) |  | 44613.4955 | Item | sites/1232505342/CMiC RFI Response | 0462
21029900-0461 | Structural - CPK02 - RA4 - RR Washer Clarification | RFI-0461 Structural - CPK02 - RA4 - RR Washer Clarification RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | ADVANCED TECHNOLOGY GROUP INC (Matthew Sutherland) |  | 44614.4758 | Item | sites/1232505342/CMiC RFI Response | 0461
21029900-0460 | CSA - RA4 - CPK02 - Compression Post Clarification | RFI-0460 CSA - RA4 - CPK02 - Compression Post Clarification RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | ADVANCED TECHNOLOGY GROUP INC (Matthew Sutherland) |  | 44623.4149 | Item | sites/1232505342/CMiC RFI Response | 0460
21029900-0459 | I and C-CPK03-R2- MSB1- Missing MSB1-TCV102-31-22A | RFI-0459-I and C-CPK03-R2- MSB1- Missing MSB1-TCV102-31-22A.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44609.7856 | Item | sites/1232505342/CMiC RFI Response | 0459
21029900-0457 | I and C-CPK03-R2- MSB1-Magnetrol Switch Probe Length | RFI-0457-I and C-CPK03-R2- MSB1-Magnetrol Switch Probe Length.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44614.4151 | Item | sites/1232505342/CMiC RFI Response | 0457
21029900-0456 | Wet Mech - MSB - CPK03-R2 - TCHW Conflict with Fire Protection Piping at P/56, R/54, R/56 | 21029900-0456 - Wet Mech - MSB - CPK03-R2 - TCHW Conflict with Fire Piping at P56 R54 R56.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Dave Knecht) |  | 44620.4609 | Item | sites/1232505342/CMiC RFI Response | 0456
21029900-0455 | Wet Mech - MSB - CPK03-R2 - CHW Conflict with Fire Protection at Column M/51 | 21029900-0455 - Wet Mech - MSB - CPK03-R2 - CHW Conflict with Fire Protection at Column M51.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Dave Knecht) |  | 44622.602 | Item | sites/1232505342/CMiC RFI Response | 0455
21029900-0454 | Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Protection Piping BT/47, BT/55, BT/56 | 21029900-0454 - Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Piping BT47 BT55 BT56.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Dave Knecht) |  | 44616.5761 | Item | sites/1232505342/CMiC RFI Response | 0454
21029900-0453 | Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Protection Piping BT/42, BT/43, BT/45 | 21029900-0453 - Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Piping BT42 BT43 BT45.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Dave Knecht) |  | 44622.6014 | Item | sites/1232505342/CMiC RFI Response | 0453
21029900-0452 | Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Protection Piping BT/39, BT/40, BT/41 | 21029900-0452 - Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Piping BT39 BT40 BT41.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Dave Knecht) |  | 44613.6545 | Item | sites/1232505342/CMiC RFI Response | 0452
21029900-0451 | Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Protection Piping BT/34, BT/35, BT/36 | 21029900-0451 - Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Piping BT34 BT35 BT36.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Dave Knecht) |  | 44614.4734 | Item | sites/1232505342/CMiC RFI Response | 0451
21029900-0450 | Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Protection Piping BT31, BT32, BT33 | 21029900-0450 - Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Piping BT31 BT32 BT33.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Dave Knecht) |  | 44613.5163 | Item | sites/1232505342/CMiC RFI Response | 0450
21029900-0449 | Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Protection Piping BT/19, BT/20, BT/21 | 21029900-0449 - Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Piping BT19 BT20 BT21.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Dave Knecht) |  | 44613.5168 | Item | sites/1232505342/CMiC RFI Response | 0449
21029900-0448 | Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Protection Piping BT/7, BT/12, BT/18 | 21029900-0448 - Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Piping BT7 BT12 BT18.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Dave Knecht) |  | 44620.4627 | Item | sites/1232505342/CMiC RFI Response | 0448
21029900-0447 | Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Protection Piping BT/22, BT/23, BT/24 | 21029900-0447 - Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Piping BT22 BT23 BT24.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Dave Knecht) |  | 44614.7099 | Item | sites/1232505342/CMiC RFI Response | 0447
21029900-0446 | Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Protection Piping BT/25, BT/26, BT/27 | 21029900-0446 - Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Piping BT25 BT26 BT27.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Dave Knecht) |  | 44613.5177 | Item | sites/1232505342/CMiC RFI Response | 0446
21029900-0445 | Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Protection Piping BT/28, BT/29, BT/30, BT/50 | 21029900-0445 - Wet Mech - MSB - CPK03-R2 - TCHW Conflict Fire Piping BT28 BT29 BT30 BT50.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | BMWC CONSTRUCTORS INC (Dave Knecht) |  | 44613.4946 | Item | sites/1232505342/CMiC RFI Response | 0445
21029900-0444 | Structural - MSB - CPK03-R10 - Strut Rack Detail Changes | RFI-444 - Structural - MSB - CPK03-R10 - Strut Rack Detail Changes- RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | SOWLES CO DBA SOWLES STEEL ERECTORS (Kyle Wilcox) |  | 44616.6453 | Item | sites/1232505342/CMiC RFI Response | 0444
21029900-0443 | Telecom- CPK02-R4-RA4-SCR 422 Termination | RFI-0443 Telecom- CPK02-R4-RA4-SCR 422 Termination.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44613.5543 | Item | sites/1232505342/CMiC RFI Response | 0443
21029900-0442 | Process - MSB - CPK03-R2 - Charter RFI#172 UPWS Offset Clashing Steel | 21029900-0442 - Process - MSB - CPK03-R2 - Charter RFI172 UPWS Offset Clashing Steel.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | CHARTER MECHANICAL CONTRACTORS INC (Mike Tucker) |  | 44620.5583 | Item | sites/1232505342/CMiC RFI Response | 0442
21029900-0441 | Process - MSB - CPK03-R2 - Charter RFI#170 PV Piping Spec Discrepancy | 21029900-0441 - Process - MSB - CPK03-R2 - Charter RFI170 PV Piping Spec Discrepancy.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | CHARTER MECHANICAL CONTRACTORS INC (Mike Tucker) |  | 44620.562 | Item | sites/1232505342/CMiC RFI Response | 0441
21029900-0440 | Process - MSB - CPK03-R2 - Charter RFI#169 JEB Spec CPCW Lines | 21029900-0440 - Process - MSB - CPK03-R2 - Charter RFI169 JEB Spec CPCW Lines.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | CHARTER MECHANICAL CONTRACTORS INC (Mike Tucker) |  | 44620.5632 | Item | sites/1232505342/CMiC RFI Response | 0440
21029900-0439R1 | DRYMECH-CSA-CPK02-South Exterior MA Penetration Vs Steel | RFI-0439R1 DRYMECH-CSA-CPK02-South Exterior MA Penetration Vs Steel RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | STREIMER SHEET METAL WORKS INC (Guenevere Brown) | 23311301 | 44622.7687 | Item | sites/1232505342/CMiC RFI Response | 0439R1
21029900-0438 | Mechanical - CPK03-R2 - Streimer RFI 19 - 1SA EXVO Route Deviation and Zone Conflict | RFI0438 - Mech - CPK03-R2- Streimer 19 - 1SA EXVO Route Deviation - Response.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 23311302 | 44622.5728 | Item | sites/1232505342/CMiC RFI Response | 0438
21029900-0437 | Mechanical - CPK03-R2 - Streimer RFI 20 - HXRA Rectangular Clash | RFI0437 - Mechanical - CPK03-R2 - Streimer RFI 20 - HXRA Rectangular Clash - Response.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 23311302 | 44622.5729 | Item | sites/1232505342/CMiC RFI Response | 0437
21029900-0436 | Mechanical - CPK03-R2 - Streimer RFI 26 - EXSC Drain Duct Slope vs Steel Clash | RFI-0436 - Mechanical - MSB - CPK03-R2 - Streimer RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | STREIMER SHEET METAL WORKS INC (Guenevere Brown) | 23311302 | 44622.5688 | Item | sites/1232505342/CMiC RFI Response | 0436
21029900-0435 | Structural - RA4 - CPK02-R2 Beam Conflicts with (E) Wall | RFI-435 - Structural - RA4 - CPK02-R2 Beam Conflicts with (E) Wall-RESPONSE.pdf | Void | JACOBS ENGINEERING GROUP INC (Document Control) | SOWLES CO DBA SOWLES STEEL ERECTORS (Kyle Wilcox) |  | 44621.5062 | Item | sites/1232505342/CMiC RFI Response | 0435
21029900-0434 | Multi - MSB - CPK03-R2 - LIT133 tags | RFI0434 - Multi - MSB - CPK03-R2 - LIT133 Tags.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn | MS1-133-D0-A06 | 44616.6932 | Item | sites/1232505342/CMiC RFI Response | 0434
21029900-0433 | CSA - RA4 - CPK02-R2 - Beam Conflicts with E wall | RFI-0433 - CSA - RA4 - CPK02-R2 - Beam Conflicts with E wall RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | SOWLES CO DBA SOWLES STEEL ERECTORS (Kyle Wilcox) |  | 44614.4152 | Item | sites/1232505342/CMiC RFI Response | 0433
21029900-0431 | Wet Mech - RA4 - CPK02-R4 - MEL PID inst tags do not match for 135 VFD | RFI0431 - Wet Mech - RA4 - CPK02-R4 - MEL PID inst tags do not match for 135 VFD - Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn | RA4-135-D0-A02 | 44613.4674 | Item | sites/1232505342/CMiC RFI Response | 0431
21029900-0430 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#121 Missing Plumbing Detail | 21029900-0430 - Wet Mech - MSB - CPK03-R2 - BMWC RFI121 Missing Plumbing Detail.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44620.5584 | Item | sites/1232505342/CMiC RFI Response | 0430
21029900-0429 | Wet Mech - MSB - CPK03-R9 - Safety Shower Relocation with Scope Deletion | 21029900-0429 - Wet Mech - MSB - CPK03-R9 - Safety Shower Relocation with Scope Deletion.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44620.5641 | Item | sites/1232505342/CMiC RFI Response | 0429
21029900-0428 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#115 Safety Shower Spec Revision | 21029900-0428 - Wet Mech - MSB - CPK03-R2 - BMWC RFI115 Safety Shower Spec Revision.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 22_40_00_00 | 44613.6733 | Item | sites/1232505342/CMiC RFI Response | 0428
21029900-0427 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#114 BA-4s on ADB Spec | 21029900-0427 - Wet Mech - MSB - CPK03-R2 - BMWC RFI114 BA-4s on ADB Spec.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40_05_15_31 | 44615.835 | Item | sites/1232505342/CMiC RFI Response | 0427
21029900-0426 | Process - MSB - CPK03-R2 - Charter RFI#168 Spare Lateral in Bay 52N1S-S | 21029900-0426 - Process - MSB - CPK03-R2 - Charter RFI168 Spare Lateral in Bay 52N1S-S.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44620.5619 | Item | sites/1232505342/CMiC RFI Response | 0426
21029900-0425 | Process - MSB - CPK03-R2 - Charter RFI#167 H2N2 GL-78 Size Not Matching | 21029900-0425 - Process - MSB - CPK03-R2 - Charter RFI167 H2N2 GL-78 Size Not Matching.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44620.5589 | Item | sites/1232505342/CMiC RFI Response | 0425
21029900-0424 | Process - MSB - CPK03-R2 - Charter RFI#166 AWN Air Gap Height | 21029900-0424 - Process - MSB - CPK03-R2 - Charter RFI166 AWN Air Gap Height.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44622.6019 | Item | sites/1232505342/CMiC RFI Response | 0424
21029900-0423 | Process - MSB - CPK03-R2 - Charter RFI#165 CPCW Valve Not on P and ID | 21029900-0423 - Process - MSB - CPK03-R2 - Charter RFI165 CPCW Valve Not on P and ID.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44620.5276 | Item | sites/1232505342/CMiC RFI Response | 0423
21029900-0421 | Mechanical - CPK03-R2 - Streimer RFI 25 - L1 Missing Fire Damper in 12" SA | RFI0421 - CPK03-R2 - Streimer RFI 25 - L1 Missing Fire Damper in 12 in SA - Response.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 23311302 | 44622.5697 | Item | sites/1232505342/CMiC RFI Response | 0421
21029900-0420 | Structural - RA4 - CPK02-R2 - Spliced Rod Drops | RFI-0420 - Structural - RA4 - CPK02-R2 - Spliced Rod Drops RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | ADVANCED TECHNOLOGY GROUP INC (Matthew Sutherland) |  | 44616.4956 | Item | sites/1232505342/CMiC RFI Response | 0420
21029900-0419 | Structural - RA4 - CPK02-R2 - TCHW Inertia Pad Clarifications | RFI-0419 - Structural - RA4 - CPK02-R2 - TCHW Inertia Pad Clarifications RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44620.5607 | Item | sites/1232505342/CMiC RFI Response | 0419
21029900-0418 | CSA - MSB - CPK03-R2 - Southeast MSB Pipe Support | RFI-0418 CSA - MSB - CPK03-R2 - Southeast MSB Pipe Support.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JACOBS ENGINEERING GROUP INC (Roger Chen) |  | 44614.6755 | Item | sites/1232505342/CMiC RFI Response | 0418
21029900-0417 | Structural - PUB1 - CPK02-R2 - Concrete Pad Details | RFI-0417 - Structural - RA4 - CPK02-R2 - PUB1 Concrete Pad Details RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44615.7956 | Item | sites/1232505342/CMiC RFI Response | 0417
21029900-0416 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#019 CHWSR Loop EOL Valve | 21029900-0416 - Wet Mech - MSB - CPK03-R2 - BMWC RFI019 CHWSR Loop EOL Valve.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44615.8334 | Item | sites/1232505342/CMiC RFI Response | 0416
21029900-0415 | Mechanical - MSB1 - CPK03-R2 - Shift FFU on Level 2 Fab C4 at grid L-11 | RFI0415 - Mechanical - CPK03-R2 - Shift FFU on Level 2 Fab C4 at grid L-11 - Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JACOBS ENGINEERING GROUP INC (Gage Kehler) |  | 44609.7163 | Item | sites/1232505342/CMiC RFI Response | 0415
21029900-0414 | Mechanical - CPK03-R2 - Fan Coil Unit Specifications | RFI0414 - Mechanical - CPK03-R2 - Fan Coil Unit Specifications - Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn | 23821900 | 44622.4162 | Item | sites/1232505342/CMiC RFI Response | 0414
21029900-0412 | Mechanical - CPK03-R3 - Dry Cooling Coil Data Sheet Corrections | RFI0412 - Mechanical - CPK03-R3 - Dry Cooling Coil Data Sheet Corrections - Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44613.3994 | Item | sites/1232505342/CMiC RFI Response | 0412
21029900-0411 | Process - MSB - CPK03-R2 - Charter - GL-18 Substitution Request | RFI0411 - Process - CPK03-R2 - Charter - GL-18 Substitution Request - Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40051531 | 44615.8322 | Item | sites/1232505342/CMiC RFI Response | 0411
21029900-0410R1 | Process - MSB - CPK03-R2 - Charter - BF-34 Substitution Request | RFI0410R1 - Process - MSB - CPK03-R2 - Charter - BF-34 Sub Req - Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | CHARTER MECHANICAL CONTRACTORS INC (Mike Tucker) | 40051531 | 44622.7066 | Item | sites/1232505342/CMiC RFI Response | 0410R1
21029900-0410 | Process - MSB - CPK03-R2 - Charter - BF-34 Substitution Request | RFI0410 - MSB - CPK03-R2 - Charter - BF-34 Substitution Request - Response.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40051531 | 44622.5442 | Item | sites/1232505342/CMiC RFI Response | 0410
21029900-0409 | Mechanical - MSB1 - CPK03-R3 - EXSC Ductwork issue at AC line | RFI0409 - Mechanical - MSB1 - CPK03-R3 - EXSC Ductwork issue at AC line.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | AC line v U line | 44607.7343 | Item | sites/1232505342/CMiC RFI Response | 0409
21029900-0408 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#111 Missing IA Source for TCVs | 21029900-0408 - Wet Mech - MSB - CPK03-R2 - BMWC RFI111 Missing IA Source for TCVs.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44615.834 | Item | sites/1232505342/CMiC RFI Response | 0408
21029900-0407 | Electrical- CPK03-R2 Subfab Light Mounting on North Side of Steel | RFI-0407-Electrical- CPK03-R2 Subfab Light Mounting on North Side of Steel.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44620.8037 | Item | sites/1232505342/CMiC RFI Response | 0407
21029900-0406 | CSA - CPK02-R2 - Structural Infill Clarification | RFI-0406 - CSA - CPK02-R2 - Structural Infill Clarification RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44613.3985 | Item | sites/1232505342/CMiC RFI Response | 0406
21029900-0405 | Process - MSB - CPK03-R9 - Charter RFI#164 BEA Content Above Ceiling | 21029900-0405 - Process - MSB - CPK03-R9 - Charter RFI164 BEA Content Above Ceiling.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | CHARTER MECHANICAL CONTRACTORS INC (David Hartshorn) |  | 44622.571 | Item | sites/1232505342/CMiC RFI Response | 0405
21029900-0404 | Process - MSB - CPK03-R2 - Charter RFI#162 HPN2 Deviations from DM | 21029900-0404 - Process - MSB - CPK03-R2 - Charter RFI162 HPN2 Deviations from DM.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44614.63 | Item | sites/1232505342/CMiC RFI Response | 0404
21029900-0403 | Process - MSB - CPK03-R2 - Charter RFI#161 CHCO2DI QSP Valve and Keynote | 21029900-0403 - Process - MSB - CPK03-R2 - Charter RFI161 CHCO2DI QSP Valve and Keynote.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44616.8217 | Item | sites/1232505342/CMiC RFI Response | 0403
21029900-0402R1 | Process - MSB - CPK03-R2 - Charter RFI#160 SHCW Branches Model and Keynotes- R1 | 21029900-0402R1 - Process - MSB - CPK03-R2 - Charter RFI160 SHCW Branches Model Keynotes- R1.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | CHARTER MECHANICAL CONTRACTORS INC (Mike Tucker) |  | 44620.4302 | Item | sites/1232505342/CMiC RFI Response | 0402R1
21029900-0402 | Process - MSB - CPK03-R2 - Charter RFI#160 SHCW Branches Model and Keynotes | 21029900-0402 - Process - MSB - CPK03-R2 - Charter RFI160 SHCW Branches Model and Keynotes.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44616.8051 | Item | sites/1232505342/CMiC RFI Response | 0402
21029900-0401 | Telecom- CPK03-R2-MSB1-CCH-CP24-A9 288 Strand Request | RFI-0401 Telecom- CPK03-R2-MSB1-CCH-CP24-A9 288 Strand Request.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44616.8046 | Item | sites/1232505342/CMiC RFI Response | 0401
21029900-0400 | Mechanical - CPK03-R2/R3 - Streimer RFI 24 - FAB Level Coil Discrepancies | RFI0400 - Mechanical - CPK03-R2R3 - Streimer RFI 24 - FAB Level Coil Discrepancies - Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 23821661 | 44607.3582 | Item | sites/1232505342/CMiC RFI Response | 0400
21029900-0399 | Mechanical - CPK03-R2 - Streimer RFI 23 - EXGB Fan vs GRD CFM | RFI0399 - Mechanical - CPK03-R2 - Streimer RFI 23 - EXGB Fan vs GRD CFM - Response.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 23311301 | 44622.5723 | Item | sites/1232505342/CMiC RFI Response | 0399
21029900-0398 | Process - MSB - CPK03-R2 - Charter RFI#159 OFA Lateral Reduction Missing in DM | 21029900-0398 - Process - MSB - CPK03-R2 - Charter RFI159 OFA Lateral Reduction Missing in DM.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44614.594 | Item | sites/1232505342/CMiC RFI Response | 0398
21029900-0397 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#089 End of Lateral DPIT | 21029900-0397 - Wet Mech - MSB - CPK03-R2 - BMWC RFI089 End of Lateral DPIT.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40_90_14_00 | 44620.5265 | Item | sites/1232505342/CMiC RFI Response | 0397
21029900-0396 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#095 DPIT Valve Redundancy Clarification | 21029900-0396 - Wet Mech - MSB - CPK03-R2 - BMWC RFI095 DPIT Valve Redundancy Clarification.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44609.479 | Item | sites/1232505342/CMiC RFI Response | 0396
21029900-0395 | Wet Mech - MSB - CPK03-R2 - BMWCRFI#093 KEE Fitting Confirmation | 21029900-0395 - Wet Mech - MSB - CPK03-R2 - BMWCRFI093 KEE Fitting Confirmation.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40_05_16_32 | 44613.7261 | Item | sites/1232505342/CMiC RFI Response | 0395
21029900-0394 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#092 General Process Exhaust Port Clarification | 21029900-0394 - Wet Mech - MSB - CPK03-R2 - BMWC RFI092 General Process Port Clarification.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44614.5924 | Item | sites/1232505342/CMiC RFI Response | 0394
21029900-0393 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#091 Lateral Sample Detail Conflicts KEE Spec | 21029900-0393 - Wet Mech - MSB - CPK03-R2 - BMWC RFI091 Lateral Sample Conflicts KEE Spec.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40_05_16_32 | 44614.5524 | Item | sites/1232505342/CMiC RFI Response | 0393
21029900-0392 | Wet Mech - MSB - CPK03-R2 - BMWCRFI#090 Air Exhaust Port Clarification | 21029900-0392 - Wet Mech - MSB - CPK03-R2 - BMWCRFI090 Air Exhaust Port Clarification.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44622.5722 | Item | sites/1232505342/CMiC RFI Response | 0392
21029900-0391 | Wet Mech - MSB - CPK03-R2 - BMWC RFI088 DPIT Spec Clarification | 21029900-0391 - Wet Mech - MSB - CPK03-R2 - BMWC RFI088 DPIT Spec Clarification.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40_05_15_31 | 44616.8049 | Item | sites/1232505342/CMiC RFI Response | 0391
21029900-0390 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#101 CHW Conflict with Cable Tray | 21029900-0390 - Wet Mech - MSB - CPK03-R2 - BMWC RFI101 CHW Conflict with Cable Tray.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44613.7278 | Item | sites/1232505342/CMiC RFI Response | 0390
21029900-0389 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#099 Line Numbering Discrepancy | 21029900-0389 - Wet Mech - MSB - CPK03-R2 - BMWC RFI099 Line Numbering Discrepancy.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44620.5591 | Item | sites/1232505342/CMiC RFI Response | 0389
21029900-0388 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#098 CHWSR Clash with Door | 21029900-0388 - Wet Mech - MSB - CPK03-R2 - BMWC RFI098 CHWSR Clash with Door.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44613.725 | Item | sites/1232505342/CMiC RFI Response | 0388
21029900-0387 | CSA - MSB - CPK03-R3 - M16 & M10 Rod Drops @ Strut Embed Alternate #2 | RFI-0387 CSA.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | PERFORMANCE CONTRACTING INC (Matthew Reinert) |  | 44615.8141 | Item | sites/1232505342/CMiC RFI Response | 0387
21029900-0386 | Wet Mech - MSB - CPK03-R2 - BMWC RFI097 CHWSR In Egress Zone | 21029900-0386 - Wet Mech - MSB - CPK03-R2 - BMWC RFI097 CHWSR In Egress Zone.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44613.7286 | Item | sites/1232505342/CMiC RFI Response | 0386
21029900-0385R1 | CSA - MSB - CPK03-R8 - Door Schedule Clarifications | RFI-0385 CSA - MSB - CPK03-R8 Door Schedule Clarifications.pdf | Open | JACOBS ENGINEERING GROUP INC (Document Control) | PERFORMANCE CONTRACTING INC (Grayson Sorenson) |  | 44620.4658 | Item | sites/1232505342/CMiC RFI Response | 0385R1
21029900-0384 | Electrical MSB LLE01 - OIT Equipment Tag Change Confirmation | RFI-00304 Electrical MSB LLE01 - OIT Equipment Tag Change Confirmation.pdf | Open | JACOBS ENGINEERING GROUP INC (Document Control) |  | D-I-1910_08 | 44601.7433 | Item | sites/1232505342/CMiC RFI Response | 0384
21029900-0383 | Process - MSB - CPK03-R2 - Charter RFI#156 CO2 Laterals Not Matching Drawing | 21029900-0383 - Process - MSB - CPK03-R2 - Charter RFI156 CO2 Laterals Not Matching Drawing.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44614.5945 | Item | sites/1232505342/CMiC RFI Response | 0383
21029900-0382 | Process - MSB - CPK03-R2 - Charter RFI#155 AWN Various Issues | 21029900-0382 - Process - MSB - CPK03-R2 - Charter RFI155 AWN Various Issues.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44615.8134 | Item | sites/1232505342/CMiC RFI Response | 0382
21029900-0381 | Process - MSB - CPK03-R2 - Charter RFI#050.1 UPW Lateral Follow Up | 21029900-0381 - Process - MSB - CPK03-R2 - Charter RFI050.1 UPW Lateral Follow Up.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44613.7232 | Item | sites/1232505342/CMiC RFI Response | 0381
21029900-0380R1 | MSB - CPK03-R3 - Door MS1B07A Wall Type | RFI-0380 CSA - MSB - CPK03-R3 Door MS1B07A Wall Type.pdf | Open | JACOBS ENGINEERING GROUP INC (Document Control) | PERFORMANCE CONTRACTING INC (Grayson Sorenson) |  | 44620.4655 | Item | sites/1232505342/CMiC RFI Response | 0380R1
21029900-0379 | Electrical- CPK03-R2 ECR Confirm Circuits | RFI-0379 Electrical- CPK03-R2 ECR Confirm Circuits.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44615.8146 | Item | sites/1232505342/CMiC RFI Response | 0379
21029900-0378 | Electrical- CPK03-R2 ECR VFD147-2-00 and VFD147-4-00 Clarifications | RFI-0378 Electrical- Electrical- CPK03-R2 ECR VFD147-2-00 and VFD147-4-00 Clarifications.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44610.7522 | Item | sites/1232505342/CMiC RFI Response | 0378
21029900-0377 | Electrical- CPK03-R2- ECR NPS for MSB1-RIO650-104-02 | RFI-0377 Electrical- CPK03-R2- ECR NPS for MSB1-RIO650-104-02.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44610.7422 | Item | sites/1232505342/CMiC RFI Response | 0377
21029900-0376 | Electrical- CPK03-R2 General Purpose Receptacles Conduit | RFI-0376 Electrical- CPK03-R2 General Purpose Receptacles Conduit.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44615.8148 | Item | sites/1232505342/CMiC RFI Response | 0376
21029900-0375 | Wet Mech - MSB - CPK03-R2 - BMWCRFI#096 Safety Shower Missing Drawing | 21029900-0375 - Wet Mech - MSB - CPK03-R2 - BMWCRFI096 Safety Shower Missing Drawing.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44615.5158 | Item | sites/1232505342/CMiC RFI Response | 0375
21029900-0374 | Wet Mech - MSB - CPK03-R2 -BMWCRFI#087 - CHWSR Reducers vs. Eccentric | 21029900-0374 - Wet Mech - MSB - CPK03-R2 -BMWCRFI087 - CHWSR Reducers vs. Eccentric.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44613.7248 | Item | sites/1232505342/CMiC RFI Response | 0374
21029900-0373 | Process - RA4 - LLP02R1 - Suez CHCO2DI Skid Redundancy Upgrade Kit | RFI-0373 Process - RA4 - LLP02R1 - Suez CHCO2DI Skid Redundancy Upgrade Kit RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44621.8097 | Item | sites/1232505342/CMiC RFI Response | 0373
21029900-0372 | Process - RA4 - CPK02-R2 - TCHWS Clash with Cable Tray Unistrut | RFI-0372 Process - RA4 - CPK02-R2 - TCHWS Clash with Cable Tray Unistrut RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44617.8999 | Item | sites/1232505342/CMiC RFI Response | 0372
21029900-0371 | Process - RA4 - CPK02-R4 - AWN Tanks and Pump Vendor | RFI-0371 Process - RA4 - CPK02-R4 - AWN Tanks and Pump Vendor RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44620.5617 | Item | sites/1232505342/CMiC RFI Response | 0371
21029900-0369 | Process - RA4 - CPK02-R4 - GL-66H Purge Ports | RFI-0369 Process - RA4 - CPK02-R4 - GL-66H Purge Ports RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44620.5587 | Item | sites/1232505342/CMiC RFI Response | 0369
21029900-0368 | Process - RA4 - CPK02-R2 - TCHW Discrepancies in DM at RA4-RAH102-09 thru RA4-RAH102-13 | RFI-0368 Process - RA4 - CPK02-R2 - TCHW Discrepancies in DM at RA4-RAH102-09 thru -13 RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44620.5615 | Item | sites/1232505342/CMiC RFI Response | 0368
21029900-0366 | Process - RA4 - CPK02-R4 - 2 inch PA IDC Discrepancy | RFI-0366 Process - RA4 - CPK02-R4 - 2 inch PA IDC Discrepancy RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44607.649 | Item | sites/1232505342/CMiC RFI Response | 0366
21029900-0365R1 | CSA - CPK03-R2 MSB LVL2 HSS Cup Conflicts - R1 | RFI-0365R1 - CSA - CPK03-R2 MSB LVL2 HSS Cup Conflicts - R1-RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | SOWLES CO DBA SOWLES STEEL ERECTORS (Kyle Wilcox) |  | 44621.4483 | Item | sites/1232505342/CMiC RFI Response | 0365R1
21029900-0365 | CSA - CPK03-R2 MSB LVL2 HSS Cup Conflicts - R1 | RFI-365 CSA - CPK03-R2 MSB LVL2 HSS Cup Conflicts-RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | SOWLES CO DBA SOWLES STEEL ERECTORS (Kyle Wilcox) |  | 44623.4386 | Item | sites/1232505342/CMiC RFI Response | 0365
21029900-0364 | Process - RA4 - CPK02-R4 - 2 inch OFA Lateral FPOC Qty | RFI-0364 Process - RA4 - CPK02-R4 - 2 inch OFA Lateral FPOC Qty RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44620.5614 | Item | sites/1232505342/CMiC RFI Response | 0364
21029900-0363 | CSA - CPK03-R2 Clean Room Stair Landings | RFI-363 - CSA - CPK03-R2 Clean Room Stair Landings-RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | SOWLES CO DBA SOWLES STEEL ERECTORS (Kyle Wilcox) |  | 44615.477 | Item | sites/1232505342/CMiC RFI Response | 0363
21029900-0362 | Process - RA4 - CPK02-R2 - SSH-5140 Clash with PCW | RFI-0362 Process - RA4 - CPK02-R2 - SSH-5140 Clash with PCW RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44615.8145 | Item | sites/1232505342/CMiC RFI Response | 0362
21029900-0361 | Process - RA4 - CPK02-R2 - BEA Routing Clash with Duct | RFI-0361 Process - RA4 - CPK02-R2 - BEA Routing Clash with Duct RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44615.8138 | Item | sites/1232505342/CMiC RFI Response | 0361
21029900-0360 | Mech Process - RA4 - CPK02-R2 - TCHW Conflict with RMF at E.5/10, J.2/7, and E.5/9 | RFI-0360 Mech Process - RA4 - CPK02-R2 - TCHW Conflict with RMF at E.5-10 J.2-7 E.5-9 RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44620.8038 | Item | sites/1232505342/CMiC RFI Response | 0360
21029900-0359 | Architectural - RA4 - CPK02-R4 - Mineral Wool Insulation | RFI-0359 Architectural - RA4 - CPK02-R4 - Mineral Wool Insulation RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | ADVANCED TECHNOLOGY GROUP INC (Ned Naffakh) |  | 44623.4392 | Item | sites/1232505342/CMiC RFI Response | 0359
21029900-0358 | Process - MSB - CPK03-R2 - Charter RFI#073.1 Dead Legs | 21029900-0358 - Process - MSB - CPK03-R2 - Charter RFI073.1 Dead Legs.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44613.7225 | Item | sites/1232505342/CMiC RFI Response | 0358
21029900-0357 | Electrical- CPK03-R2 ECR Model and Spec Discrepancy | RFI-0357 Electrical- CPK03-R2 ECR Model and Spec Discrepancy.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44610.7415 | Item | sites/1232505342/CMiC RFI Response | 0357
21029900-0355 | CSA - MSB - CPK03-R3 Strut Fitting Substitution | RFI-0355 CSA - MSB - CPK03-R3 Strut Fitting Substutution.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | PERFORMANCE CONTRACTING INC (Grayson Sorenson) |  | 44615.8152 | Item | sites/1232505342/CMiC RFI Response | 0355
21029900-0354 | CSA - MSB - CPK03-R3 RA-ST-2200 Substitution | RFI-0354 CSA - MSB - CPK03-R3 RA-ST-2200.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | PERFORMANCE CONTRACTING INC (Grayson Sorenson) |  | 44615.8124 | Item | sites/1232505342/CMiC RFI Response | 0354
21029900-0353 | Structural - RA4 - CPK02-R2 - Framing Details at GL A-9 | RFI-0353 - Structural - RA4 - CPK02-R2 - Framing Details at GL A-9 RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | ADVANCED TECHNOLOGY GROUP INC (Ned Naffakh) |  | 44606.1505 | Item | sites/1232505342/CMiC RFI Response | 0353
21029900-0352R1 | CSA - MSB - CPK03-R3 Door & Sill Clarifications | RFI-0352 CSA - MSB - CPK03-R3 Door and Sill Clarifications.pdf | Open | JACOBS ENGINEERING GROUP INC (Document Control) | PERFORMANCE CONTRACTING INC (Grayson Sorenson) | RA-AR-D1807 | 44620.6675 | Item | sites/1232505342/CMiC RFI Response | 0352R1
21029900-0351 | CSA - MSB - CPK03-R3 - Stair 1 Design Changes | RFI-0351 CSA - MSB -CPK03-R3 - Stair 1 Design Changes.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | PERFORMANCE CONTRACTING INC (Grayson Sorenson) |  | 44620.4046 | Item | sites/1232505342/CMiC RFI Response | 0351
21029900-0350 | Process - MSB - CPK03-R2 - Charter RFI#153 UN2 and SWS | 21029900-0350 - Process - MSB - CPK03-R2 - Charter RFI153 UN2 and SWS.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44617.686 | Item | sites/1232505342/CMiC RFI Response | 0350
21029900-0349 | Process - MSB - CPK03-R2 - Charter RFI#154 5% H2-He Line Reduced | 21029900-0349 - Process - MSB - CPK03-R2 - Charter RFI154 5 H2-He Line Reduced.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44613.7262 | Item | sites/1232505342/CMiC RFI Response | 0349
21029900-0348 | CSA - MSB - CPK03-R2 LVL2 Connections to Embedded Strut-f | RFI-0348 CSA - MSB - CPK03-R2 LVL2 Connections to Embedded Strut-f.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | SOWLES CO DBA SOWLES STEEL ERECTORS (Kyle Wilcox) | RA-ST-2144 | 44606.6892 | Item | sites/1232505342/CMiC RFI Response | 0348
21029900-0347 | Process - MSB - CPK03-R2 - Charter RFI#150 Space Heater Requirement | 21029900-0347 - Process - MSB - CPK03-R2 - Charter RFI150 Space Heater Requirement.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44609.5607 | Item | sites/1232505342/CMiC RFI Response | 0347
21029900-0346 | CSA - MSB - CPK03-R5 - Option of RA-ST-2024 | RFI-0346 - CSA - MSB - CPK03-R5 - Option of RA-ST-2024 RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | SOWLES CO DBA SOWLES STEEL ERECTORS (Kyle Wilcox) |  | 44614.5919 | Item | sites/1232505342/CMiC RFI Response | 0346
21029900-0345 | Process - MSB - CPK03-R2 - Charter RFI#149 Adjustable Foot Support | 21029900-0345 - Process - MSB - CPK03-R2 - Charter RFI149 Adjustable Foot Support.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44613.7284 | Item | sites/1232505342/CMiC RFI Response | 0345
21029900-0344 | Process - MSB - CPK03-R2 - Charter RFI#59.1 CHCO2DI Future Lateral | 21029900-0344 - Process - MSB - CPK03-R2 - Charter RFI59.1 CHCO2DI Future Lateral.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44617.6862 | Item | sites/1232505342/CMiC RFI Response | 0344
21029900-0343 | Process - MSB - CPK03-R2 - Charter RFI#147 Metering Pump Door Material | 21029900-0343 - Process - MSB - CPK03-R2 - Charter RFI147 Metering Pump Door Material.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44620.5285 | Item | sites/1232505342/CMiC RFI Response | 0343
21029900-0342 | Process - MSB - CPK03-R2 - Charter RFI#146 HPN2 Design Deviation | 21029900-0342 - Process - MSB - CPK03-R2 - Charter RFI146 HPN2 Design Deviation.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44613.7228 | Item | sites/1232505342/CMiC RFI Response | 0342
21029900-0341 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#086 Socket Weld of ADB Piping | 21029900-0341 - Wet Mech - MSB - CPK03-R2 - BMWC RFI086 Socket Weld of ADB Piping.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44609.5631 | Item | sites/1232505342/CMiC RFI Response | 0341
21029900-0340R1 | Structural - CPK01-R2 - Harder RFI 12 - AB/57 4" Conduit Clash w New Rack - R1 | RFI0340R1 - Struct - CPK01-R2 - AB57 4 in Conduit Clash w Rack - R1-Res.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | HARDER MECHANICAL CONTRACTORS INC (Kayleigh Arendt) |  | 44623.4145 | Item | sites/1232505342/CMiC RFI Response | 0340R1
21029900-0340 | Structural - CPK01-R2 - Harder RFI 12 - AB/57 4" Conduit Clash w New Rack | RFI0340 - Structural - CPK01-R2 - Harder RFI 12 - AB57 4 in Conduit Clash w New Rack - Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44620.526 | Item | sites/1232505342/CMiC RFI Response | 0340
21029900-0339 | Process - RA4 - CPK02-R2 - PSV248-1C-16A Type Clarification | RFI-0339 Process - RA4 - CPK02-R2 - PSV248-1C-16A Type Clarification RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44609.563 | Item | sites/1232505342/CMiC RFI Response | 0339
21029900-0338 | Process - MSB - CPK01-R2 - Harder RFI 11 - ZREF Additional MSB Inline Valve | RFI0338 - Process - MSB - CPK01-R2 - Harder RFI 11 - ZREF Additional MSB Inline Valve - Response.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44622.5441 | Item | sites/1232505342/CMiC RFI Response | 0338
21029900-0337 | CSA - MSB - CPK03-R5 CJP Weld RA-ST-2096 | RFI-0337 - CSA - MSB - CPK03-R5 - CJP Weld RA-ST-2096 RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | SOWLES CO DBA SOWLES STEEL ERECTORS (Kyle Wilcox) |  | 44614.592 | Item | sites/1232505342/CMiC RFI Response | 0337
21029900-0336 | Electrical- CPK03-R2 Subfab General Purpose Receptacle Elevation | RFI-0336 Electrical- CPK03-R2 Subfab General Purpose Receptacle Elevation RESP.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44608.4595 | Item | sites/1232505342/CMiC RFI Response | 0336
21029900-0334 | Electrical- CPK03-R2 - ECR Tool Cluster | RFI-0334- Electrical- CPK03-R2 - ECR Tool Cluster.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44606.6479 | Item | sites/1232505342/CMiC RFI Response | 0334
21029900-0333 | Mechanical - CPK03-R2 - Streimer RFI 21 - FAB SA Hanger Issue | RFI0333 - Mechanical - CPK03-R2 - Streimer RFI 21 - FAB SA Hanger Issue - Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 23_31_13_02 | 44602.7123 | Item | sites/1232505342/CMiC RFI Response | 0333
21029900-0332 | Process - MSB - CPK03-R2 - Charter RFI#134 VELAN Glove Valve Clarification | 21029900-0332 - Process - MSB - CPK03-R2 - Charter RFI134 VELAN Glove Valve Clarification.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44608.4599 | Item | sites/1232505342/CMiC RFI Response | 0332
21029900-0331 | Electrical- CPK03-R2 EC 1200 amp D-Boards Grounding | PM3010_2022_02_07__09_14_05.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44601.7888 | Item | sites/1232505342/CMiC RFI Response | 0331
21029900-0331 | Electrical- CPK03-R2 EC 1200 amp D-Boards Grounding | RFI-0331 Electrical- CPK03-R2 EC 1200 amp D-Boards Grounding.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44610.7418 | Item | sites/1232505342/CMiC RFI Response | 0331
21029900-0330 | Mechanical - CPK03-R2 - MSB - Streimer - Level 2 HXRA Dampers | RFI0330 - Mechanical - CPK03-R2 - MSB - Streimer - Level 2 HXRA Dampers - Response.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44622.6013 | Item | sites/1232505342/CMiC RFI Response | 0330
21029900-0329 | Process - MSB - CPK03-R2 - Charter RFI 15 - KN2 Detail Clarification | RFI0329 - Process - MSB - CPK03-R2 - Charter RFI 15 - KN2 Detail Clarification - Response.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44622.5444 | Item | sites/1232505342/CMiC RFI Response | 0329
21029900-0328 | Process - MSB - CPK03-R2 - Charter RFI 14 - BCD Tray Cut Sheet | RFI0328 - Process - MSB - CPK03-R2 - Charter RFI 14 - BCD Tray Cut Sheet - Response.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44622.5439 | Item | sites/1232505342/CMiC RFI Response | 0328
21029900-0327 | Electrical - CPK02-R2 RA4 Power Cable Tray Height - Confirming | RFI-0327 Electrical - CPK02-R2 RA4 Power Cable Tray Height - Confirming RESPONSE.pdf | Answered - Complete | OEG INC (Ryan Pfeifer) |  | 26_05_36_00 | 44600.7675 | Item | sites/1232505342/CMiC RFI Response | 0327
21029900-0325 | Mechanical - CPK03-R2 - Streimer RFI 22 - HXRA Return Air Flex Duct | RFI0325 - Mechanical - CPK03-R2 - Streimer RFI 22 - HXRA Return Air Duct - Response.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40_05_15_16 | 44622.6002 | Item | sites/1232505342/CMiC RFI Response | 0325
21029900-0324 | I and C - CPK02-R2 RA4 Existing Column Mounted TET Devices - Confirming | RFI-0324 I and C - CPK02-R2 RA4 Existing Column Mounted TET Devices - Confirming RESPONSE.pdf | Answered - Complete | OEG INC (Ryan Pfeifer) |  |  | 44600.6948 | Item | sites/1232505342/CMiC RFI Response | 0324
21029900-0322 | Telecom - CPK02-R2 RA4 Existing Column Mounted WAP Devices - Confirming | RFI-0322 Telecom - CPK02-R2 RA4 Existing Column Mounted WAP Devices - Confirming RESPONSE.pdf | Answered - Complete | OEG INC (Ryan Pfeifer) |  |  | 44600.6995 | Item | sites/1232505342/CMiC RFI Response | 0322
21029900-0321 | Electrical - CPK02-R2 RA4 Existing Column Mounted Electrical Devices - Confirming | RFI-0321 Elec - CPK02-R2 RA4 Existing Column Mounted Electrical Devices - Confirming RESPONSE.pdf | Answered - Complete | OEG INC (Ryan Pfeifer) |  |  | 44600.6497 | Item | sites/1232505342/CMiC RFI Response | 0321
21029900-0319 | Electrical- CPK03-R2 ECR MS1-GMAH103-01-00 | RFI-0319 Electrical- CPK03-R2 ECR MS1-GMAH103-01-00.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44610.7422 | Item | sites/1232505342/CMiC RFI Response | 0319
21029900-0318 | Electrical- CPK03-R2 ECR for MXT2S57E | RFI-0318 Electrical- CPK03-R2 ECR for MXT2S57E.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44610.7417 | Item | sites/1232505342/CMiC RFI Response | 0318
21029900-0317 | Electrical- CPK03-R2 30A Conduit Size Request | RFI-0317 Electrical- CPK03-R2 30A Conduit Size Request.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44610.752 | Item | sites/1232505342/CMiC RFI Response | 0317
21029900-0316 | Electrical - CPK02-R2 RA4 D-Board R4D1C15A Future Tag Discrepancy - Confirming | RFI-0316 Electrical - CPK02-R2 RA4 D-Board R4D1C15A Future Tag Discrepancy - Confirming RESPONSE.pdf | Answered - Complete | OEG INC (Ryan Pfeifer) |  |  | 44600.636 | Item | sites/1232505342/CMiC RFI Response | 0316
21029900-0315 | Process - MSB - CPK03-R2 - Charter RFI#145 Inaccessible Cleanout on CSW Submain | 21029900-0315 - Process - MSB - CPK03-R2 - Charter RFI145 Inaccessible Cleanout on CSW Submain.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44607.4545 | Item | sites/1232505342/CMiC RFI Response | 0315
21029900-0314R1 | Process - MSB - CPK03-R2 - Charter RFI#144 Future Branch Missing R1 | 21029900-0314R1 - Process - MSB - CPK03-R2 - Charter RFI144 Future Branch Missing R1.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44616.8055 | Item | sites/1232505342/CMiC RFI Response | 0314R1
21029900-0314 | Process - MSB - CPK03-R2 - Charter RFI#144 Future Branch Missing | 21029900-0314 - Process - MSB - CPK03-R2 - Charter RFI144 Future Branch Missing.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44606.4532 | Item | sites/1232505342/CMiC RFI Response | 0314
21029900-0313 | Process - MSB - CPK03-R2 - Charter RFI#143 OFA Lateral in Bay U Ductwork Clash | 21029900-0313 - Process - MSB - CPK03-R2 - Charter RFI143 OFA Lateral in Bay U Ductwork Clash.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44609.5446 | Item | sites/1232505342/CMiC RFI Response | 0313
21029900-0312 | Process - MSB - CPK03-R2 - Charter RFI#142 CPCW Valve Handles Clash | 21029900-0312 - Process - MSB - CPK03-R2 - Charter RFI142 CPCW Valve Handles Clash.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44607.4567 | Item | sites/1232505342/CMiC RFI Response | 0312
21029900-0311 | Electrical- CPK03-R2 ECR 30A Construction Receptacles MXR2X57B | RFI-0311 Electrical- CPK03-R2 ECR 30A Construction Receptacles MXR2X57B.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44610.7414 | Item | sites/1232505342/CMiC RFI Response | 0311
21029900-0310 | Process - MSB - CPK03-R2 - Charter RFI#118 UPS PRV Swap V582 | 21029900-0310 - Process - MSB - CPK03-R2 - Charter RFI118 UPS PRV Swap V582.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44622.5189 | Item | sites/1232505342/CMiC RFI Response | 0310
21029900-0308 | CSA - RA4 - CPk02-R4 - Details and Keynote Clarification | RFI-0308_CSA - RA4 - CPk02-R4 - Details and Keynote Clarification RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44608.4667 | Item | sites/1232505342/CMiC RFI Response | 0308
21029900-0307 | Electrical CPK03 R2 ECR Source Panel MXR1R53B Confirmation | RFI-0307 Electrical CPK03 R2 ECR Source Panel MXR1R53B Confirmation - Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 26_24_16_43_ | 44607.4551 | Item | sites/1232505342/CMiC RFI Response | 0307
21029900-0306 | Electrical B0001-CPK03-R2 MSB Ground Wire Size Confirmation | RFI0306 Electrical B0001-CPK03-R2 MSB Ground Wire Size Confirmation Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 26_24_16_43 | 44610.4072 | Item | sites/1232505342/CMiC RFI Response | 0306
21029900-0305 | Electrical B0001-CPK03-R2 MSB ERC Source Panel MXR1N53B Confirmation | RFI-0305 - Electrical B0001-CPK03-R2 MSB ERC Source Panel MXR1N53B Confirmation Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 26_24_16_43 | 44610.7521 | Item | sites/1232505342/CMiC RFI Response | 0305
21029900-0304 | Electrical CPK03 R2 CMXR1M53B Panel Confirmation | RFI-304 Electrical CPK03 R2CMXR1M53B Panel ConfirmationResponse.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 26_24_16_43 | 44599.4659 | Item | sites/1232505342/CMiC RFI Response | 0304
21029900-0303 | Structural - MSB - CPK01- R2 - AE-56 Subfab Rack Steel Connection As-Built | RFI 303 - Structural - MSB - CPK01- R2 - AE-56 Subfab Rack Steel Connection As-Built-RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44613.4673 | Item | sites/1232505342/CMiC RFI Response | 0303
21029900-0301 | DRYMECH-ELEC-CPK02-RA4-Conduit Relocation at Grid E.5 and 13 of Subfab Level | RFI-0301DRYMECH-ELEC-CPK02-RA4-Conduit Relocation at Grid E.5 and 13 of Sublab Level RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44616.4384 | Item | sites/1232505342/CMiC RFI Response | 0301
21029900-0300 | Electrical - MSB LLE01 VFD202-3-10 CPCW Distribution Pump Confirmation | RFI-300 Electrical - MSB LLE01 VFD202-3-10 CPCW Distribution Pump Confirmation Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 26_29_65_00 | 44607.4543 | Item | sites/1232505342/CMiC RFI Response | 0300
21029900-0299 | DRYMECH-CSA-CPK02-R2-RA4-Duct Vs Tube Steel Conflict at Grid F and 10 Confirmation | RFI-0299 DRYMECH-CSA-CPK02-R2-RA4 Duct Vs tube Steel Conflict at Grid F and 10 RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44609.7587 | Item | sites/1232505342/CMiC RFI Response | 0299
21029900-0298 | DRYMECH-CPK02-R2-RA4- Duct Sizing Confirmation | RFI-0298 DRYMECH-CPK02-R2-RA4-Duct Sizing Confirmation RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44607.5106 | Item | sites/1232505342/CMiC RFI Response | 0298
21029900-0297 | Structural - CPK01-R2 - Harder RFI 9 - U57 and AD57 Column Strut Rack Conflict | RFI0297 - Structural - CPK01-R2 - Harder RFI 9 - Column Strut Rack Conflict - Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44607.4605 | Item | sites/1232505342/CMiC RFI Response | 0297
21029900-0296 | Structural - MSB - CPK03-R2 - RA-ST-2031 P2343 Change to P2341 | RFI 296 - Structural - MSB - CPK03-R2 - RA-ST-2031 P2343 Change to P2341 - RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | SOWLES CO DBA SOWLES STEEL ERECTORS (Kyle Wilcox) |  | 44613.4422 | Item | sites/1232505342/CMiC RFI Response | 0296
21029900-0295 | Process - MSB - CPK03-R2 - Charter RFI#78.1 CPCW Mechanical Area Issues | 21029900-0295 - Process - MSB - CPK03-R2 - Charter RFI78.1 CPCW Mechanical Area Issues.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44609.5442 | Item | sites/1232505342/CMiC RFI Response | 0295
21029900-0294 | DRYMECH-CSA-CPK02-R2-RA4-Plenum Wall Extension | RFI-0294 DRYMECH-CSA-CPK02-R2-RA4 Plenum Wall Extension RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44615.7812 | Item | sites/1232505342/CMiC RFI Response | 0294
21029900-0293R1 | DRY MECH-CPK02-RA4- Diffuser and Supply Grille Cans Vs Ceiling Grid Conflicts | RFI-0293R1 DRY-MECH-CPK02-R2-RA4 Diffuser and Supply Grilles Cans Vs Ceiling Grid RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | APOLLO INC (Evan Lehman) |  | 44621.4292 | Item | sites/1232505342/CMiC RFI Response | 0293R1
21029900-0293 | DRY MECH-CPK02-RA4- Diffuser and Supply Grille Cans Vs Ceiling Grid Conflicts | RFI-0293 DRYMECH-CPK02-R2-Diffuser and Supply Grilles Cans Vs Ceiling Grid Conflicts RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | APOLLO INC (Evan Lehman) |  | 44616.4381 | Item | sites/1232505342/CMiC RFI Response | 0293
21029900-0292 | Structural - MSB - CPK03-R5 - RA-ST-2001 Key Note 4 and 6 Callout | RFI-292 Structural - MSB - CPK03-R5 - RA-ST-2001 Key Note 4 and 6 Callout- RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | SOWLES CO DBA SOWLES STEEL ERECTORS (Kyle Wilcox) |  | 44620.598 | Item | sites/1232505342/CMiC RFI Response | 0292
21029900-0291 | Process - MSB - CPK03-R2 - Charter RFI#141 CPCW EOL Size Discrepancy | 21029900-0291 - Process - MSB - CPK03-R2 - Charter RFI141 CPCW EOL Size Discrepancy.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44616.3988 | Item | sites/1232505342/CMiC RFI Response | 0291
21029900-0290 | Process - MSB - CPK03-R2 - Charter RFI#140 CHCO2DI Missing DA-26 | 21029900-0290 - Process - MSB - CPK03-R2 - Charter RFI140 CHCO2DI Missing DA-26.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44609.5612 | Item | sites/1232505342/CMiC RFI Response | 0290
21029900-0289 | Process - MSB - CPK03-R2 - Charter RFI#139 CSW & GSW Low Point Discrepancy | 21029900-0289 - Process - MSB - CPK03-R2 - Charter RFI139 CSW GSW Low Point Discrepancy.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44609.5455 | Item | sites/1232505342/CMiC RFI Response | 0289
21029900-0287 | Process - MSB - CPK03-R2 - Charter RFI#138 SHCW FI-1 Range Needed | 21029900-0287 - Process - MSB - CPK03-R2 - Charter RFI138 SHCW FI-1 Range Needed.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44609.5468 | Item | sites/1232505342/CMiC RFI Response | 0287
21029900-0286 | Structural - MSB - CPK03-R2- South MAH Platform Changes | RFI-286 Structural - MSB - CPK03-R2- South MAH Platform Changes - RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | SOWLES CO DBA SOWLES STEEL ERECTORS (Kyle Wilcox) |  | 44623.391 | Item | sites/1232505342/CMiC RFI Response | 0286
21029900-0285 | Process - MSB - CPK03-R2 - Charter RFI#137 UPN 412 Clash with Lateral Racks | 21029900-0285 - Process - MSB - CPK03-R2 - Charter RFI137 UPN 412 Clash with Lateral Racks.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44616.399 | Item | sites/1232505342/CMiC RFI Response | 0285
21029900-0284 | Process - MSB - CPK03-R2 - Charter RFI#136 FRP Reinforced Blind Flange | 21029900-0284 - Process - MSB - CPK03-R2 - Charter RFI136 FRP Reinforced Blind Flange.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44609.5608 | Item | sites/1232505342/CMiC RFI Response | 0284
21029900-0283 | Process - RA4 - CPK02-R2 - IW Insulation Clarification | RFI-0283 Process - RA4 - CPK02-R2 - IW Insulation Clarification RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44615.479 | Item | sites/1232505342/CMiC RFI Response | 0283
21029900-0282 | Process - RA4 - CPK02-R4 - Bearing Air Valve Clarification | RFI-0282 Process - RA4 - CPK02-R4 - Bearing Air Valve Clarification RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44615.5182 | Item | sites/1232505342/CMiC RFI Response | 0282
21029900-0281 | Process - RA4 - CPK02-R4 - Zero Reference Clarification | RFI-0281 Process - RA4 - CPK02-R4 - Zero Reference Clarification RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44615.5187 | Item | sites/1232505342/CMiC RFI Response | 0281
21029900-0271 | Structural - CPK02-R2 CUPS Conflicts Sector E | RFI-0271 Structural - CPK02-R2 CUPS Conflicts Sector E RESPONSE.pdf | Answered - Complete | SOWLES CO DBA SOWLES STEEL ERECTORS (Eric Chambers) |  |  | 44622.6587 | Item | sites/1232505342/CMiC RFI Response | 0271
21029900-0270 | Process - RA4 - CPK02-R2 - HRWS/R Piping Demo | RFI-0270 Process - RA4 - CPK02-R2 - HRWS-R Piping Demo RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44620.4964 | Item | sites/1232505342/CMiC RFI Response | 0270
21029900-0269 | DRYMECH-ELEC-CPK02-R2-RA4-Conduit Relocation at Grid C,D,10.5, B and F of Subfab Level. | RFI-0296 DRYMECH-ELEC-CPK02-R2-RA4-Conduit Relocation at Grid CD10.5 B and F of Subfab Level.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44606.205 | Item | sites/1232505342/CMiC RFI Response | 0269
21029900-0269 | DRYMECH-ELEC-CPK02-R2-RA4-Conduit Relocation at Grid C,D,10.5, B and F of Subfab Level. | RFI-269 DRYMECH-ELEC-CPK02-R2 Conduit Relocation at Grid CD10.5.B and F RESPONSE (1297481040).pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44616.4425 | Item | sites/1232505342/CMiC RFI Response | 0269
21029900-0268 | DRY MECH-CPK02-R2-RA4 EXGF Blast Gate Vs Damper Confirmation | RFI-0268 DRY MECH-CPK02-R2-RA4 EXGF Blast Gate Vs Damper Confirmation RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | APOLLO INC (Evan Lehman) |  | 44607.7347 | Item | sites/1232505342/CMiC RFI Response | 0268
21029900-0267 | Process - RA4 - CPK02-R2 - Design Discrepancy for Piping to TCHW, CHW Equipment | RFI-0267 Process - RA4 - CPK02-R2 - Design Discrepancy TCHW CHW Equipment RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44617.567 | Item | sites/1232505342/CMiC RFI Response | 0267
21029900-0265 | Process - RA4 - CPK02-R2 - SHCWS BA-8 | RFI-0265 Process - RA4 - CPK02-R2 - SHCWS BA-8 RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44617.6868 | Item | sites/1232505342/CMiC RFI Response | 0265
21029900-0264 | Process - RA4 - CPK02-R2 - TCHW Bypass | RFI-0264 Process - RA4 - CPK02-R2 - TCHW Bypass RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44615.478 | Item | sites/1232505342/CMiC RFI Response | 0264
21029900-0263 | Process - RA4 - CPK02-R2 - BA-59s on Specification JEA | RFI-0263 Process - RA4 - CPK02-R2 - BA-59s on Specification JEA RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44615.4779 | Item | sites/1232505342/CMiC RFI Response | 0263
21029900-0259 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#062 Safety Shower Locations | 21029900-0259 - Wet Mech - MSB - CPK03-R2 - BMWC RFI062 Safety Shower Locations.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 22400000 | 44613.4223 | Item | sites/1232505342/CMiC RFI Response | 0259
21029900-0255 | CSA - MSB - CPK03-R2 & CPK03-R3 - Cleanroom Slider Door Clarification | RFI-255 CSA - MSB - CPK03-R2 CPK03-R3 - Cleanroom Slider Door Clarification.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | PERFORMANCE CONTRACTING INC (Grayson Sorenson) |  | 44613.384 | Item | sites/1232505342/CMiC RFI Response | 0255
21029900-0247 | MSB - CSA - CPK03-R2&CPK03-R3 M16 Rod Drops at Embed Strut Alternate Details | RFI-0247 CSA - MSB - CPK03-R3 M16 Rod Drops at Embed Strut Alt Detail.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44615.6177 | Item | sites/1232505342/CMiC RFI Response | 0247
21029900-0246 | Process - RA4 - CPK02-R2 - Safety Shower Relocation Clarification | RFI-0246 Process - RA4 - CPK02-R2 - Safety Shower Relocation Clarification RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44617.8019 | Item | sites/1232505342/CMiC RFI Response | 0246
21029900-0245 | Process - RA4 - CPK02-R2 - PV Reducer Clarification | RFI-0245 Process - RA4 - CPK02-R2 - PV Reducer Clarification RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44617.802 | Item | sites/1232505342/CMiC RFI Response | 0245
21029900-0244 | Process - RA4 - CPK02-R2 - BIO Spec Change From Tank | RFI-0244 Process - RA4 - CPK02-R2 - BIO Spec Change From Tank RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44617.8021 | Item | sites/1232505342/CMiC RFI Response | 0244
21029900-0243 | Process - RA4 - CPK02-R2 - UN2 1/2" KET Jumper Assembly | RFI-0243 Process - RA4 - CPK02-R2 - UN2 0.5 inch KET Jumper Assembly RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44589.7502 | Item | sites/1232505342/CMiC RFI Response | 0243
21029900-0242 | Process - RA4 - CPK02-R2 - BF-23 Callout Location | RFI-0242 Process - RA4 - CPK02-R2 - BF-23 Callout Location RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44617.8021 | Item | sites/1232505342/CMiC RFI Response | 0242
21029900-0241 | Process - RA4 - CPK02-R2 - PDIT Valve Specification | RFI-0241 Process-RA4-CPK02-R2-PDIT Valve Specification RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44613.4445 | Item | sites/1232505342/CMiC RFI Response | 0241
21029900-0237R1 | Wet Mech - MSB - CPK03-R2 - BMWC RFI#040 Lateral EOL Shunt Detail R1 | 21029900-0237R1 - Wet Mech - MSB - CPK03-R2 - BMWC RFI040 Lateral EOL Shunt Detail R1.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44613.5185 | Item | sites/1232505342/CMiC RFI Response | 0237R1
21029900-0236 | MECH-ELEC-InC-CPK02-R2 RAH Units System Tag in MEL Log | RFI-0236 MECH-ELEC-InC-CPK02-R2-RA4 RAH Units System Tag in MEL Log RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44606.0219 | Item | sites/1232505342/CMiC RFI Response | 0236
21029900-0226 | Structural - MSB - CPK03-R5 Conflicts with Continuity Plates | RFI-0226 - Structural - MSB - CPK03-R5 - Conflicts with Continuity Plates RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | SOWLES CO DBA SOWLES STEEL ERECTORS (Kyle Wilcox) |  | 44615.4388 | Item | sites/1232505342/CMiC RFI Response | 0226
21029900-0218 | MECH-CPK-02-R2-RA4-Ceiling Diffusers CD9 and CD10 Type Confirmation | RFI-0218 MECH-CPK02-R2-RA4-Ceiling Diffusers CD9 and CD10 Type Confirmation RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 23_37_13_00 | 44588.4909 | Item | sites/1232505342/CMiC RFI Response | 0218
21029900-0214 | Mechanical - CPK03-R2 - MSB - Exhaust Submain Damper Actuator Orientation | RFI0214 - Mechanical - CPK03-R2 - MSB - Exhaust Submain Damper Actuator Orientation - Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44622.7067 | Item | sites/1232505342/CMiC RFI Response | 0214
21029900-0210 | Process - MSB - CPK03-R2 - Charter RFIs 62-103 | RFI-0120 - Process - MSB - CPK03-R2 - Charter RFIs 62-103RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44622.5991 | Item | sites/1232505342/CMiC RFI Response | 0210
21029900-0209 | Process - MSB - CPK03-R2 - Charter RFIs 42-61 | RFI-0209 - Process - MSB - CPK03-R2 - Charter RFIs 42-61Response.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44622.5993 | Item | sites/1232505342/CMiC RFI Response | 0209
21029900-0208 | I&C- MSB1-CPK03-R2- Panel Anchoring | RFI-0208 - I_C - MSB - CPK03-R2 - Panel AnchoringRESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44622.5992 | Item | sites/1232505342/CMiC RFI Response | 0208
21029900-0207 | Wet Mech - MSB - CPK03-R2 - PI-12 Pressure Gauge Range | RFI-0207 - Wet Mech - MSB - CPK03-R2 - PI-12 Pressure Gauge Range.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40051524 | 44622.599 | Item | sites/1232505342/CMiC RFI Response | 0207
21029900-0206 | I&C- MSB1-CPK03-R2- FE Datasheet Revise | RFI-206 - I_C- MSB - CPK03-R2 - Datasheet ReviseRESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44622.5989 | Item | sites/1232505342/CMiC RFI Response | 0206
21029900-0205 | Process - MSB - LLP02 - Confirmation of Chilled Water Supply Conditions to the CHCO2DI Heat Exchanger | RFI-0205 - MSB - LLP02-R1 - Confirmation of CHWS Conditions to CHCO2DI HXRA RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44616.7725 | Item | sites/1232505342/CMiC RFI Response | 0205
21029900-0204 | Process - MSB - LLP02 - Confirmation of space available around the RA4 CO2DI skid | RFI-0204 - Process - RA4 - LLP02 - Confirmation CHCO2DI SKD Space RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44616.7872 | Item | sites/1232505342/CMiC RFI Response | 0204
21029900-0203 | Process - MSB - LLP02 - Confirmation of CO2 gas pressure to the IMO Carbonator skid | RFI-0203 - Process - MSB - LLP02 - Confirmation of CO2 Pressure to IMO CHCO2DI SKD RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44616.7553 | Item | sites/1232505342/CMiC RFI Response | 0203
21029900-0202 | Process - MSB - LLP02 - Vibration Isolation for IMO Carbonator pumps | RFI-0202 - Process - MSB - LLP02 - Vibration Isolation for IMO Carbonator Pump RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44616.7234 | Item | sites/1232505342/CMiC RFI Response | 0202
21029900-0201 | DRY-MECH-CPK02-R2-RAH Units Return Air Damper Removal Confirmation | RFI-0201 DRY-MECH-CPK02-R2-RAH Units Return Air Damper Removal Confirmation RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44593.6924 | Item | sites/1232505342/CMiC RFI Response | 0201
21029900-0200 | Electrical - CPK03 R2 MSB L2 Cleanroom Wall Ground Clarifications | RFI-0200 Electrical - CPK03 R2 MSB L2 Cleanroom Wall Ground Clarifications - Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44592.6079 | Item | sites/1232505342/CMiC RFI Response | 0200
21029900-0198 | Wet Mech - MSB - CPK03-R2 - BA-73 in Lieu of BA-6 on Propress IDC Piping Line Class | RFI-198 - Wet Mech - MSB - CPK03-R2 - BA-73 in Lieu of BA-6RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40051611 | 44622.5691 | Item | sites/1232505342/CMiC RFI Response | 0198
21029900-0197 | Electrical CPK03 R3 MSB - Equipment Tag Confirmation | RFI-0197 Electrical CPK03 R3 MSB - Equipment Tag Confirmation Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44592.6334 | Item | sites/1232505342/CMiC RFI Response | 0197
21029900-0196 | Wet Mech - MSB - CPK03-R2 - Branch Order Discrepancy Between P&ID and BIM Model | RFI-196 - Wet Mech - MSB - CPK03-R2 - Branch Order PID_vs_BIMRESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44622.5437 | Item | sites/1232505342/CMiC RFI Response | 0196
21029900-0195 | Wet Mech - MSB - CPK03-R2 - CUB-4 CHW Pump FNPT Cap vs. H-1 | RFI-195 - Wet Mech - MSB - CPK03-R2 - CUB-4 CHW Pump FNPT Cap vs. H-1RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40051521 | 44622.5421 | Item | sites/1232505342/CMiC RFI Response | 0195
21029900-0194 | Wet Mech - MSB - CPK03-R2 - MS1-113-D0-Z05 Line Numbering | RFI-194 - Wet Mech - MSB - CPK03-R2 - MS1-113-D0-Z05 Line NumberingRESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44622.5438 | Item | sites/1232505342/CMiC RFI Response | 0194
21029900-0193 | Wet Mech - MSB - CPK03-R2 - CHW Pump SSP-3 versus SPP-3 | RFI-0193 - Wet Mech - MSB - CPK03-R2 - CHW Pump SSP-3 versus SPP-3RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44622.5434 | Item | sites/1232505342/CMiC RFI Response | 0193
21029900-0192 | Wet Mech - MSB - CPK03-R2 - CHWS Drawing Continuation Clarification | RFI-192 - Wet Mech - MSB - CPK03-R2 - CHWS Drawing Continuation ClarificationRESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44622.5417 | Item | sites/1232505342/CMiC RFI Response | 0192
21029900-0191 | I&C- MSB1-CPK03-R2- Missing Data Sheet PMP272-(16-17-18)-40 | RFI-191 - I_C - MSB - CPK03-R2 - Missing Data Sheet PMP272RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44622.5418 | Item | sites/1232505342/CMiC RFI Response | 0191
21029900-0190 | Electrical CPK03 R2/CPK03 R3 MSB - Panelboard MXD2R50A Confirmation | RFI-00190 Electrical CPK03 R2-CPK03 R3 MSB - Panelboard MXD2R50A Confirmation Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 26_24_16_43 | 44585.477 | Item | sites/1232505342/CMiC RFI Response | 0190
21029900-0188 | Wet Mech - MSB - CPK03-R2 - BA-5 vs BF-3 on 3" ADA CHWS/R Laterals | RFI-0188 - Wet Mech - MSB - CPK03-R2 - BA-5 vs BF-3 on 3IN ADA CHWSR LateralsRESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40051651 | 44621.7111 | Item | sites/1232505342/CMiC RFI Response | 0188
21029900-0187 | Structural - RA4 - CPK02-R3 - Pipe Support Model Discrepancy | RFI-0187 Structural - RA4 - CPK02-R3 - Pipe Support Model Discrepancy RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44589.4072 | Item | sites/1232505342/CMiC RFI Response | 0187
21029900-0186 | LSS - RA4 - CPK02-R3 - Missing VESDA Drawings | RFI-0186 LSS - RA4 - CPK02-R3 - Missing VESDA Drawings RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44589.4078 | Item | sites/1232505342/CMiC RFI Response | 0186
21029900-0185 | Process - RA4 - CPK02-R2 - TCHW Coil Isolation for Future Scope | RFI-0185 Process - RA4 - CPK02-R2 - TCHW Coil Isolation for Future Scope RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44581.8614 | Item | sites/1232505342/CMiC RFI Response | 0185
21029900-0184 | Wet Mech - MSB - CPK03-R2 - Cooling Coil Mounting Details | RFI-0184 - Wet Mech - MSB - CPK03-R2 - Cooling Coil Mounting DetailsRESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44621.711 | Item | sites/1232505342/CMiC RFI Response | 0184
21029900-0183 | Wet Mech - MSB - CPK03-R2 - Missing Detail RA-PL-D105 | RFI-0183 - Wet Mech - MSB - CPK03-R2 - Missing Detail RA-PL-D105RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44621.7113 | Item | sites/1232505342/CMiC RFI Response | 0183
21029900-0182 | Wet Mech - MSB - CPK03-R2 - CUB4 CHW Pump Suction Diffuser Specification | RFI-0182 - Wet Mech - MSB - CPK03-R2 - CUB4 CHW PUMP SUCTION DIFFUSER SPEC_RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40051521 | 44621.6887 | Item | sites/1232505342/CMiC RFI Response | 0182
21029900-0177 | CSA - Structural - CPK02-R1 - Bolted Column Splice Alternative | RFI-0177 - CSA - Structural - CPK02-R1 - Bolted Column Splice Alternative.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | SOWLES CO DBA SOWLES STEEL ERECTORS (Kyle Wilcox) |  | 44608.7063 | Item | sites/1232505342/CMiC RFI Response | 0177
21029900-0176 | CSA - MSB - CPK03R2 - Wall Type Clarification | RFI-0176 - CSA - MSB - CPK03-R2 - Wall Type Clarification RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | PERFORMANCE CONTRACTING INC (Grayson Sorenson) |  | 44614.5526 | Item | sites/1232505342/CMiC RFI Response | 0176
21029900-0174 | Mechanical - CPK03-R1 - MSB - Harder RFIs 5-6 - GA-11 Valve and Clarifications | RFI-0174 - Mechanical - MSB - CPK03-R1 - Harder RFIs Valve and Clarifications RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40051531 | 44622.5443 | Item | sites/1232505342/CMiC RFI Response | 0174
21029900-0167 | Mech.Electrical.LSS.Telecom.IandC - CPK02-R2 RA4 - RAH 9-13 Conflicts | RFI-0167 Mech.Electrical.LSS.Telecom.IandC - CPK02-R2 RA4 - RAH 9-13 Conflicts RESPONSE.pdf | Answered - Complete | OEG INC (Riley Loyd) |  |  | 44615.8353 | Item | sites/1232505342/CMiC RFI Response | 0167
21029900-0166 | Structural - MSB - CPK03-R2- MS1-SS-2FM-B0300 TOS Elevations | RFI-0166 Structural - MSB - CPK03-R2- MS1-SS-2FM-B0300 TOS Elevations.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44621.5068 | Item | sites/1232505342/CMiC RFI Response | 0166
21029900-0166 | Structural - MSB - CPK03-R2- MS1-SS-2FM-B0300 TOS Elevations | RFI-0166 - Structural - MSB - CPK03-R2 - TOS ELEVATIONS_RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44621.5055 | Item | sites/1232505342/CMiC RFI Response | 0166
21029900-0165 | Structural - MSB- CPK03-R5 RA-ST-2043 Alt Welded Connection | RFI-0165 Structural - MSB- CPK03-R5 RA-ST-2043 Alt Welded Connection.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | SOWLES CO DBA SOWLES STEEL ERECTORS (Kyle Wilcox) |  | 44588.702 | Item | sites/1232505342/CMiC RFI Response | 0165
21029900-0164 | Structural - RA4 - CPK02 - Field Condition Stanchion Conflict | RFI-0164 Structural - RA4 - CPK02 - Field Condition Stanchion Conflict.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44615.4405 | Item | sites/1232505342/CMiC RFI Response | 0164
21029900-0161 | Dry Mech-CPK02-R2-RA4-Duct Supports From New HSS Steel Confirmation. | RFI-0161 Dry Mech-CPK02-R2-RA4-Duct Supports From New HSS Steel Confirmation.pdf | Pending | JACOBS ENGINEERING GROUP INC (Document Control) | APOLLO INC (Evan Lehman) |  | 44572.6957 | Item | sites/1232505342/CMiC RFI Response | 0161
21029900-0159 | I and C - MSB1-CPK03R2-TE218-0-08A - Threaded to Welded | RFI-0159 - I and C - MSB1 - CPK03R2-TE218-0-08A RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44614.5539 | Item | sites/1232505342/CMiC RFI Response | 0159
21029900-0158 | Control Valves-MSB-LLP02/CPK03 R2-Damper Size Change Confirmation | RFI-0158 Control Valves-MSB-LLP02-CPK03 R2-Damper Size Change Confirmation RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40051534 | 44586.482 | Item | sites/1232505342/CMiC RFI Response | 0158
21029900-0157 | Dry Mech-CPK02-R2-RA4 Table for Spring Isolators Confirmation | RFI-0157 Dry Mech-CPK02-R2-RA4 Table for Spring Isolators Confirmation RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | APOLLO INC (Evan Lehman) | 40_05_16(15071) | 44586.4586 | Item | sites/1232505342/CMiC RFI Response | 0157
21029900-0155 | Dry Mech- CPK02-R2-RA4-Spring Isolation on RAH Recirculation Air Design | RFI-0155 Dry Mech-CPK02-R2-RA4- Spring Isolation on RAH Recirculation Air Design RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | APOLLO SHEET METAL INC (Shawn Aasheim) | 40_05_15_16 | 44595.716 | Item | sites/1232505342/CMiC RFI Response | 0155
21029900-0154 | TEST RFI | RFI-0154 TEST RFI RESPONSE.pdf | Answered - Complete | JE Dunn |  |  | 44596.5774 | Item | sites/1232505342/CMiC RFI Response | 0154
21029900-0153 | Structural - MSB - CPK03-R5 Below Roof Upgrade Conflicts | RFI-0153 Structural - MSB - CPK03-R5 Below Roof Upgrade Conflicts.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | SOWLES CO DBA SOWLES STEEL ERECTORS (Kyle Wilcox) |  | 44588.702 | Item | sites/1232505342/CMiC RFI Response | 0153
21029900-0153 | Structural - MSB - CPK03-R5 Below Roof Upgrade Conflicts | RFI-0153 Structural - MSB - CPK03-R5 Below Roof Upgrade Conflicts (1295039716).pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | SOWLES CO DBA SOWLES STEEL ERECTORS (Kyle Wilcox) |  | 44588.7025 | Item | sites/1232505342/CMiC RFI Response | 0153
21029900-0151 | Structural - RA4 - CPK02-R2 - Washer Dimensions | RFI-0151 Structural - RA4 - CPK02-R2 - Washer Dimensions RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | ADVANCED TECHNOLOGY GROUP INC (Matthew Sutherland) |  | 44571.7157 | Item | sites/1232505342/CMiC RFI Response | 0151
21029900-0145 | I and C- MSB1-CPK03-R2- Outdated transmitters | RFI-0145 - Electrical - MSB - CPK03-R2 - Outdated TransmittersRESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | EC ELECTRIC INC (sylvia ashley) |  | 44615.7246 | Item | sites/1232505342/CMiC RFI Response | 0145
21029900-0144 | Dry Mech-CPK02-R2-RA4 Air Coils Fluid Temp Change Confirmation | RFI-0144 Dry Mech-CPK02-R2-RA4 Air Coils Fluid Temp Change Confirmation RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 23_82_16_61 | 44595.7127 | Item | sites/1232505342/CMiC RFI Response | 0144
21029900-0143 | Electrical- MSB - Luminaire Screw Clamp Detail RAC-EL-D034 | RFI-0043 Electrical-MSB-Luminaire Screw Clamp Detail RAC-EL-D034 Response.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44581.6439 | Item | sites/1232505342/CMiC RFI Response | 0143
21029900-0139R1 | I&C - CPK02-R2 - CPK07 - RA4 - RIO650-1B-07 Package Verification - R1 | RFI-0139R1-IandC-CPK02-R2-CPK07-RA4-RIO650-1B-07 Package Verification RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 25_14_04_00_DAT | 44572.6294 | Item | sites/1232505342/CMiC RFI Response | 0139R1
21029900-0139 | I&C - CPK02-R2 - CPK07 - RA4 - RIO650-1B-07 Package Verification | RFI-0139 - I and C - CPK02-R2 - CPK07 - RA4 - RIO650-1B-07 Package Verification.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 25_14_04_00_DAT | 44565.4581 | Item | sites/1232505342/CMiC RFI Response | 0139
21029900-0133 | Electrical MSB - CPK03 R2- MSB1-RIO650-102-04 Relocation | RFI-0133 - Electrical - MSB - CPK03 R2 - MSB1-RIO650-102-04 RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44614.5523 | Item | sites/1232505342/CMiC RFI Response | 0133
21029900-0132 | I and C - CPK02-R2 RA4 - PDIT and TET Instruments on Column Discrepancy | RFI-0132 I and C - CPK02-R2 RA4 - PDIT and TET Instruments on Column Discrepancy RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | OEG INC (Nathan Trtek) |  | 44585.6201 | Item | sites/1232505342/CMiC RFI Response | 0132
21029900-0131 | Electrical MSB - CPK03 R2- RIO650-101-04 Relocation | RFI-0131 - Electrical - MSB - CPK03-R2 - RIO650-101-04 Relocation RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44613.7275 | Item | sites/1232505342/CMiC RFI Response | 0131
21029900-0130 | Wet Mechanical - RA4 - CPK02-R2 - BMWC RFI's | RFI-0130 Wet Mechanical - RA4 - CPK02-R2 - BMWC RFIs RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44575.5233 | Item | sites/1232505342/CMiC RFI Response | 0130
21029900-0129 | Telecom/Mechanical CPK02-R2 RA4 - Level 1 Telecom and Ductwork Conflicts | RFI-0129 - Telecom.Mechanical CPK02-R2 RA4 - Level 1 Telecom and Ductwork Conflicts RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44583.5003 | Item | sites/1232505342/CMiC RFI Response | 0129
21029900-0128R1 | Process - RA4 - CPK02-R2 - BMWC RFI's | RFI-0128R1 - Process - RA4 - CPK02-R2 - BMWC RFIs - RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44614.5171 | Item | sites/1232505342/CMiC RFI Response | 0128R1
21029900-0128 | Process - RA4 - CPK02-R2 - BMWC RFI's | RFI-0128 Process - RA4 - CPK02-R2 - BMWC RFIs - RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44575.5232 | Item | sites/1232505342/CMiC RFI Response | 0128
21029900-0127 | Structural - RA4 - CPK02-R2 - Gyp Board Thickness | RFI-0127 Structural - RA4 - CPK02-R2 - Gyp Board Thickness RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44566.764 | Item | sites/1232505342/CMiC RFI Response | 0127
21029900-0126 | Structural - RA4 - CPK02-R2 - General Notes Reference | RFI-0126 Structural - RA4 - CPK02-R2 - General Notes Reference RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44566.7297 | Item | sites/1232505342/CMiC RFI Response | 0126
21029900-0124-R1 | CSA-CPK02-R2-Sheet Metal Sheathing Type Confirmation | RFI-0124-R1-CSA-CPK02-R2-Sheet Metal Sheathing Type Confirmation RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44606.5757 | Item | sites/1232505342/CMiC RFI Response | 0124-R1
21029900-0124 | Structural - RA4 - CPK02-R2 - Sheet Metal Sheathing Install | RFI-0124 Structural - RA4 - CPK02-R2 - Sheet Metal Sheathing Install RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44566.6476 | Item | sites/1232505342/CMiC RFI Response | 0124
21029900-0123 | Structural - RA4 - CPK02-R2 - Seismic Cable Sizing | RFI-0123_Structural - RA4 - CPK02-R2 - Seismic Cable Sizing RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44565.6428 | Item | sites/1232505342/CMiC RFI Response | 0123
21029900-0122 | Structural - MSB - CPK03-R5 IFC- Revised Drawings | RFI-0122 Structural - MSB - CPK03-R5 IFC- Revised Drawings.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44588.695 | Item | sites/1232505342/CMiC RFI Response | 0122
21029900-0119 | Process - MSB - CPK03-R2 - Charter P&ID vs Model Clarification | RFI-0119 - Process - MSB - CPK03-R2 - Charter PID vs Model Clarifications Reponse.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44609.7474 | Item | sites/1232505342/CMiC RFI Response | 0119
21029900-0118 | Mechanical - CPK03-R2 - GMAH and GAH Riser | RFI0118 - Mechanical - CPK03-R2 - GMAH and GAH Riser - Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44614.553 | Item | sites/1232505342/CMiC RFI Response | 0118
21029900-0117 | HVAC--LLP02-MSB- TCHW TCV | RFI-0117 - Mechanical - MSB - LLP02 - TCHW TCV RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40_05_15_34 | 44613.5358 | Item | sites/1232505342/CMiC RFI Response | 0117
21029900-0114 | Electrical MSB-CPK03-MAH Evaporator circuits LCP101-7-50A EVAP & LCP101-8-50A EVAP | RFI-0144 - Electrical - MSB - CPK03 - MAH Evaporator circuits RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | QUALITY PLUS SERVICES INC (Megan Ives) |  | 44614.5172 | Item | sites/1232505342/CMiC RFI Response | 0114
21029900-0113 | CSA - MSB - CPK03-R2 IFC - Existing Wall Clarification | RFI-0113 CSA - MSB - CPK03-R2 IFC - Existing Wall Clarification.pdf | Open | JACOBS ENGINEERING GROUP INC (Document Control) | PERFORMANCE CONTRACTING INC (Grayson Sorenson) |  | 44582.5783 | Item | sites/1232505342/CMiC RFI Response | 0113
21029900-0113 | CSA - MSB - CPK03-R2 IFC - Existing Wall Clarification | RFI-0113 - CSA - MSB - CPK03-R2 - Existing Wall Clarification RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | PERFORMANCE CONTRACTING INC (Grayson Sorenson) |  | 44609.7084 | Item | sites/1232505342/CMiC RFI Response | 0113
21029900-0112 | Electrical- CPK03- MSB- AHU Alternate Feeder Route | RFI-0112 Electrical- CPK03- MSB- AHU Alternate Feeder Route - Response.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44610.5373 | Item | sites/1232505342/CMiC RFI Response | 0112
21029900-0110 | CSA-MSB – CPK01-R2 Shop Welded Strut Type | RFI-0110 CSA-MSB CPK01-R2 Shop Welded Strut Type- RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | SOWLES CO DBA SOWLES STEEL ERECTORS (Kyle Wilcox) |  | 44588.6956 | Item | sites/1232505342/CMiC RFI Response | 0110
21029900-0109 | Mechanical - CPK03 - MSB - GMAH103-0-00 Piping Connection Sizes | RFI-0109 - Mechanical - MSB - CPK03 - GMAH103-0-00 Piping Connection Sizes.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44614.515 | Item | sites/1232505342/CMiC RFI Response | 0109
21029900-0108 | CSA - MSB - CPK03-R2 IFC - High Bay Clarification | RFI-0108 CSA - MSB - CPK03-R2 IFC - High Bay Clarification.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | PERFORMANCE CONTRACTING INC (Matthew Reinert) |  | 44613.4009 | Item | sites/1232505342/CMiC RFI Response | 0108
21029900-0104 | Mechanical - CPK03-R2 - PMP111-17-00 10% Head Increase Spec Deviation | RFI-0104 - Mechanical - CPK03-R2 - PMP111-17-00 10 Head Increase Spec Dev Response.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn | 40051551 | 44609.6872 | Item | sites/1232505342/CMiC RFI Response | 0104
21029900-0102 | Mech- CSA - CPK02 RA4 Handrail Modification | RFI-0102 Mech-CSA-CPK02 RA4 Handrail Modification RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44607.4337 | Item | sites/1232505342/CMiC RFI Response | 0102
21029900-0101 | CSA - CPK02-01 - Columns on RA4-SS-4RB-K0000 Confirmation | RFI-0101 CSA - CPK02-01 - Columns on RA4-SS-4RB-K0000 Confirmation.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | SOWLES CO DBA SOWLES STEEL ERECTORS (Kyle Wilcox) |  | 44582.5718 | Item | sites/1232505342/CMiC RFI Response | 0101
21029900-0100 | Electrical-OHIEX-R-B0001-CPK03-RIO 650_1B_01 | RFI-0100 - Electrical - MSB - CPK03 - RIO 650_1B_01 RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44614.5147 | Item | sites/1232505342/CMiC RFI Response | 0100
21029900-0099 | Electrical CPK03-R2 MSB PDIT Equipment Order/Not Order | RFI-0099 - Electrical - MSB - CPK03-R2 - PDIT Equipment Order_Not Order RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 25_14_01_00 | 44609.4632 | Item | sites/1232505342/CMiC RFI Response | 0099
21029900-0098 | CSA - CPK02-R2 - Dots on HSS Cups and Beams Clarification | RFI-0098 CSA - CPK02-R2 - Dots on HSS Cups and Beams Clarification.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | SOWLES CO DBA SOWLES STEEL ERECTORS (Kyle Wilcox) |  | 44588.6949 | Item | sites/1232505342/CMiC RFI Response | 0098
21029900-0097 | Process - MSB and RA4 - OFA Laterals | RFI-0097 Process - MSB and RA4 - OFA Laterals RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn | 40_05_16_32 | 44538.5967 | Item | sites/1232505342/CMiC RFI Response | 0097
21029900-0096R2 | Mech-Process-Elec-CSA-CPK02/CPK02-R2-RA4-South-MAU Penetrations Clashes and Relocations | RFI-0096R2-Mech-Proc-Elec-CPK02-CPK02-R2-South-MAU Penetrations Clashes and Relocation RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 233113 | 44622.7586 | Item | sites/1232505342/CMiC RFI Response | 0096R2
21029900-0096R1 | Mech-Process-Elec-CSA-CPK02/CPK02-R2-RA4 MAU Penetrations Clashes and Relocations | RFI-0096R1_Mech-Process-Elec-CPK02-CPK02-R2-MAU Penetrations Clashes and Relocation RESPONSE.pdf | Pending | JACOBS ENGINEERING GROUP INC (Document Control) |  | 233113 | 44586.4583 | Item | sites/1232505342/CMiC RFI Response | 0096R1
21029900-0096 | Mechanical-CPK02-R2 RA4 MAU Penetrations Clashes and Relocation | RFI-0096 Mechanical-CPK02-R2 RA4 MAU Penetrations Clashes and Relocation RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | STREIMER SHEET METAL WORKS INC (Jeff Vian) | 233113 | 44595.7058 | Item | sites/1232505342/CMiC RFI Response | 0096
21029900-0095 | CSA - MSB - CPK03-IFC - Existing Pedestal Connections | RFI-0095 CSA - MSB - CPK03-IFC - Existing Pedestal Connections - RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44588.6957 | Item | sites/1232505342/CMiC RFI Response | 0095
21029900-0093 | Mechanical-CPK02-R1-RA4 Make Up Air Flex | RFI-0093 Mechanical-CPK02-R1-RA4 Make Up Air Flex.pdf | Open | JACOBS ENGINEERING GROUP INC (Document Control) | STREIMER SHEET METAL WORKS INC (Jeff Vian) |  | 44533.3129 | Item | sites/1232505342/CMiC RFI Response | 0093
21029900-0093 | Mechanical-CPK02-RA4 Make Up Air Flex Confirmation | RFI-0093 Mechanical-CPK02-RA4 Make Up Air Flex Confirmation RESPONSE (1284011460).pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | STREIMER SHEET METAL WORKS INC (Jeff Vian) |  | 44595.702 | Item | sites/1232505342/CMiC RFI Response | 0093
21029900-0092 | CSA - MSB - CPK03 IFC- MSB Base Build - Architectural Detail Reference | PM3010_2021_12_01__18_02_07.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44566.5112 | Item | sites/1232505342/CMiC RFI Response | 0092
21029900-0092 | CSA - MSB - CPK03 IFC- MSB Base Build - Architectural Detail Reference | RFI-0092 CSA - MSB - CPK03 IFC- MSB Base Build - Architectural Detail Reference- RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44566.5111 | Item | sites/1232505342/CMiC RFI Response | 0092
21029900-0091 | Electrical-LLE01 RA4 Field ETAP Panels Count Confirmation | RFI-0091 Electrical-RA4 Field ETAP Panels Count Confirmation RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 25_14_01_00 | 44538.6982 | Item | sites/1232505342/CMiC RFI Response | 0091
21029900-0089 | Mechanical - LLP02 - RA4 - RAH Submittal Approval | RFI-0089 Mechanical - LLP02 - RA4 - RAH Submittal Approval RESPONSE.pdf | Closed | INTEL NETWORK SYSTEMS INC (Chris Van Zee) | JE Dunn | 45431367 | 44595.6895 | Item | sites/1232505342/CMiC RFI Response | 0089
21029900-0087 | CSA - MSB - CPK03R2 - 2FA Full Height GWB Wall at GL J.3 | RFI-0087 CSA - MSB - CPK03R2 - 2FA Full Height GWB Wall at GL J.3.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | PERFORMANCE CONTRACTING INC (AJ Therrien) |  | 44599.6813 | Item | sites/1232505342/CMiC RFI Response | 0087
21029900-0086 | Process - CPK03-R1 - MSB - HRW Pipe Support Clarifications | RFI-0086 Process - CPK03-R1 - MSB - HRW Pipe Support Clarifications RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | HARDER MECHANICAL CONTRACTORS INC (Kayleigh Arendt) |  | 44531.6643 | Item | sites/1232505342/CMiC RFI Response | 0086
21029900-0085 | Process - CPK01-R2 - MSB - UN2 and HPO2 Purge Port Valve Assemblies | RFI-0085 Process - CPK01-R2 - MSB - UN2 and HPO2 Purge Port Valve Assemblies RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44531.6542 | Item | sites/1232505342/CMiC RFI Response | 0085
21029900-0084 | Mechanical - CPK03 - MSB - Level 2 AB South Duct Change | RFI-0084 Mechanical - CPK03 - MSB - Level 2 AB South Duct Change RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44531.652 | Item | sites/1232505342/CMiC RFI Response | 0084
21029900-0082 | CSA - CPK02-R2-AT90 - CRC Type Confirmation | RFI-0082 CSA - CPK02-R2-AT90 - CRC Type Confirmation.pdf | Void | JACOBS ENGINEERING GROUP INC (Document Control) |  | 09617800 | 44613.4967 | Item | sites/1232505342/CMiC RFI Response | 0082
21029900-0081 | Electrical - CPK02 RA4 - Sizing for Feeder K3 from XR4D2E32C to XR4T4J12C | RFI-0081 Electrical - CPK02 RA4 - Sizing for Feeder K3 from XR4D2E32C to XR4T4J12C RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | QUALITY PLUS SERVICES INC (Megan Ives) | 26_24_16_43_DAT | 44615.7825 | Item | sites/1232505342/CMiC RFI Response | 0081
21029900-0080 | Mechanical-CPK01-R1-MSB Demo Enabling Spot Cooling Confirmation | RFI-0080 Mechanical-CPK01-R1-MSB Demo Enabling Spot Cooling Confirmation.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44588.6857 | Item | sites/1232505342/CMiC RFI Response | 0080
21029900-0079 | LLP02 CPK02 R2/CPK03 R2 Rotork Actuators from EPC - Quantity and Size Verification | RFI-0079 - MSB_RA4 - LLP02_CPK02-R2_CPK03-R3 - Rotork Actuators from EPC RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40_05_15_34 | 44610.7104 | Item | sites/1232505342/CMiC RFI Response | 0079
21029900-0078 | LLP02 CPK02 R2/CPK03 R2 Rotork Actuators from Fabtech - Quantity and Size Verification | RFI-0078 - MSB_RA4 - LLP02_CPK02-R2_CPK03-R3 - Rotork Actuators from EPC RESPONSE.pdf | Void | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40_05_15_34 | 44610.7126 | Item | sites/1232505342/CMiC RFI Response | 0078
21029900-0077 | Structural-Mechanical - RA4 -CPK02-R1 Additional Framing Support for MAH Duct | RFI-0077 Structural-Mechanical - RA4 -CPK02-R1 Additional Framing Support for MAH Duct RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44586.3981 | Item | sites/1232505342/CMiC RFI Response | 0077
21029900-0076 | I and C - LLE01 - RA4-MSB Stratix Ethernet Switch EOL Replacement | RFI-0076 I and C - LLE01 - RA4-MSB Stratix Ethernet Switch EOL Replacement RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 25_14_01_00_APP_ | 44606.2209 | Item | sites/1232505342/CMiC RFI Response | 0076
21029900-0075 | Structural - MSB - CPK01-R2 Subfab Steel - Grid Alignment Vs Survey Points | RFI-0075_Structural - MSB - CPK01-R2 Subfab Steel - Grid Alignment Vs Survey Points RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44516.6775 | Item | sites/1232505342/CMiC RFI Response | 0075
21029900-0074 | Mechanical - CPK03-R2 - MSB - HXRA unit VFDs | RFI-0074 Mechanical - CPK03-R2 - MSB - HXRA unit VFDs RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 45_43_13_67 | 44582.5889 | Item | sites/1232505342/CMiC RFI Response | 0074
21029900-0073 | CSA - CPK02-R2 - RA4 - Slotted Holes in HSS Beams Confirmation | RFI-0073 CSA - CPK02-R2 - RA4 - Slotted Holes in HSS Beams Confirmation.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | SOWLES CO DBA SOWLES STEEL ERECTORS (Kyle Wilcox) |  | 44588.6783 | Item | sites/1232505342/CMiC RFI Response | 0073
21029900-0072 | CSA - CPK02-R2 - RA4 - Adjustability of HSS10x6 Cups Confirmation | RFI-0072 CSA - CPK02-R2 - RA4 - Adjustability of HSS10x6 Cups Confirmation RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) | SOWLES CO DBA SOWLES STEEL ERECTORS (Kyle Wilcox) |  | 44585.5393 | Item | sites/1232505342/CMiC RFI Response | 0072
21029900-0071 | CSA - MSB - CPK03R2 - All Thread Rod Lengths (M10 &M16) | RFI-0071 CSA - MSB - CPK03R2 - All Thread Rod Lengths M10 and M16.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44582.5658 | Item | sites/1232505342/CMiC RFI Response | 0071
21029900-0070 | Process - LLP02 - LLP02R1 - Valve Matrix | RFI-0070 - Process - MSB_RA4 - LLP02_LLP02-R1 - Valve Matrix.pdf | Closed | INTEL NETWORK SYSTEMS INC (Mark Harrington) |  |  | 44609.7857 | Item | sites/1232505342/CMiC RFI Response | 0070
21029900-0069 | Mechanical - LLP02 - MSB - ATTD and IMO Dry Cooling Coil Quantity | RFI-0069 Mechanical - LLP02 - MSB - ATTD and IMO Dry Cooling Coil Quantity RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 23821661 | 44588.72 | Item | sites/1232505342/CMiC RFI Response | 0069
21029900-0068 | Process - LLP02-R1 - MSB - Carbonator Performance Spec Alignment | RFI-0068 Process - LLP02-R1 - MSB - Carbonator Performance Spec Alignment.pdf | Answered - Complete | INTEL NETWORK SYSTEMS INC (Mark Harrington) |  |  | 44589.778 | Item | sites/1232505342/CMiC RFI Response | 0068
21029900-0067 | CSA - MSB - CPK01R1 - Fire Rating Wall Patch Confirmation | RFI-0067 CSA - MSB - CPK01R1 - Fire Rating Wall Patch Confirmation RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | ADVANCED TECHNOLOGY GROUP INC (Trylan Wassmann) |  | 44531.6398 | Item | sites/1232505342/CMiC RFI Response | 0067
21029900-0066 | Structural - CPK01-R2 - MSB Beam Layout Level 1 GRID AE_56-57 | RFI-0066 Structural - CPK01-R2 - MSB Beam Layout Level 1 GRID AE_56-57 RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44531.6309 | Item | sites/1232505342/CMiC RFI Response | 0066
21029900-0065 | LLP03 – PSSS – MSB - Analyzer Panel Name Confirmation | RFI-0065 LLP03 PSSS MSB - Analyzer Panel Name Confirmation RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44586.6681 | Item | sites/1232505342/CMiC RFI Response | 0065
21029900-0064 | Mechanical - CPK03-R2 - MSB - HXRA Unit Scope Inclusion | RFI-0064 Mechanical - CPK03-R2 - MSB - HXRA Unit Scope Inclusion RESPONSE.pdf | Closed | INTEL NETWORK SYSTEMS INC (Mark Harrington) |  | 45_43_13_67 | 44531.6255 | Item | sites/1232505342/CMiC RFI Response | 0064
21029900-0063 | Electrical - LLP02 - RA4/MSB - TCHW Pumps | RFI-0063 Electrical-LLP02-RA4-MSB - TCHW Pumps RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40_05_15_51 | 44586.6606 | Item | sites/1232505342/CMiC RFI Response | 0063
21029900-0062 | Process - MSB - CPK01R1 - FPN2 Valve Clarification | RFI-0062 Process - MSB - CPK01R1 - FPN2 Valve Clarification RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44531.61 | Item | sites/1232505342/CMiC RFI Response | 0062
21029900-0060R1 | Process - LLP02 - RA4 BCS Pumps PMP252-1-40 and PMP252-2-40 - Duty Point - R1 | RFI-0060R1 Process - LLP02 - RA4 BCS Pumps PMP252-1-40 and PMP252-2-40 - Duty Point - R1 RESP.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40_05_15_51 | 44617.7835 | Item | sites/1232505342/CMiC RFI Response | 0060R1
21029900-0060 | Process - LLP02 - RA4 BCS Pumps PMP252-1-40 and PMP252-2-40 - Duty Point | RFI-0060 Process - LLP02 - RA4 BCS Pumps PMP252-1-40 and PMP252-2-40 - Duty Point RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40_05_15_51 | 44592.7335 | Item | sites/1232505342/CMiC RFI Response | 0060
21029900-0059 | Structural - MSB - CPK03 - Beam to Beam Moment Connection - Roof Level 5RF | RFI-0059 MSB CPK03 - Beam Moment Connection at Roof - Response.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44565.464 | Item | sites/1232505342/CMiC RFI Response | 0059
21029900-0058 | Process - LLE01 - CPCW Heat Exchanger Dimensions | RFI-0058 Process - LLE01 - CPCW Heat Exchanger Dimensions RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 42_13_10_66 | 44586.633 | Item | sites/1232505342/CMiC RFI Response | 0058
21029900-0057 | Process - LLP02R1 - Valve Spec Change | RFI-0057 Process - LLP02R1 - Valve Spec Change RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40_05_15_32 | 44586.6331 | Item | sites/1232505342/CMiC RFI Response | 0057
21029900-0056R3 | Process - LLP02 - LLP02R1 - Valve Matrix - REV 3 | RFI-0056R3 - Process - MSB_RA4 - LLP02_LLP02R1 - Valve Matrix RESPONSE.pdf | Closed | INTEL NETWORK SYSTEMS INC (Mark Harrington) | JE Dunn |  | 44609.7162 | Item | sites/1232505342/CMiC RFI Response | 0056R3
21029900-0056R2 | Process - LLP02 - LLP02R1 - Valve Matrix | RFI-0056R2 Process - LLP02 - LLP02R1 - Valve Matrix RESPONSE.pdf | Closed | INTEL NETWORK SYSTEMS INC (Mark Harrington) |  |  | 44595.4452 | Item | sites/1232505342/CMiC RFI Response | 0056R2
21029900-0056R1 | Process - LLP02 - LLP02R1 - Valve Matrix-R1 | RFI-0056R1 Process - LLP02 - LLP02R1 - Valve Matrix-R1 RESPONSE.pdf | Closed | INTEL NETWORK SYSTEMS INC (Mark Harrington) |  |  | 44586.6245 | Item | sites/1232505342/CMiC RFI Response | 0056R1
21029900-0056 | Process - LLP02 - LLP02R1 - Valve Matrix | RFI-0056 Process - LLP02 - LLP02R1 - Valve Matrix RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44586.6244 | Item | sites/1232505342/CMiC RFI Response | 0056
21029900-0055R1 | CSA - CPK02-R2-AT30 - Eyxte Threaded Steel Rod Confirmation R1 | RFI-0055R1 -CSA - CPK02-R2-AT30 - Eyxte Threaded Steel Rod Confirmation R1.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 055000 | 44585.5391 | Item | sites/1232505342/CMiC RFI Response | 0055R1
21029900-0053 | Mechanical – LLP02 – TCHW Pumps MSB and RA4 | RFI-0053 Mechanical LLP02 TCHW Pumps MSB and RA4 RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40_05_15_51 | 44586.6243 | Item | sites/1232505342/CMiC RFI Response | 0053
21029900-0051 | Process - LLE01 - RA4 - BCS Tank Dimension diameter and height conformation | RFI-0051 Process-LLE01-RA4-BCS Tank Dimension diameter and height conformation RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44586.6237 | Item | sites/1232505342/CMiC RFI Response | 0051
21029900-0050 | MSB West Door Logistics Modifications -Proposed Stud Alternate | RFI-0050 MSB West Door Logistics Modifications -Proposed Stud Alternate RESPONSE.pdf | Answered - Complete | GLUMAC (Mike Colligan) |  |  | 44586.6238 | Item | sites/1232505342/CMiC RFI Response | 0050
21029900-0049 | CSA - CPK02-R2-AT30 - Steel Support Questions for Exyte Ceiling Grid Coordination (Part 2) | RFI-0049 CSA-CPK02-R2-AT30-Steel Support for Exyte Ceiling Grid Coordination P2 RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) | JE Dunn |  | 44586.6238 | Item | sites/1232505342/CMiC RFI Response | 0049
21029900-0048 | Process - FIT and Pipe Size Conformation | RFI-0048 Process - FIT and Pipe Size Conformation RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44531.4985 | Item | sites/1232505342/CMiC RFI Response | 0048
21029900-0047 | Process - CPK01 R2 - HP02 Tie Point Conformation | RFI-0047 Process - CPK01 R2 - HP02 Tie Point Conformation RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44531.4555 | Item | sites/1232505342/CMiC RFI Response | 0047
21029900-0046 | Process - CPK01 R2 - HP02 Line Size Valve | RFI-0046 Process - CPK01 R2 - HP02 Line Size Valve RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44531.4552 | Item | sites/1232505342/CMiC RFI Response | 0046
21029900-0044 | CSA - CPK02-R2-AT30 - Layout for Exyte Ceiling Grid Anchor Rods | RFI-0044 CSA - CPK02-R2-AT30 - Layout for Exyte Ceiling Grid Anchor Rods RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44531.6949 | Item | sites/1232505342/CMiC RFI Response | 0044
21029900-0043 | Structural - CPK01-R2 - MSB Shared Rack Strut Elevation- VOID | RFI-0043Structural - CPK01-R2 - MSB Shared Rack Strut Elevation- VOID.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44530.3412 | Item | sites/1232505342/CMiC RFI Response | 0043
21029900-0042 | Mechanical - Eletrical - LLP02 – RA4 and MSB PMP113 Tagging | RFI-0042_Mech-Elect- LLP02RA4-MSB PMP113 Tagging_RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44586.6242 | Item | sites/1232505342/CMiC RFI Response | 0042
21029900-0041 | Mechanical - InC - LLE01 - Silicon Water Treatment Lift Pumps | RFI-0041 Mechanical - InC - LLE01 - Silicon Water Treatment Lift Pumps RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 26_29_65 | 44586.5515 | Item | sites/1232505342/CMiC RFI Response | 0041
21029900-0040 | Mech, InC, Electric-LLE01-Critical Process Cooling Water Circulation Pumps 202-1-10, 202-2-10, 202-3-10 | RFI-0040 Mech_InC_Electrical_LLE01_Critical_Process_Cooling_Water_Circulation_Pumps_RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44586.6234 | Item | sites/1232505342/CMiC RFI Response | 0040
21029900-0039 | Mechanical - LLP02 - Manufacturer specification change | RFI-0039 Mechanical - LLP02 - Manufacturer specification change RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40_05_15_34 | 44519.612 | Item | sites/1232505342/CMiC RFI Response | 0039
21029900-0038R1 | Electrical - LLP02 - Honeywell Gas Detection Panels with Internal Component Parts R1 | RFI-0038R1_Electrical_LLP02_Honeywell_Gas_Detection_Panels_W_Internal_Component_Parts_ RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 01_11_00 | 44586.6119 | Item | sites/1232505342/CMiC RFI Response | 0038R1
21029900-0038 | Electrical - LLP02 - Honeywell Gas Detection Panels with Internal Component Parts | RFI-0058 Process - LLE01 - CPCW Heat Exchanger Dimensions RESPONSE (1282931249).pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 01_11_00 | 44586.6122 | Item | sites/1232505342/CMiC RFI Response | 0038
21029900-0037 R1 | Electrical - LLP02 – Siemens Tool Annunciation SystemR1 | RFI-0037R1 Electrical - LLP02 Siemens Tool Annunciation SystemR1 RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 01_11_00 | 44586.6122 | Item | sites/1232505342/CMiC RFI Response | 0037 R1
21029900-0036 | I and C - LLP02 - Panel Procurement Confirmation | RFI-0036 I and C - LLP02 - Panel Procurement Confirmation RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 25_14_01_00 | 44586.6125 | Item | sites/1232505342/CMiC RFI Response | 0036
21029900-0035 | Mechanical - LLP02 - Phase 2 RAH Procurement | RFI-0035 Mechanical - LLP02 - Phase 2 RAH Procurement RESPONSE.pdf | Answered - Complete | INTEL NETWORK SYSTEMS INC (Mark Harrington) |  |  | 44586.7004 | Item | sites/1232505342/CMiC RFI Response | 0035
21029900-0034 | Process - LLP02 - High Vacuum Process Vacuum Receiver Tank MSB1-TK221-1-60 | RFI-0034 Process - LLP02 - High Vacuum Process Vacuum Receiver Tank MSB1-TK221-1-60 RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 43_41_13_10 | 44586.6121 | Item | sites/1232505342/CMiC RFI Response | 0034
21029900-0033 | Electrical - LLE01 - Acid Scrubber Exhaust Fan VFD | RFI-0033 Electrical - LLE01 - Acid Scrubber Exhaust Fan VFD RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 26_29_65_00 | 44586.612 | Item | sites/1232505342/CMiC RFI Response | 0033
21029900-0032R1 | Mechanical - LLP02 - Carbonator System Procurement R1 | RFI-0032R1 Mechanical - LLP02 - Carbonator System Procurement R1 RESPONSE.pdf | Answered - Complete | INTEL NETWORK SYSTEMS INC (Mark Harrington) |  |  | 44586.6123 | Item | sites/1232505342/CMiC RFI Response | 0032R1
21029900-0031 | Process - LLE01 - RA4- TK252-1-00 Outlet Nozzle Size | RFI-0031 Process - LLE01 - RA4- TK252-1-00 Outlet Nozzle Size RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44586.601 | Item | sites/1232505342/CMiC RFI Response | 0031
21029900-0030 | Mechanical - LLP02 - IMO Cooling Coil Latent Load Confirmation | RFI-0030 Mechanical - LLP02 - IMO Cooling Coil Latent Load Confirmation RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | CC102-01-30 | 44586.5623 | Item | sites/1232505342/CMiC RFI Response | 0030
21029900-0029 | Mechanical - LLP02 - ATTD Coil Temperatures | RFI-0029 Mechanical - LLP02 - ATTD Coil Temperatures RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | CC102-01-30 | 44586.5635 | Item | sites/1232505342/CMiC RFI Response | 0029
21029900-0028R1 | Mechanical - LLP02- Dry Cooling Coils Approved Manufacturers R1 | RFI-0028R1 Mechanical - LLP02- Dry Cooling Coils Approved Manufacturers R1 RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 23_82_16_61 | 44586.5621 | Item | sites/1232505342/CMiC RFI Response | 0028R1
21029900-0027 | Process - LLP02 - Pump Capacity and Differential Head Requirements | RFI-0027 Process - LLP02 - Pump Capacity and Differential Head Requirements RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40_05_15_51 | 44586.562 | Item | sites/1232505342/CMiC RFI Response | 0027
21029900-0026 | Process -LLP02 - RA4 Split Case Pump Conformation | RFI-0026 Process -LLP02 - RA4 Split Case Pump Conformation RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40_05_15_51 | 44586.5622 | Item | sites/1232505342/CMiC RFI Response | 0026
21029900-0025 | Process - OMI-HB-IMO - LLE01- MSB- Tank Vacuum Rating | RFI-0025 Process - OMI-HB-IMO - LLE01- MSB- Tank Vacuum Rating RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44586.5514 | Item | sites/1232505342/CMiC RFI Response | 0025
21029900-0024 | Mechanical - LLE01 RA4 - Sort North RAH Condensate Drain Line Conformation | RFI-0024 Mechanical - LLE01 RA4 - Sort North RAH Condensate Drain Line Conformation RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 45_43_13_67 | 44586.5625 | Item | sites/1232505342/CMiC RFI Response | 0024
21029900-0023 | Mechanical_LLE01_RA4_Sort North_RAH_Piping_Stubbed_Connections. | RFI-0023 Mechanical_LLE01_RA4_Sort North_RAH_Piping_Stubbed_Connections RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 45_43_13_67 | 44586.5621 | Item | sites/1232505342/CMiC RFI Response | 0023
21029900-0022 | Mechanical - OMI-HB-IMO - LLE01 - RA4 - Sort North RAH VFD for Fan Walls | RFI-0022 Mechanical - OMI-HB-IMO - LLE01 - RA4 - Sort North RAH VFD for Fan Walls RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 45_43_13_67 | 44586.5618 | Item | sites/1232505342/CMiC RFI Response | 0022
21029900-0021 | Mechanical - OMI-HB-IMO - LLE01 - RA4 - Sort North RAH Control Panel Conformation | RFI-0021 Mechanical - OMI-HB-IMO - LLE01 - RA4 - Sort North RAH Control Panel Conformation.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 45_43_13_67 | 44586.5619 | Item | sites/1232505342/CMiC RFI Response | 0021
21029900-0020 | Mechanical - OMI-HB-IMO - LLE01 - RA4 - Sort North RAH End Switch Conformation | RFI-0020 Mechanical - OMI-HB-IMO - LLE01 - RA4 - Sort North RAH End Switch Conformation RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 45_43_13_67 | 44586.5617 | Item | sites/1232505342/CMiC RFI Response | 0020
21029900-0019 | Mechanical - OMI-HB-IMO - LLE01- Grease Spec Conformation | RFI-0019 Mechanical - OMI-HB-IMO - LLE01- Grease Spec Conformation RESPONSE - VOID.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 23_34_00_02 | 44519.4915 | Item | sites/1232505342/CMiC RFI Response | 0019
21029900-0018 | LLE- OMI-HB-IMO - LLE01 - C4 Descope QB Items | RFI-0018 LLE- OMI-HB-IMO - LLE01 - C4 Descope QB Items RESPONSE.pdf | Closed | INTEL NETWORK SYSTEMS INC (Mark Harrington) |  |  | 44586.552 | Item | sites/1232505342/CMiC RFI Response | 0018
21029900-0017 | Structural - RA4 Steel Angle Clip Detail | RFI-0017 Structural - RA4 Steel Angle Clip Detail RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44586.5519 | Item | sites/1232505342/CMiC RFI Response | 0017
21029900-0016 | B0001-CPK01-R1 IFC | RFI-016 B0001-CPK01-R1 IFC RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44574.6544 | Item | sites/1232505342/CMiC RFI Response | 0016
21029900-0015 | Wet - Mech - LLE01 Filter Pressure Ratings | RFI-0015 Wet - Mech - LLE01 Filter Pressure Ratings RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44586.5519 | Item | sites/1232505342/CMiC RFI Response | 0015
21029900-0014 | Process - LLE01 Mech MSB01 - PCV Positioner Input | RFI-0014 Process - LLE01 Mech MSB01 - PCV Positioner Input RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44586.5513 | Item | sites/1232505342/CMiC RFI Response | 0014
21029900-0013 | I and C - LLE01 - Port Device Coupler Conformation | RFI-0013 I and C - LLE01 - Port Device Coupler Conformation RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 25_14_01_00_PBSP | 44586.5518 | Item | sites/1232505342/CMiC RFI Response | 0013
21029900-0012 | Process - RA4 - PMP299 Material Confirmation | RFI-0012 Process - RA4 - PMP299 Material Confirmation RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | RA4-299-D0-Z08 | 44586.5516 | Item | sites/1232505342/CMiC RFI Response | 0012
21029900-0010 | Process - LLE01 -RA4 - CMS299 LLE01 Mixers | RFI-0010 Process - LLE01 -RA4 - CMS299 LLE01 Mixers RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44610.3773 | Item | sites/1232505342/CMiC RFI Response | 0010
21029900-0009 | Structural - LLE01 - RA4 - Catwalk Design Criteria | RFI-0009 Structural - LLE01 - RA4 - Catwalk Design Criteria RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44586.5378 | Item | sites/1232505342/CMiC RFI Response | 0009
21029900-0008R1 | I and C - LLE01 - PMP275 Data Sheets and Package R1 | RFi-0008.1 I and C - LLE01 - PMP275 Data Sheets and Package R1 RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40_05_15_16 | 44586.538 | Item | sites/1232505342/CMiC RFI Response | 0008R1
21029900-0008 | I and C - LLE01 - PMP275 Data Sheets and Package | RFI-0008 I and C - LLE01 - PMP275 Data Sheets and Package RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  | 40_05_15_16 | 44574.6563 | Item | sites/1232505342/CMiC RFI Response | 0008
21029900-0007 | Process - LLE01 - RA4 - BCS Tank Dimension | RFI-0007 Process - LLE01 - RA4 - BCS Tank Dimension RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44586.526 | Item | sites/1232505342/CMiC RFI Response | 0007
21029900-0006 | RA4 - LLE01 - Sort North RAH | RFI-0006 RA4 - LLE01 - Sort North RAH RESPONSE.pdf | Closed | INTEL NETWORK SYSTEMS INC (Mark Harrington) |  |  | 44586.7001 | Item | sites/1232505342/CMiC RFI Response | 0006
21029900-0005 | Electrical - LLe01 - Acid Scrubber Exhaust Fan VFD | RFI-0005 Electrical - LLe01 - Acid Scrubber Exhaust Fan VFD RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44586.5195 | Item | sites/1232505342/CMiC RFI Response | 0005
21029900-0004 | Process - LLE01 - MS01 - Dome Topped Tanks | RFI-0004 Process - LLE01 - MS01 - Dome Topped Tanks RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44586.5534 | Item | sites/1232505342/CMiC RFI Response | 0004
21029900-0003 | MS01 RA4 L20A Revised Beams | RFI-0003 MS01 RA4 L20A Revised Beams RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44574.6456 | Item | sites/1232505342/CMiC RFI Response | 0003
21029900-0002 | B0001-CPK01-IFC JE Dunn Response | RFI-0002 B0001-CPK01-IFC JE Dunn Response RESPONSE.pdf | Answered - Complete | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44574.6455 | Item | sites/1232505342/CMiC RFI Response | 0002
21029900-0001 | Post-Installed Anchors at Waffle Slabs | RFI-0001 Post-Installed Anchors at Waffle Slabs RESPONSE.pdf | Closed | JACOBS ENGINEERING GROUP INC (Document Control) |  |  | 44586.5132 | Item | sites/1232505342/CMiC RFI Response | 0001
|  | RFI-0002 B0001-CPK01-IFC JE Dunn Response RESPONSE (1278158561).pdf |  |  |  |  | 44495.9424 | Item | sites/1232505342/CMiC RFI Response
|  | RFI-0104 Electrical - CPK03-R2 - RA4 - INSTALL PMD - RESPONSE.pdf |  |  |  |  | 44540.4698 | Item | sites/1232505342/CMiC RFI Response
|  | RFI-0060 Process - LLP02 - BCS Scrubber Pumps RA4-PMP252-1-2-40 Duty Point RESPONSE.pdf |  |  |  |  | 44564.603 | Item | sites/1232505342/CMiC RFI Response
|  | RFI-0125 Structural - RA4 - CPK02-R2 - Inside Wall Sheet Metal.pdf |  |  |  |  | 44566.7095 | Item | sites/1232505342/CMiC RFI Response
|  | RFI00173_ DRY MECH RESPONSE.pdf |  |  |  |  | 44580.3918 | Item | sites/1232505342/CMiC RFI Response
|  | RFI-0077 Structural-Mechanical - RA4 -CPK02-R1 Additional Framing Support for MAH Duct RESPONSE (1297449896).pdf |  |  |  |  | 44595.6811 | Item | sites/1232505342/CMiC RFI Response
|  | RFI-0093 Mechanical-CPK02-RA4 Make Up Air Flex Confirmation RESPONSE.pdf |  |  |  |  | 44595.7017 | Item | sites/1232505342/CMiC RFI Response
|  | RFI-0096 Mechanical-CPK02-R2 RA4 MAU Penetrations Clashes and Relocation RESPONSE (2).pdf |  |  |  |  | 44595.7092 | Item | sites/1232505342/CMiC RFI Response
|  | RFI-0144 Dry Mech-CPK02-R2-RA4 Air Coils Fluid Temp Change Confirmation RESPONSE (1297478180).pdf |  |  |  |  | 44595.7158 | Item | sites/1232505342/CMiC RFI Response
|  | RFI-0155 Dry Mech-CPK02-R2-RA4- Spring Isolation on RAH Recirculation Air Design RESPONSE (1297478229).pdf |  |  |  |  | 44595.7159 | Item | sites/1232505342/CMiC RFI Response
|  | RFI-0268 DRY MECH-CPK02-R2-RA4 EXGF Blast Gate Vs Damper Confirmation RESPONSE (1297480353).pdf |  |  |  |  | 44595.7228 | Item | sites/1232505342/CMiC RFI Response
|  | RFI-0323 LSS - CPK02-R2 RA4 Existing Column Mounted FA and Security Devices - Confirming.pdf |  |  |  |  | 44600.668 | Item | sites/1232505342/CMiC RFI Response
|  | RFI-0326 Electrical - CPK02-R2 RA4 VFD135 Tag - Confirming.pdf |  |  |  |  | 44600.6988 | Item | sites/1232505342/CMiC RFI Response
|  | RFI-0124-R1-CSA-CPK02-R2-Sheet Metal Sheathing Type Confirmation RESPONSE (1).pdf |  |  |  |  | 44606.1596 | Item | sites/1232505342/CMiC RFI Response
|  | RFI-0102 Mech-CSA-CPK02 RA4 Handrail Modification RESPONSE (1).pdf |  |  |  |  | 44606.4244 | Item | sites/1232505342/CMiC RFI Response
|  | RFI0413 - Mechanical - CPK03-R3 - In Row Cooling Unit Data Sheet Corrections - Response.pdf |  |  |  |  | 44607.3694 | Item | sites/1232505342/CMiC RFI Response
|  | RFI0288 - Mechanical - CPK03-R2 - Streimer RFI 18 - Damper Actuator Clashes - Response.pdf |  |  |  |  | 44609.6865 | Item | sites/1232505342/CMiC RFI Response
|  | RFI0468 - Mechanical - CPK03 - MSB - Streimer RFI 27 - Level 5 Roof Make Up Air Duct UPN.pdf |  |  |  |  | 44613.4204 | Item | sites/1232505342/CMiC RFI Response
|  | RFI-0082 - CSA - RA4 - CPK02-R2 - CRC Type Confirmation.pdf |  |  |  |  | 44613.496 | Item | sites/1232505342/CMiC RFI Response
|  | RFI-0301DRYMECH-ELEC-CPK02-RA4-Conduit Relocation at Grid E.5 and 13 of Sublab Level RESPONSE (1301550671).pdf |  |  |  |  | 44616.4385 | Item | sites/1232505342/CMiC RFI Response
|  | RFI-269 DRYMECH-ELEC-CPK02-R2 Conduit Relocation at Grid CD10.5.B and F RESPONSE.pdf |  |  |  |  | 44616.4392 | Item | sites/1232505342/CMiC RFI Response
|  | RFI-0293DRYMECH-CPK02-R2-DiffuserandSupplyGrillesCansVsCeilingGridConflictsRESPO.pdf |  |  |  |  | 44616.4394 | Item | sites/1232505342/CMiC RFI Response
|  | RFI-365R1 - CSA - CPK03-R2 MSB LVL2 HSS Cup Conflicts - R1 - RESPONSE.pdf |  |  |  |  | 44621.3712 | Item | sites/1232505342/CMiC RFI Response
|  | RFI-0293R1 DRY-MECH-CPK02-R2-RA4 Diffuser and Supply Grilles Cans Vs Ceiling Grid RESPONSE (1302636505).pdf |  |  |  |  | 44621.4296 | Item | sites/1232505342/CMiC RFI Response
|  | RFI-0598-Electrical- CPK03-R2 MXD1R51A and MXD1R51B- Relocation.pdf |  |  |  |  | 44622.5163 | Item | sites/1232505342/CMiC RFI Response
|  | RFI-0096R2-Mech-Proc-Elec-CPK02-CPK02-R2-South-MAU Penetrations Clashes and Relocation RESPONSE (1303184459).pdf |  |  |  |  | 44622.7681 | Item | sites/1232505342/CMiC RFI Response
|  | RFI-0589 DRYMECH-CPK02-R2-EXGF Duct and Damper Size Discrepancy RESPONSE.pdf |  |  |  |  | 44623.5722 | Item | sites/1232505342/CMiC RFI Response
|  | RFI-0554 CSA-ELC-CPK02-R2-RA4-Wall Clash Near Stockers RESPONSE.pdf |  |  |  |  | 44623.5723 | Item | sites/1232505342/CMiC RFI Response

## LATE PACKAGES
For Reference Only | Expected | Ping Greg
CPK03-R12

## INSTRUCTIONS & ASSUMPTIONS
1 | Package Owners
0 | Setup & Assumption
2 | IFC Drawing Page Compare
0 | Setup & Assumption
1 | Add package code to log as it is in the Package owner log, don't even hestitate to use absolute links.
2 | Insert New Pages and fill down formula for dates (macro coming soon)
3 | For now only IFCs are required to be in package compare. The owner log will notify when IFC is not in the compare log. DD sets may be added with the correct code if you wish to compare them.
4 | When inserting, cleanup list to be only drawing pages, delete headers, tags, and specs.
5 | Panels, Tags, Etc may appear in here since it is a bookmark export. Use judgment to decide what duplicates need to be reviewed. It is a tool to compare items you may expect to see in multiple packages
0 | Usage
1 | Select a drawing number
2 | Ctrl+Shift+F will filter for selection as drawing number.
3 | RFI Log
0 | Process
1 | Assign Pre-con to RFIs
2 | RFI should be complete and ready to post. If it is in cold storage but not in Answered RFIs (linking), rename properly and transfer. | 2b | If RFI is not complete or something is wrong. Mark incorrect. Batch these to Garret and Jenna.
3 | Post flag with proper naming throughout document sets.
4 | Slip sheet any new pages from RFIs